## Summary PSC Meeting
| Actual | Budget
| RM | RM
Billing | 11980879.4 | 45500000
Revenue | 18005150.3995 | 45500000
Budget cost |  | 36394200
Actual cost | 22614999.0534
Accrued/Deferred cost | -8450000
| 14164999.0534 | 36394200
Margin | 3840151.3461 | 9105800
% | 21.33% | 20.01%

## Summary Executive
| PROJECT TITLE | : | Fomema Foreign Worker Medical Examination System (FWMES) integration with myIMMS, Department of Immagiration Malaysia and Biometric verification of Foreoign Worker in Malaysia
| PROJECT CODE | : | SAD-FOMEMA
| CUSTOMER | : | FOMEMA SDN BHD
| CONTRACT NO. | :
| PROJECT DURATION | : | 7 years - after loa issuance date
| REPORT AS AT | : | 30/11/2018
a) | Status of Project Work
| Total contract | : | 45500000
| HHS | : | 45500000
b) | Status of Project Revenue
|  |  | TOTAL | HHS
| Payment received | : | 10622439.37 | 10622439.37
| Billing | : | 11980879.4 | 11980879.4
| Balance to be bill | : | 41726415.09 | 41726415.09
| Total | : | 64329733.86 | 64329733.86
| % Actual vs budget (based on billing) | : | 26.33% | 26.33%
| Invoice Status | : | Date issued | RM | Invoice No | Ageing (days) | Payment Status
|  |  | 03.03.2017 | 3773584.91 | 1817000459 |  | PAID 3.04.2017
|  |  | 15.06.2017 | 1415094.34 | 1817001257 |  | PAID 07.07.2017
|  |  | 06.07.2017 | 1358440.03 | 1817001315 |  | PAID 26.10.2017
|  |  | 29.12.2017 | 1358440.03 | 1817002556 |  | PAID 15.02.2018
|  |  | 10.04.2018 | 1358440.03 | 1818000482 |  | PAID 30.05.2018
|  |  | 12.07.2018 | 1358440.03 | 1818001529 |  | PAID 03.09.2018
|  |  | 10.10.2018 | 1358440.03 | 1818002054 |  | PENDING
| Total Invoice Issued |  |  | 11980879.4
c) | Status of Project Cost
| WBS |  | HHS | TOTAL
| Budgetted Costs |  | 36394200 | 36394200
| Actual Costs Incurred |  | 22211328.97 | 22211328.97
| % actual vs budget |  | 61.03% | 61.03%
Please view respective actual costs for details.
d) | Project Financial Status |  | 30/11/2018
| DESCRIPTION |  | YTD P&L 2017 |  | CUMULATIVE PROJECT |  | CONTRACT
|  |  | RM |  | RM |  | RM
Revenue
| HHS |  | 3773584.91 |  | 18005150.3995 |  | 45500000
| Revenue recognition |  | 6024270.9995 |  | 6024270.9995
| Total Inflow |  | 9797855.9095 |  | 24029421.3989 |  | 45500000
Costs
| HHS | [5 empty] | 36394200
| Actual Costs |  | 6496609.79 |  | 22211328.97
| Cost Recognition |  | 0 |  | 0
| Total Outflow |  | 6496609.79 |  | 22211328.97 |  | 36394200
| Net Inflow / (Outflow) |  | 3301246.1195 |  | 1818092.4289 |  | 9105800
| Margin |  | 33.69% |  | 7.566% |  | 20.01%
| % Actual vs Budget |  | HHS | TOTAL
| Revenue (based on billing) |  | 26.33% | 26.33%
| Costs ( actual costs incurred) |  | 61.03% | 61.03%
| Variance |  | -34.7% | -34.7%

## Summary
Summary Details
|  | CONTRACT VALUE |  |  |  | REVENUE |  |  |  | COSTS |  |  |  | MARGIN
WBS | SCOPE OF WORK | Revenue | Costs | Margin |  | Actual Revenue | Revenue Accrued 2016 | Total Revenue | Balance to be bill | Actual Costs | COE/SALARY | Costs Accrued | Total Costs | Actual Margin | % | Recognised Margin | %
SAD-FOMEMA |  | 45500000 | 36394200 | 9105800 | 20.01% | 11980879.4 |  | 11980879.4 | 33519120.6 | 22341767.99 |  |  | 22341767.99 | -10360888.59 | -86.48% | -10360888.59 | -86.48% | SAD-SPPCD | TBS
[13 empty] | 0 | 0 |  | 0
SAD-FOMEMA-01SA | Application Development, Training and Test | 1805509.434 | 1476200 | 329309.434 | 18.24% | 11980879.4 | 6024270.9995 | 18005150.3995 | -10175369.966 | 1028119.6 |  | 0 | 1028119.6 | 10952759.8 | 91.42% | 16977030.7995 | 94.29%
SAD-FOMEMA-02DC | Data Center Hardware and Services | 2366000 | 728000 | 1638000 | 69.23% | 0 |  | 0 | 2366000 | 107281.62 |  | 0 | 107281.62 | -107281.62 | #DIV/0! | -107281.62 | #DIV/0!
SAD-FOMEMA-03SH | FingerPrint Device and Deployment | 7378867.9245 | 3606000 | 3772867.9245 | 51.13% | 0 |  | 0 | 7378867.9245 | 3418208.93 |  |  | 3418208.93 | -3418208.93 |  | -3418208.93
SAD-FOMEMA-04SA | Consultancy Services | 6370000 | 7886336.97 | -1516336.97 | -23.8% | 0 |  | 0 | 6370000 | 9207718.82 |  |  | 9207718.82 | -9207718.82 | #DIV/0! | -9207718.82 | #DIV/0!
|  | 17920377.3585 | 13696536.97 | 4223840.3885 | 23.57% | 11980879.4 | 6024270.9995 | 18005150.3995 | 5939497.9585 | 13761328.97 | 0 | 0 | 13761328.97 | -1780449.57 | -14.86% | 4243821.4295 | 23.57%
WBS | SCOPE OF WORK | Revenue | Costs | Margin |  | Actual Revenue | Revenue Accrued 2016 | Total Revenue | Balance to be bill | Actual Costs | COE/SALARY | Costs Accrued | Total Costs | Actual Margin | % | Recognised Margin | %
SAD-FOMEMA-06SA | Finance Charges |  | 600000 | -600000 | #DIV/0! | 0 |  |  |  | 130439.02
|  | 0 | 600000 | -600000 | #DIV/0! | 0 |  | 0 | 0 | 130439.02 |  | 130439.02 | 0 | 0 | #REF! | 0
WBS | SCOPE OF WORK | Revenue | Costs | Margin |  | Actual Revenue | Revenue Accrued 2016 | Total Revenue | Balance to be bill | Actual Costs | COE/SALARY | Costs Accrued | Total Costs | Actual Margin | % | Recognised Margin | %
SAD-FOMEMA-05MS | Annual Maintenance for 10 Years | 27579622.6415 | 22097663.03 | 5481959.6115 | 19.88% | 0 |  | 0 | 27579622.6415 | 8450000 |  | -4725000 | 3725000 | -8450000 | #DIV/0! | -3725000 | #DIV/0!
|  | 27579622.6415 | 22097663.03 | 5481959.6115 | 19.88% | 0 |  | 0 | 27579622.6415 | 8450000 | 0 | -4725000 | 3725000 | -8450000 | #DIV/0! | -3725000
| OVERALL | 45500000 | 35794200 | 9705800 | 21.33% | [10 empty] | -14604710.0195
% of cost completion
|  | Rev recognition | 18005150.3995
|  | Billing | 11980879.4
6024270.9995
| DR 220001 DI | 6024270.9995
| CR 411001 SAD-FOMEMA-01SA |  | 6024270.9995

## BILLING
Invoice no |  |  | 1817000459 | 1817001257 | 1817001315 | 1817002556 | 1818000482 | 1818001529 | 1818002054
Date |  |  | 03.03.2017 | 15.06.2017 | 06.07.2017 | 29.12.2017 | 10.04.2018 | 12.07.2018 | 10.10.2018
Status |  |  | PAID 3.04.2017 | PAID 07.07.2017 | 26.10.2017 | 15.02.2018 | paid 30.05.2018 | paid 03.09.2018 | PENDING
WBS | SCOPE OF WORK | Revenue | Billing 1 | Billing 2 | Billing 3 | Billing 4 | Billing 5 | Billing 6 | Billing 7 | Total Billing | Balance to be bill
SAD-FOMEMA |  | 45500000 | 3773584.91 | 1415094.34 | 1358440.03 | 1358440.03 | 1358440.03 | 1358440.03 | 1358440.03 | 11980879.4 | 33519120.6 | TBS
SAD-FOMEMA-01SA | Application Development, Training and Test | 1805509.434 | 3773584.91 | 1415094.34 | 1358440.03 | 1358440.03 | 1358440.03 | 1358440.03 | 1358440.03 | 11980879.4 | -1968075.476
SAD-FOMEMA-02DC | Data Center Hardware and Services | 2366000 | [7 empty] | 0 | 2366000
SAD-FOMEMA-03SH | FingerPrint Device and Deployment | 7378867.9245 | [7 empty] | 0 | 7378867.9245
SAD-FOMEMA-04SA | Consultancy Services | 6370000 | [7 empty] | 0 | 6370000
SAD-FOMEMA-05MS | Annual Maintenance for 10 Years | 27579622.6415 | [7 empty] | 0 | 27579622.6415
SAD-FOMEMA-06SA | Finance Charges | [8 empty] | 0
|  | 45500000 | 3773584.91 | 1415094.34 | 1358440.03 | 1358440.03 | 1358440.03 | 1358440.03 | 1358440.03 | 11980879.4 | 41726415.09
|  |  | 226415.0946 | 84905.6604 | 81506.4018 | 81506.4018 | 81506.4018 | 81506.4018 | 81506.4018 | 718852.764
|  |  | 4000000.0046 | 1500000.0004 | 1439946.4318 | 1439946.4318 | 1439946.4318 | 1439946.4318 | 1439946.4318 | 12699732.164

## COST
Postg Date | DocumentNo | RefDocNo | Cost Elem. | WBS Element | ValCOArCur | Name | Cost element descr. | Doc. Text | OffAc.name | Purchase order text | BusA | 01SA | 02DC | 03SH | 04SA | 05MS | 06SA
20.03.2017 | 100209868 | 5000012259 | 512001 | SAD-FOMEMA -03SH -C | -330188 |  | PROJECT IMPLEMENTATION |  | GR.IR | DEPLOYMENT SERVICES FOR FOMEMA MyIMMS | HSS |  |  | -330188
20.03.2017 | 100209870 | 5000012261 | 512001 | SAD-FOMEMA -03SH -C | -320188.68 |  | PROJECT IMPLEMENTATION |  | GR.IR | DEPLOYMENT SERVICES FOR FOMEMA MyIMMS | HSS |  |  | -320188.68
20.03.2017 | 100209872 | 5000012263 | 512001 | SAD-FOMEMA -03SH -C | -330188.68 |  | PROJECT IMPLEMENTATION |  | GR.IR | DEPLOYMENT SERVICES FOR FOMEMA MyIMMS | HSS |  |  | -330188.68
20.03.2017 | 100209866 | 5000012257 | 512001 | SAD-FOMEMA -03SH -C | 330188 |  | PROJECT IMPLEMENTATION |  | GR.IR | DEPLOYMENT SERVICES FOR FOMEMA MyIMMS | HSS |  |  | 330188
20.03.2017 | 100209869 | 5000012260 | 512001 | SAD-FOMEMA -03SH -C | 320188.68 |  | PROJECT IMPLEMENTATION |  | GR.IR | DEPLOYMENT SERVICES FOR FOMEMA MyIMMS | HSS |  |  | 320188.68
20.03.2017 | 100209871 | 5000012262 | 512001 | SAD-FOMEMA -03SH -C | 330188.68 |  | PROJECT IMPLEMENTATION |  | GR.IR | DEPLOYMENT SERVICES FOR FOMEMA MyIMMS | HSS |  |  | 330188.68
20.03.2017 | 100209873 | 5000012264 | 512001 | SAD-FOMEMA -03SH -C | 330188.68 |  | PROJECT IMPLEMENTATION |  | GR.IR | DEPLOYMENT SERVICES FOR FOMEMA MyIMMS | HSS |  |  | 330188.68
20.03.2017 | 100209865 | 5000012256 | 512001 | SAD-FOMEMA -04SA -C | 1900800 |  | PROJECT IMPLEMENTATION | 1900800 | GR.IR | FOMEMA BIOMETRIC MIDDLEWARE DEVELOPMENT | HSS |  |  |  | 1900800
20.03.2017 | 100209867 | 5000012258 | 512001 | SAD-FOMEMA -04SA -C | 672610.38 |  | PROJECT IMPLEMENTATION |  | GR.IR | THE SCOPE OF WORK FOR FOMEMA's | HSS |  |  |  | 672610.38
27.03.2017 | 100210265 | 5000012300 | 524001 | SAD-FOMEMA -03SH -C | 660000 |  | COST OF HARDWARE AND SOFTWARE |  | GR.IR | BIOMETRIC FINGERPRINT SCANNERS | HSS |  |  | 660000
01.05.2017 | 100215109 | 117001576 | 512001 | SAD-FOMEMA -03SH -C | 1.65 | SERVICE CHARGES FR FUND TRANSFER TO CYBERTECH | PROJECT IMPLEMENTATION | SERVICE CHARGES | RHBi ESC FOMEMA-OG |  | HSS |  |  | 1.65
01.05.2017 | 100214983 | 117001577 | 512001 | SAD-FOMEMA -03SH -C | 5 | SERVICE CHARGES FR FUND TRANSFER TO KHALIFAT LIMA | PROJECT IMPLEMENTATION | SERVICE CHARGES | RHBi ESC FOMEMA-OG |  | HSS |  |  | 5
01.05.2017 | 100215109 | 117001576 | 512001 | SAD-FOMEMA -04SA -C | 3.35 | SERVICE CHARGES FR FUND TRANSFER TO CYBERTECH | PROJECT IMPLEMENTATION | SERVICE CHARGES | RHBi ESC FOMEMA-OG |  | HSS |  |  |  | 3.35
01.05.2017 | 100214982 | 117001575 | 512001 | SAD-FOMEMA -04SA -C | 5 | SERVICE CHARGES FR FUND TRANSFER TO BEANS GROUP | PROJECT IMPLEMENTATION | SERVICE CHARGES | RHBi ESC FOMEMA-OG |  | HSS |  |  |  | 5
08.05.2017 | 100212797 | 5000012529 | 524001 | SAD-FOMEMA -02DC -C | 7930 |  | COST OF HARDWARE AND SOFTWARE |  | GR.IR | MACBOOK APPLE | HSS |  | 7930
08.05.2017 | 100212797 | 5000012529 | 524001 | SAD-FOMEMA -02DC -C | 3980 |  | COST OF HARDWARE AND SOFTWARE |  | GR.IR | HPN SWITCH | HSS |  | 3980
14.06.2017 | 100217191 | 117002368 | 512001 | SAD-FOMEMA -03SH -C | 12249.53 | CHARGES ACCEPTED COMMISION-KAYANGAN CAHAYA SB | PROJECT IMPLEMENTATION | CHARGES ISSUANCE OF BA | AMBANK ISLAMIC OG |  | HSS |  |  | 12249.53
14.06.2017 | 100217191 | 117002368 | 512001 | SAD-FOMEMA -03SH -C | 2 | CHARGES ON CABLE (RENTAS)-KAYANGAN CAHAYA SB | PROJECT IMPLEMENTATION | CHARGES ISSUANCE OF BA | AMBANK ISLAMIC OG |  | HSS |  |  | 2
15.06.2017 | 100215620 | 5000012705 | 524001 | SAD-FOMEMA -03SH -C | 4725000 |  | COST OF HARDWARE AND SOFTWARE |  | GR.IR | BIOMETRIC INTEGRATION, VERIFICATION AND | HSS | 1000000 |  |  |  | 3725000
19.06.2017 | 100215786 | 5000012718 | 512001 | SAD-FOMEMA -02DC -C | 14000 |  | PROJECT IMPLEMENTATION |  | GR.IR | 42U RACK AND ACCSESSORIES | HSS |  | 14000
19.06.2017 | 100215786 | 5000012718 | 512001 | SAD-FOMEMA -02DC -C | 79200 |  | PROJECT IMPLEMENTATION |  | GR.IR | x3650 M5 (2x 8Core, 32GB RAM, 2x 1TB HDD | HSS |  | 79200
19.06.2017 | 100215811 | 5000012722 | 512001 | SAD-FOMEMA -04SA -C | 1900800 |  | PROJECT IMPLEMENTATION |  | GR.IR | FOMEMA BIOMETRIC MIDDLEWARE DEVELOPMENT | HSS |  |  |  | 1900800
06.07.2017 | 100216908 | 5000012762 | 524001 | SAD-FOMEMA -03SH -C | 220000 |  | COST OF HARDWARE AND SOFTWARE |  | GR.IR | BIOMETRIC FINGERPRINT SCANNERS | HSS |  |  | 220000
10.07.2017 | 100219609 | 5000012940 | 512001 | SAD-FOMEMA -03SH -C | 1269811.32 |  | PROJECT IMPLEMENTATION |  | GR.IR | DEPLOYMENT SERVICES FOR FOMEMA MyIMMS | HSS |  |  | 1269811.32
10.07.2017 | 100219607 | 5000012939 | 512001 | SAD-FOMEMA -04SA -C | 634776.1 |  | PROJECT IMPLEMENTATION |  | GR.IR | THE SCOPE OF WORK FOR FOMEMA's | HSS |  |  |  | 634776.1
11.07.2017 | 100219611 | 117002888 | 512001 | SAD-FOMEMA -03SH -C | 5 | BANK CHARGES FOR FUND TRANSFER -CYBERTECH SECURITY | PROJECT IMPLEMENTATION | BANK CHARGES | RHBi ESC FOMEMA-OG |  | HSS |  |  | 5
11.07.2017 | 100219612 | 117002889 | 512001 | SAD-FOMEMA -04SA -C | 5 | BANK CHARGES FOR FUND TRANSFER -CYBERTECH SECURITY | PROJECT IMPLEMENTATION | BANK CHARGES | RHBi ESC FOMEMA-OG |  | HSS |  |  |  | 5
31.07.2017 | 100218227 | 1917004792 | 509004 | SAD-FOMEMA -01SA -C | 7572 | MAJLIS PELANCARAN SISTEM BIOMETRIK PEKERJA ASING | TRAVELLING - ENTERTAINMENT | MAJLIS PELANCARAN SISTEM | RIMBUNAN SELERA |  | HSS | 7572
08.08.2017 | 100219165 | 5000012874 | 512001 | SAD-FOMEMA -04SA -C | 1267200 |  | PROJECT IMPLEMENTATION |  | GR.IR | FOMEMA BIOMETRIC MIDDLEWARE DEVELOPMENT | HSS |  |  |  | 1267200
14.08.2017 | 100219275 | 5000012904 | 512001 | SAD-FOMEMA -04SA -C | 950400 |  | PROJECT IMPLEMENTATION |  | GR.IR | FOMEMA BIOMETRIC MIDDLEWARE DEVELOPMENT | HSS |  |  |  | 950400
04.09.2017 | 100222113 | 117003313 | 512001 | SAD-FOMEMA -04SA -C | 5 | BANK CHARGES FOR FUND TRANSFER TO KHALIFAT LIMA SB | PROJECT IMPLEMENTATION | BANK CHARGES | RHBi ESC FOMEMA-OG |  | HSS |  |  |  | 5
27.09.2017 | 100221629 | 5000013068 | 524001 | SAD-FOMEMA -03SH -C | 880000 |  | COST OF HARDWARE AND SOFTWARE |  | GR.IR | BIOMETRIC FINGERPRINT SCANNERS | HSS |  |  | 880000
31.10.2017 | 100224699 | 2517005145 | 509001 | SAD-FOMEMA -01SA -C | 869.05 | CLAIM SEPTEMBER 2017-SCM15102017 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | 2566.SEPT-OCT 17 | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 869.05
31.10.2017 | 100224565 | 2517005067 | 509001 | SAD-FOMEMA -01SA -C | 21 | GCG201710300026 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | MAS MALINY BINTI MAT |  | HSS | 21
31.10.2017 | 100224565 | 2517005067 | 509001 | SAD-FOMEMA -01SA -C | 39.9 | GCG201710300026 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | MAS MALINY BINTI MAT |  | HSS | 39.9
31.10.2017 | 100224703 | 2517005143 | 509001 | SAD-FOMEMA -01SA -C | 578.05 | CLAIM 2566.JUL-AUG 17-SCM15102017 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | 2566.JUL-AUG 17 | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 578.05
31.10.2017 | 100224699 | 2517005145 | 512001 | SAD-FOMEMA -01SA -C | 232 | CLAIM SEPTEMBER 2017-SCM15102017 | PROJECT IMPLEMENTATION | 2566.SEPT-OCT 17 | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 232
31.10.2017 | 100224703 | 2517005143 | 512001 | SAD-FOMEMA -01SA -C | 4160 | CLAIM 2566.JUL-AUG 17-SCM15102017 | PROJECT IMPLEMENTATION | 2566.JUL-AUG 17 | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 4160
03.10.2017 | 100224273 | 117003787 | 512001 | SAD-FOMEMA -03SH -C | 45935.75 | SETTLEMNT OF BA FAC W AMISLAMIC (KAYANGAN CHY SB) | PROJECT IMPLEMENTATION | SETTLEMENT OF BA FACILITY | AMBANK ISLAMIC OG |  | HSS |  |  | 45935.75
31.10.2017 | 100224461 | 117003921 | 512001 | SAD-FOMEMA -03SH -C | 5 | BANK CHARGES FOR FUND TRANSFER -CYBERTECH SECURITY | PROJECT IMPLEMENTATION | BANK CHARGES | RHBi ESC FOMEMA-OG |  | HSS |  |  | 5
31.10.2017 | 100224462 | 117003922 | 512001 | SAD-FOMEMA -03SH -C | 5 | BANK CHARGES FOR FUND TRANSFER -CYBERTECH SECURITY | PROJECT IMPLEMENTATION | BANK CHARGES | RHBi ESC FOMEMA-OG |  | HSS |  |  | 5
25.10.2017 | 100223530 | 5000013194 | 512001 | SAD-FOMEMA -04SA -C | 242950.49 |  | PROJECT IMPLEMENTATION |  | GR.IR | 'THE SCOPE OF WORK FOR FOMEMA's | HSS |  |  |  | 242950.49
28.11.2017 | 100225945 | 5000013429 | 512001 | SAD-FOMEMA -02DC -C | 1500 |  | PROJECT IMPLEMENTATION |  | GR.IR | PROFESSIONAL SERVICE LUMP SUM | HSS |  | 1500
30.11.2017 | 100226235 | 1917007821 | 512001 | SAD-FOMEMA -04SA -C | 4550 | PHOTO SERVICE & VIDEOGRAPHY - FOMEMA | PROJECT IMPLEMENTATION | SOFT LAUNCH EXPENSES CLAI | ISHAMMUDDIN BIN RAZAMAN |  | HSS |  |  |  | 4550
30.11.2017 | 100226235 | 1917007821 | 512001 | SAD-FOMEMA -04SA -C | 2500 | ROLL UP BACKDROP & BIOMETRIC LEAFLETS - FOMEMA | PROJECT IMPLEMENTATION | SOFT LAUNCH EXPENSES CLAI | ISHAMMUDDIN BIN RAZAMAN |  | HSS |  |  |  | 2500
30.11.2017 | 100226235 | 1917007821 | 512001 | SAD-FOMEMA -04SA -C | 860 | SEWA PERALATAN BANQUET MAJLIS PELANCARAN BIOMETRIK | PROJECT IMPLEMENTATION | SOFT LAUNCH EXPENSES CLAI | ISHAMMUDDIN BIN RAZAMAN |  | HSS |  |  |  | 860
04.12.2017 | 100229128 | 117004730 | 512001 | SAD-FOMEMA -04SA -C | 5 | BANK CHARGES FOR FUND TRANSFER-KHALIFAT LIMA SB | PROJECT IMPLEMENTATION | BANK CHARGES | RHBi ESC FOMEMA-OG |  | HSS | 5
29.12.2017 | 100228230 | 2517006297 | 507001 | SAD-FOMEMA -01SA -C | 605.04 | GCG201711200006 | MAINTENANCE OF NODES & DISASTER RECOVERY | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 605.04
29.12.2017 | 100228230 | 2517006297 | 509001 | SAD-FOMEMA -01SA -C | 33.8 | GCG201711200006 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 33.8
29.12.2017 | 100228230 | 2517006297 | 509001 | SAD-FOMEMA -01SA -C | 33.8 | GCG201711200006 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 33.8
29.12.2017 | 100228230 | 2517006297 | 509001 | SAD-FOMEMA -01SA -C | 39 | GCG201711200006 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 39
29.12.2017 | 100228230 | 2517006297 | 509001 | SAD-FOMEMA -01SA -C | 39 | GCG201711200006 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 39
29.12.2017 | 100228230 | 2517006297 | 509001 | SAD-FOMEMA -01SA -C | 33.8 | GCG201711200006 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 33.8
29.12.2017 | 100228230 | 2517006297 | 509001 | SAD-FOMEMA -01SA -C | 33.8 | GCG201711200006 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 33.8
29.12.2017 | 100228230 | 2517006297 | 509001 | SAD-FOMEMA -01SA -C | 33.8 | GCG201711200006 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 33.8
29.12.2017 | 100228230 | 2517006297 | 509001 | SAD-FOMEMA -01SA -C | 33.8 | GCG201711200006 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 33.8
29.12.2017 | 100229322 | 2517006944 | 509001 | SAD-FOMEMA -01SA -C | 403.05 | CLAIM 2566.DEC 17-SCM15122017 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | 2566.DEC 17 | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 403.05
29.12.2017 | 100228230 | 2517006297 | 509004 | SAD-FOMEMA -01SA -C | 180 | GCG201711200006 | TRAVELLING - ENTERTAINMENT | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 180
29.12.2017 | 100228230 | 2517006297 | 509004 | SAD-FOMEMA -01SA -C | 180 | GCG201711200006 | TRAVELLING - ENTERTAINMENT | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 180
29.12.2017 | 100228230 | 2517006297 | 512001 | SAD-FOMEMA -01SA -C | 384 | GCG201711200006 | PROJECT IMPLEMENTATION | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 384
29.12.2017 | 100228230 | 2517006297 | 512001 | SAD-FOMEMA -01SA -C | 464.02 | GCG201711200006 | PROJECT IMPLEMENTATION | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 464.02
29.12.2017 | 100228230 | 2517006297 | 512001 | SAD-FOMEMA -01SA -C | 232 | GCG201711200006 | PROJECT IMPLEMENTATION | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 232
29.12.2017 | 100228230 | 2517006297 | 512001 | SAD-FOMEMA -01SA -C | 348.02 | GCG201711200006 | PROJECT IMPLEMENTATION | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 348.02
29.12.2017 | 100228230 | 2517006297 | 512001 | SAD-FOMEMA -01SA -C | 360 | GCG201711200006 | PROJECT IMPLEMENTATION | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 360
29.12.2017 | 100228230 | 2517006297 | 512001 | SAD-FOMEMA -01SA -C | 440.02 | GCG201711200006 | PROJECT IMPLEMENTATION | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 440.02
29.12.2017 | 100228230 | 2517006297 | 512001 | SAD-FOMEMA -01SA -C | 520 | GCG201711200006 | PROJECT IMPLEMENTATION | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 520
|  |  |  | total 2017 | 15845158.2 | [6 empty] | 1017873.95 | 106610 | 3418208.93 | 7577465.32 | 3725000 | 0
22.01.2018 | 100229864 | 5000013692 | 512001 | SAD-FOMEMA -06SA -C | 63000 |  | PROJECT IMPLEMENTATION |  | GR.IR | FOMEMA BIOMETRIC CR03 CHANGE REQUEST | HSS | [5 empty] | 63000
22.01.2018 | 100229867 | 5000013695 | 512001 | SAD-FOMEMA -06SA -C | 21600 |  | PROJECT IMPLEMENTATION |  | GR.IR | FOMEMA-MyIMMS BIOMETRIC INTEGRATION | HSS | [5 empty] | 21600
24.01.2018 | 100229971 | 5000013715 | 512001 | SAD-FOMEMA -04SA -C | 242950.49 |  | PROJECT IMPLEMENTATION |  | GR.IR | 'THE SCOPE OF WORK FOR FOMEMA's | HSS |  |  |  | 242950.49
25.01.2018 | 100229992 | 1918000205 | 509002 | SAD-FOMEMA -06SA -C | 33339.62 | END USER TRAINING FOR FOMEMA12 - 14 JAN 2018 | TRAVELLING - ACCOMMODATION AND LAUNDRY | END USER TRAINING FOR FOM | FORTUNE VALLEY SDN BHD |  | HSS | [5 empty] | 33339.62
31.01.2018 | 100230992 | 5000013783 | 512001 | SAD-FOMEMA -04SA -C | 242950.49 |  | PROJECT IMPLEMENTATION |  | GR.IR | 'THE SCOPE OF WORK FOR FOMEMA's | HSS |  |  |  | 242950.49
20.02.2018 | 100231150 | 2518000373 | 509001 | SAD-FOMEMA -01SA -C | 33.8 | GCG201802010025 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 33.8
20.02.2018 | 100231150 | 2518000373 | 509001 | SAD-FOMEMA -01SA -C | 33 | GCG201802010025 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 33
20.02.2018 | 100231150 | 2518000373 | 509001 | SAD-FOMEMA -01SA -C | 79.4 | GCG201802010025 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 79.4
20.02.2018 | 100231150 | 2518000373 | 509001 | SAD-FOMEMA -01SA -C | 45 | GCG201802010025 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 45
20.02.2018 | 100231150 | 2518000373 | 509001 | SAD-FOMEMA -01SA -C | 33.8 | GCG201802010025 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 33.8
20.02.2018 | 100231150 | 2518000373 | 509001 | SAD-FOMEMA -01SA -C | 33.8 | GCG201802010025 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 33.8
20.02.2018 | 100231150 | 2518000373 | 509001 | SAD-FOMEMA -01SA -C | 51 | GCG201802010025 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 51
20.02.2018 | 100231150 | 2518000373 | 509001 | SAD-FOMEMA -01SA -C | 72.95 | GCG201802010025 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 72.95
20.02.2018 | 100231150 | 2518000373 | 509001 | SAD-FOMEMA -01SA -C | 39 | GCG201802010025 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 39
20.02.2018 | 100231150 | 2518000373 | 509001 | SAD-FOMEMA -01SA -C | 20.5 | GCG201802010025 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 20.5
20.02.2018 | 100231150 | 2518000373 | 509001 | SAD-FOMEMA -01SA -C | 46.8 | GCG201802010025 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 46.8
20.02.2018 | 100231150 | 2518000373 | 509001 | SAD-FOMEMA -01SA -C | 42.9 | GCG201802010025 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 42.9
20.02.2018 | 100231150 | 2518000373 | 509001 | SAD-FOMEMA -01SA -C | 48 | GCG201802010025 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | GENERAL CLAIM | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 48
14.02.2018 | 100230908 | 5000013775 | 512001 | SAD-FOMEMA -04SA -C | 316800 |  | PROJECT IMPLEMENTATION |  | GR.IR | FOMEMA BIOMETRIC MIDDLEWARE DEVELOPMENT | HSS |  |  |  | 316800
13.02.2018 | 100230813 | 2518000186 | 509001 | SAD-FOMEMA -06SA -C | 196.3 | CLAIM 6709.JAN 17-SCM15022018 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | 6709.JAN 17 | ROZAIMI BIN RAMLI |  | HSS | [5 empty] | 196.3
13.02.2018 | 100230818 | 2518000187 | 509001 | SAD-FOMEMA -06SA -C | 205.35 | CLAIM 8314.JAN 17-SCM15022018 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | 8314.JAN 17 | MAS MALINY BINTI MAT |  | HSS | [5 empty] | 205.35
13.02.2018 | 100230813 | 2518000186 | 509003 | SAD-FOMEMA -06SA -C | 486 | CLAIM 6709.JAN 17-SCM15022018 | TRAVELLING - SUBSISTENCE | 6709.JAN 17 | ROZAIMI BIN RAMLI |  | HSS | [5 empty] | 486
13.02.2018 | 100230818 | 2518000187 | 509003 | SAD-FOMEMA -06SA -C | 486 | CLAIM 8314.JAN 17-SCM15022018 | TRAVELLING - SUBSISTENCE | 8314.JAN 17 | MAS MALINY BINTI MAT |  | HSS | [5 empty] | 486
21.02.2018 | 100231264 | 2518000413 | 509001 | SAD-FOMEMA -06SA -C | 263.25 | CLAIM 9110.JAN 18-SCM15022018 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | 9110.JAN 18 | HAMINUDIN BIN HAMZAH |  | HSS | [5 empty] | 263.25
21.02.2018 | 100231266 | 2518000411 | 509001 | SAD-FOMEMA -06SA -C | 415.3 | CLAIM 9139.JAN 18-SCM15022018 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | 9139.JAN 18 | MUHAMMAD AZHAR BIN ABD RAHIM |  | HSS | [5 empty] | 415.3
21.02.2018 | 100231264 | 2518000413 | 512001 | SAD-FOMEMA -06SA -C | 540 | CLAIM 9110.JAN 18-SCM15022018 | PROJECT IMPLEMENTATION | 9110.JAN 18 | HAMINUDIN BIN HAMZAH |  | HSS | [5 empty] | 540
21.02.2018 | 100231266 | 2518000411 | 512001 | SAD-FOMEMA -06SA -C | 270 | CLAIM 9139.JAN 18-SCM15022018 | PROJECT IMPLEMENTATION | 9139.JAN 18 | MUHAMMAD AZHAR BIN ABD RAHIM |  | HSS | [5 empty] | 270
28.02.2018 | 100231899 | 5000013833 | 509005 | SAD-FOMEMA -06SA -C | 9000 |  | TRAVELLING - TRANSPORTATION |  | GR.IR | COST ESTIMATION FOR 2 WAY | HSS | [5 empty] | 9000
01.03.2018 | 100234067 | 118000556 | 512001 | SAD-FOMEMA -04SA -C | 5 | BANK CHARGES FOR FUND TRNFR-BEANS GROUP SDN BHD | PROJECT IMPLEMENTATION | BANK CHARGES | RHBi ESC FOMEMA-OG |  | HSS |  |  |  | 5
01.03.2018 | 100234069 | 118000557 | 512001 | SAD-FOMEMA -04SA -C | 5 | BANK CHARGES FOR FUND TRNFR-CYBERTECH SECURITY | PROJECT IMPLEMENTATION | BANK CHARGES | RHBi ESC FOMEMA-OG |  | HSS |  |  |  | 5
26.03.2018 | 100233201 | 2518001025 | 509001 | SAD-FOMEMA -06SA -C | 85.8 | CLAIM 7654.JAN 18-SCM15032018 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | 7654.JAN 18 | MUHAMMAD HAKIMAN BIN HAMZAH |  | HSS | [5 empty] | 85.8
26.03.2018 | 100233201 | 2518001025 | 509003 | SAD-FOMEMA -06SA -C | 216 | CLAIM 7654.JAN 18-SCM15032018 | TRAVELLING - SUBSISTENCE | 7654.JAN 18 | MUHAMMAD HAKIMAN BIN HAMZAH |  | HSS | [5 empty] | 216
02.04.2018 | 100236030 | 118001170 | 512001 | SAD-FOMEMA -03SH -C | 2 | BANK CHARGES FOR FUND TRANSFER TO KHALIFAT | PROJECT IMPLEMENTATION | BANK CHARGES | RHBi ESC FOMEMA-OG |  | HSS |  | 2
02.04.2018 | 100236031 | 118001171 | 512001 | SAD-FOMEMA -03SH -C | 5 | BANK CHARGES FOR FUND TRANSFER TO BEANS GROUP | PROJECT IMPLEMENTATION | BANK CHARGES | RHBi ESC FOMEMA-OG |  | HSS |  | 5
13.04.2018 | 100234520 | 1918002138 | 509004 | SAD-FOMEMA -06SA -C | 180 | PAYMENT FOR CATERING 23.10.2017 | TRAVELLING - ENTERTAINMENT | PAYMENT FOR CATERING 23.1 | ALINA CATERING & CANOPY |  | HSS | [5 empty] | 180
20.04.2018 | 100234935 | 2518001486 | 509001 | SAD-FOMEMA -06SA -C | 35.1 | CLAIM 926.FEB 18-SCM15042018 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | 926.FEB 18 | HAMID BIN BAHARDIN @ BAHARUDIN |  | HSS | [5 empty] | 35.1
20.04.2018 | 100234935 | 2518001486 | 512001 | SAD-FOMEMA -06SA -C | 54 | CLAIM 926.FEB 18-SCM15042018 | PROJECT IMPLEMENTATION | 926.FEB 18 | HAMID BIN BAHARDIN @ BAHARUDIN |  | HSS | [5 empty] | 54
30.04.2018 | 100235689 | 2518001784 | 509001 | SAD-FOMEMA -06SA -C | 20.8 | CLAIM 2940.MAR 18-SCM15042018 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | 2940.MAR 18 | HARUN BIN BIDON |  | HSS | [5 empty] | 20.8
31.05.2018 | 100237538 | 2518002313 | 509001 | SAD-FOMEMA -01SA -C | 638.9 | CLAIM 2566.MAR-APR 18-SCM15052018 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | 2566.MAR-APR 18 | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 638.9
31.05.2018 | 100237538 | 2518002313 | 509004 | SAD-FOMEMA -01SA -C | 1026.8 | CLAIM 2566.MAR-APR 18-SCM15052018 | TRAVELLING - ENTERTAINMENT | 2566.MAR-APR 18 | AHMAD SURYADI BIN ABDUL AZIZ |  | HSS | 1026.8
31.05.2018 | 100237544 | 5000014216 | 512001 | SAD-FOMEMA -04SA -C | 242950.49 |  | PROJECT IMPLEMENTATION |  | GR.IR | 'THE SCOPE OF WORK FOR FOMEMA's | HSS |  |  |  | 242950.49
30.06.2018 | 100239597 | 118001954 | 512001 | SAD-FOMEMA -04SA -C | 5 | BANK CHARGES FOR FUND TRANSFER -CYBERTECH SECURITY | PROJECT IMPLEMENTATION | BANK CHARGES | RHBi ESC FOMEMA-OG |  | HSS |  |  |  | 5
28.8.2018 | 100242102 | 5000014537 | 512001 | SAD-FOMEMA -04SA -C | 257527.52 |  | PROJECT IMPLEMENTATION |  | GR/IR | 'THE SCOPE OF WORK FOR FOMEMA's | HSS |  |  |  | 257527.52
30.8.2018 | 100242890 | 5000014602 | 524001 | SAD-FOMEMA -03SH -C | 4725000 |  | COST OF HARDWARE AND SOFTWARE |  | GR/IR | BIOMETRIC INTEGRATION, VERIFICATION AND | HSS |  |  |  |  | 4725000
4.9.2018 | 100243933 | 118003094 | 512001 | SAD-FOMEMA -04SA -C | 5 | BANK CHARGES FOR FUND TRANSFER -CYBERTECH SECURITY | PROJECT IMPLEMENTATION | BANK CHARGES | RHBi ESC FOMEMA-OG |  | HSS |  |  |  | 5
28.9.2018 | 100244661 | 2518004620 | 509001 | SAD-FOMEMA -06SA -C | 45.5 | CLAIM 8706/AUG 18-SCM15092018 | TRAVELLING - MILEAGE,AIRFARES,TOL & PARK | 8706/AUG 18 | MUHAMMAD SHAHADAN BIN SHAHRIR |  | HSS | [5 empty] | 45.5
31.10.2018 | 100245925 | 5000014816 | 512001 | SAD-FOMEMA -02DC -C | 627 |  | PROJECT IMPLEMENTATION |  | GR/IR | FTP SITE HOSTING FOR FOMEMA DRIVER FILES | HSS |  | 627
31.10.2018 | 100246073 | 5105612093 | 512001 | SAD-FOMEMA -02DC -C | 37.62 |  | PROJECT IMPLEMENTATION | FTP SITE HOSTING FOR FOME | EXABYTES NETWORK SDN BHD | FTP SITE HOSTING FOR FOMEMA DRIVER FILES | HSS |  | 37.62
14.11.2018 | 100246897 | 5000014890 | 512001 | SAD-FOMEMA -01SA -C | 8000 |  | PROJECT IMPLEMENTATION |  | GR/IR | JOGET WORKFLOW TRAINING FOR FOMEMA | HSS | 8000
30.11.2018 | 100247432 | 5000014936 | 512001 | SAD-FOMEMA -04SA -C | -242950.49 |  | PROJECT IMPLEMENTATION |  | GR/IR | THE SCOPE OF WORK FOR FOMEMA's | HSS |  |  |  | -242950.49
30.11.2018 | 100247443 | 5000014937 | 512001 | SAD-FOMEMA -04SA -C | 570000 |  | PROJECT IMPLEMENTATION |  | GR/IR | consultancy services | HSS |  |  |  | 570000
30.11.2018 | 100247909 | 118004268 | 512001 | SAD-FOMEMA -04SA -C | 5 | BANK CHARGES FOR FUND TRANSFER -CYBERTECH SECURITY | PROJECT IMPLEMENTATION | BANK CHARGES | RHBi ESC-OG (FOMEMA) |  | HSS |  |  |  | 5
|  |  |  | total 2018 | 6496609.79 | [6 empty] | 10245.65 | 671.62 | 0 | 1630253.5 | 4725000 | 130439.02
|  |  |  | total | 22341767.99 | [6 empty] | 1028119.6 | 107281.62 | 3418208.93 | 9207718.82 | 8450000 | 130439.02 | 22341767.99 | 0
salary
|  |  |  | 01.01.2018 | 18988.6994
|  |  |  | 01.02.2018 | 19553.6398
|  |  |  | 01.03.2018 | 26039.9239
|  |  |  | 01.04.2018 | 26331.3506
|  |  |  | 01.05.2018 | 26332.3816
|  |  |  | 01.06.2018 | 26446.2182
|  |  |  | 01.07.2018 | 26443.3702
|  |  |  | 01.08.2018 | 26542.4503
|  |  |  | 01.09.2018 | 26614.0318
|  |  |  | 01.10.2018 | 26717.6406
|  |  |  | 01.11.2018 | 23221.3569
01.12.2018
273231.0634

## salary
Account | Assignment | Document Number | Document Type | Posting Key | Document Date | Posting Date | Posting period | Reference | Text | Amount in local currency | Local Currency | Business Area | WBS element | Profit Center | Cost Center | Customer | Vendor
501001 | 20180128 | 118000053 | AB | 40 | 2018-01-29 | 2018-01-28 | 1 | HRPAY00001 |  | 12600 | MYR | PSG |  | HSS10603 | HSS10603
501003 | 20180128 | 118000053 | AB | 40 | 2018-01-29 | 2018-01-28 | 1 | HRPAY00001 |  | 50 | MYR | PSG |  | HSS10603 | HSS10603
503001 | 20180128 | 118000053 | AB | 40 | 2018-01-29 | 2018-01-28 | 1 | HRPAY00001 |  | 1558 | MYR | PSG |  | HSS10603 | HSS10603
503002 | 20180128 | 118000053 | AB | 40 | 2018-01-29 | 2018-01-28 | 1 | HRPAY00001 |  | 153.9 | MYR | PSG |  | HSS10603 | HSS10603
14361.9
501001 | 20180228 | 118000272 | AB | 40 | 2018-02-27 | 2018-02-28 | 2 | HRPAY00001 |  | 12600 | MYR | PSG |  | HSS10603 | HSS10603
501003 | 20180228 | 118000272 | AB | 40 | 2018-02-27 | 2018-02-28 | 2 | HRPAY00001 |  | 50 | MYR | PSG |  | HSS10603 | HSS10603
503001 | 20180228 | 118000272 | AB | 40 | 2018-02-27 | 2018-02-28 | 2 | HRPAY00001 |  | 1558 | MYR | PSG |  | HSS10603 | HSS10603
503002 | 20180228 | 118000272 | AB | 40 | 2018-02-27 | 2018-02-28 | 2 | HRPAY00001 |  | 153.9 | MYR | PSG |  | HSS10603 | HSS10603
14361.9
501001 | 20180328 | 118000518 | AB | 40 | 2018-03-28 | 2018-03-28 | 3 | HRPAY00001 |  | 19530 | MYR | PSG |  | HSS10603 | HSS10603
501003 | 20180328 | 118000518 | AB | 40 | 2018-03-28 | 2018-03-28 | 3 | HRPAY00001 |  | 130 | MYR | PSG |  | HSS10603 | HSS10603
503001 | 20180328 | 118000518 | AB | 40 | 2018-03-28 | 2018-03-28 | 3 | HRPAY00001 |  | 2398 | MYR | PSG |  | HSS10603 | HSS10603
503002 | 20180328 | 118000518 | AB | 40 | 2018-03-28 | 2018-03-28 | 3 | HRPAY00001 |  | 230.85 | MYR | PSG |  | HSS10603 | HSS10603
22288.85
501001 | 20180428 | 118001163 | AB | 40 | 2018-04-26 | 2018-04-28 | 4 | HRPAY00001 |  | 19530 | MYR | PSG |  | HSS10603 | HSS10603
501003 | 20180428 | 118001163 | AB | 40 | 2018-04-26 | 2018-04-28 | 4 | HRPAY00001 |  | 130 | MYR | PSG |  | HSS10603 | HSS10603
503001 | 20180428 | 118001163 | AB | 40 | 2018-04-26 | 2018-04-28 | 4 | HRPAY00001 |  | 2398 | MYR | PSG |  | HSS10603 | HSS10603
503002 | 20180428 | 118001163 | AB | 40 | 2018-04-26 | 2018-04-28 | 4 | HRPAY00001 |  | 230.85 | MYR | PSG |  | HSS10603 | HSS10603
22288.85
501001 | 20180528 | 118001534 | AB | 40 | 2018-05-28 | 2018-05-28 | 5 | HRPAY00001 |  | 19530 | MYR | PSG |  | HSS10603 | HSS10603
501003 | 20180528 | 118001534 | AB | 40 | 2018-05-28 | 2018-05-28 | 5 | HRPAY00001 |  | 130 | MYR | PSG |  | HSS10603 | HSS10603
503001 | 20180528 | 118001534 | AB | 40 | 2018-05-28 | 2018-05-28 | 5 | HRPAY00001 |  | 2398 | MYR | PSG |  | HSS10603 | HSS10603
503002 | 20180528 | 118001534 | AB | 40 | 2018-05-28 | 2018-05-28 | 5 | HRPAY00001 |  | 230.85 | MYR | PSG |  | HSS10603 | HSS10603
22288.85
501001 | 20180628 | 118001927 | AB | 40 | 2018-06-26 | 2018-06-28 | 6 | HRPAY00001 |  | 19530 | MYR | PSG |  | HSS10603 | HSS10603
501003 | 20180628 | 118001927 | AB | 40 | 2018-06-26 | 2018-06-28 | 6 | HRPAY00001 |  | 130 | MYR | PSG |  | HSS10603 | HSS10603
503001 | 20180628 | 118001927 | AB | 40 | 2018-06-26 | 2018-06-28 | 6 | HRPAY00001 |  | 2398 | MYR | PSG |  | HSS10603 | HSS10603
503002 | 20180628 | 118001927 | AB | 40 | 2018-06-26 | 2018-06-28 | 6 | HRPAY00001 |  | 230.85 | MYR | PSG |  | HSS10603 | HSS10603
22288.85
501001 | 20180728 | 118002406 | AB | 40 | 2018-07-31 | 2018-07-28 | 7 | HRPAY00001 |  | 19530 | MYR | PSG |  | HSS10603 | HSS10603
501003 | 20180728 | 118002406 | AB | 40 | 2018-07-31 | 2018-07-28 | 7 | HRPAY00001 |  | 130 | MYR | PSG |  | HSS10603 | HSS10603
503001 | 20180728 | 118002406 | AB | 40 | 2018-07-31 | 2018-07-28 | 7 | HRPAY00001 |  | 2398 | MYR | PSG |  | HSS10603 | HSS10603
503002 | 20180728 | 118002406 | AB | 40 | 2018-07-31 | 2018-07-28 | 7 | HRPAY00001 |  | 230.85 | MYR | PSG |  | HSS10603 | HSS10603
22288.85
501001 | 20180828 | 118002837 | AB | 40 | 2018-08-30 | 2018-08-28 | 8 | HRPAY00001 |  | 19530 | MYR | PSG |  | HSS10603 | HSS10603
501003 | 20180828 | 118002837 | AB | 40 | 2018-08-30 | 2018-08-28 | 8 | HRPAY00001 |  | 130 | MYR | PSG |  | HSS10603 | HSS10603
503001 | 20180828 | 118002837 | AB | 40 | 2018-08-30 | 2018-08-28 | 8 | HRPAY00001 |  | 2398 | MYR | PSG |  | HSS10603 | HSS10603
503002 | 20180828 | 118002837 | AB | 40 | 2018-08-30 | 2018-08-28 | 8 | HRPAY00001 |  | 230.85 | MYR | PSG |  | HSS10603 | HSS10603
22288.85
501001 | 20180928 | 118003006 | AB | 40 | 2018-09-28 | 2018-09-28 | 9 | HRPAY00001 |  | 19530 | MYR | PSG |  | HSS10603 | HSS10603
501003 | 20180928 | 118003006 | AB | 40 | 2018-09-28 | 2018-09-28 | 9 | HRPAY00001 |  | 130 | MYR | PSG |  | HSS10603 | HSS10603
503001 | 20180928 | 118003006 | AB | 40 | 2018-09-28 | 2018-09-28 | 9 | HRPAY00001 |  | 2398 | MYR | PSG |  | HSS10603 | HSS10603
503002 | 20180928 | 118003006 | AB | 40 | 2018-09-28 | 2018-09-28 | 9 | HRPAY00001 |  | 230.85 | MYR | PSG |  | HSS10603 | HSS10603
22288.85
501001 | 20181028 | 118003677 | AB | 40 | 30.10.2018 | 28.10.2018 | 10 | HRPAY00001 |  | 19530 | MYR | PSG |  | HSS10603 | HSS10603
501003 | 20181028 | 118003677 | AB | 40 | 30.10.2018 | 28.10.2018 | 10 | HRPAY00001 |  | 130 | MYR | PSG |  | HSS10603 | HSS10603
503001 | 20181028 | 118003677 | AB | 40 | 30.10.2018 | 28.10.2018 | 10 | HRPAY00001 |  | 2398 | MYR | PSG |  | HSS10603 | HSS10603
503002 | 20181028 | 118003677 | AB | 40 | 30.10.2018 | 28.10.2018 | 10 | HRPAY00001 |  | 230.85 | MYR | PSG |  | HSS10603 | HSS10603
22288.85
501001 | 20181128 | 118004186 | AB | 40 | 28.11.2018 | 28.11.2018 | 11 | HRPAY00001 |  | 19530 | MYR | PSG |  | HSS10603 | HSS10603
501003 | 20181128 | 118004186 | AB | 40 | 28.11.2018 | 28.11.2018 | 11 | HRPAY00001 |  | 130 | MYR | PSG |  | HSS10603 | HSS10603
503001 | 20181128 | 118004186 | AB | 40 | 28.11.2018 | 28.11.2018 | 11 | HRPAY00001 |  | 2398 | MYR | PSG |  | HSS10603 | HSS10603
503002 | 20181128 | 118004186 | AB | 40 | 28.11.2018 | 28.11.2018 | 11 | HRPAY00001 |  | 230.85 | MYR | PSG |  | HSS10603 | HSS10603
22288.85

## Recognition
| RECOGNITION |  |  |  |  | Cost
|  | RECOGNITION |  | POSTING |  |  |  | RECOGNITION |  | POSTING
|  | DR | CR | DR | CR |  |  | DR | CR | DR | CR
3 | DR 110601 DE | 557408.61 |  | 557408.61
| CR 411001 SAD-FOMEMA-01SA |  | 557408.61 |  | 557408.61
4 | DR 220001 DI | 1320556.6521 |  | 763148.0421
| CR 411001 SAD-FOMEMA-01SA |  | 1320556.6521 |  | 763148.0421
5 | DR 220001 DI | 1337603.3617 |  | 17046.7096
| CR 411001 SAD-FOMEMA-01SA |  | 1337603.3617 |  | 17046.7096
6 | DR 220001 DI | 2790432.4696 |  | 1452829.1079 | [5 empty] | 4725000
| CR 411001 SAD-FOMEMA-01SA |  | 2790432.4696 |  | 1452829.1079 | [5 empty] | 4725000
7 | DR 220001 DI | 4479914.6882 |  | 1689482.2186
| CR 411001 SAD-FOMEMA-01SA |  | 4479914.6882 |  | 1689482.2186
8 | DR 220001 DI | 7649959.3924 |  | 3170044.7042 |  | 6 | DR 110601 | 4725000 |  | 4725000
| CR 411001 SAD-FOMEMA-01SA |  | 7649959.3924 |  | 3170044.7042 |  | CR 524001 SAD-FOMEMA-03SH-ACC |  | 4725000 |  | 4725000
9 | DR 220001 DI | 8907920.7876 |  | 1257961.3952 |  | 6 | DR 110601 | 4725000 |  | 4725000
| CR 411001 SAD-FOMEMA-01SA |  | 8907920.7876 |  | 1257961.3952 |  | CR 524001 SAD-FOMEMA-03SH-ACC |  | 4725000 |  | 4725000
10 | DR 220001 DI | 9329330.0857 |  | 421409.2981 |  | 6 | DR 110601 | 4725000 |  | 4725000
| CR 411001 SAD-FOMEMA-01SA |  | 9329330.0857 |  | 421409.2981 |  | CR 524001 SAD-FOMEMA-03SH-ACC |  | 4725000 |  | 4725000
11 | DR 220001 DI | 9342781.6192 |  | 13451.5335 |  | 6 | DR 110601 | 4725000 |  | 4725000
| CR 411001 SAD-FOMEMA-01SA |  | 9342781.6192 |  | 13451.5335 |  | CR 524001 SAD-FOMEMA-03SH-ACC |  | 4725000 |  | 4725000
12 | DR 220001 DI | 7876113.4318 |  | -1466668.1874 |  | 6 | DR 110601 | 4725000 |  | 4725000
| CR 411001 SAD-FOMEMA-01SA |  | 7876113.4318 |  | -1466668.1874 |  | CR 524001 SAD-FOMEMA-03SH-ACC |  | 4725000 |  | 4725000
2018
|  | RECOGNITION |  | POSTING |  |  |  | RECOGNITION |  | POSTING
|  | DR | CR | DR | CR |  |  | DR | CR | DR | CR
2 | DR 220001 DI | 9324469.8398 |  | 197388.3885 |  | 6 | DR 110601 | 4725000 |  | 4725000
| CR 411001 SAD-FOMEMA-01SA |  | 9324469.8398 |  | 197388.3885 |  | CR 524001 SAD-FOMEMA-03SH-ACC |  | 4725000 |  | 4725000
3 | DR 220001 DI | 9324915.5559 |  | 445.72 |  | 6 | DR 110601 | 3725000 |  | 3725000
| CR 411001 SAD-FOMEMA-01SA |  | 9324915.5559 |  | 445.72 |  | CR 524001 SAD-FOMEMA-03SH-ACC |  | 3725000 |  | 3725000
4 | DR 220001 DI | 9003319.6052 |  | 929372.0648 |  | 6 | DR 110601 | 3725000 |  | 3725000
| CR 411001 SAD-FOMEMA-01SA |  | 9003319.6052 |  | 929372.0648 |  | CR 524001 SAD-FOMEMA-03SH-ACC |  | 3725000 |  | 3725000
4 | DR 220001 DI | 7644888.7339 |  | -1358430.8713 |  | 6 | DR 110601 | 3725000 |  | 3725000
| CR 411001 SAD-FOMEMA-01SA |  | 7644888.7339 |  | -1358430.8713 |  | CR 524001 SAD-FOMEMA-03SH-ACC |  | 3725000 |  | 3725000
5 | DR 220001 DI | 7964941.4919 |  | 320052.758 |  | 6 | DR 110601 | 3725000 |  | 3725000
| CR 411001 SAD-FOMEMA-01SA |  | 7964941.4919 |  | 320052.758 |  | CR 524001 SAD-FOMEMA-03SH-ACC |  | 3725000 |  | 3725000
6 | DR 220001 DI | 7964948.0339 |  | 6.5419 |  | 6 | DR 110601 | 3725000 |  | 3725000
| CR 411001 SAD-FOMEMA-01SA |  | 7964948.0339 |  | 6.5419 |  | CR 524001 SAD-FOMEMA-03SH-ACC |  | 3725000 |  | 3725000
7 | DR 220001 DI | 6606508.0039 |  | -1358440.03 |  | 6 | DR 110601 | 3725000 |  | 3725000
| CR 411001 SAD-FOMEMA-01SA |  | 6606508.0039 |  | -1358440.03 |  | CR 524001 SAD-FOMEMA-03SH-ACC |  | 3725000 |  | 3725000
8 | DR 220001 DI | 6943453.7843 |  | 336945.7804 |  | 8 | DR 110601 | 4725000 |  | 4725000
| CR 411001 SAD-FOMEMA-01SA |  | 6943453.7843 |  | 336945.7804 |  | CR 524001 SAD-FOMEMA-03SH-ACC |  | 4725000 |  | 4725000
9 | DR 220001 DI | 6943460.3262 |  | 6.5419 |  | 9 | DR 110601 | 4725000 |  | 4725000
| CR 411001 SAD-FOMEMA-01SA |  | 6943460.3262 |  | 6.5419 |  | CR 524001 SAD-FOMEMA-03SH-ACC |  | 4725000 |  | 4725000
10 | DR 220001 DI | 5585889.8767 |  | -1357570.4495 |  | 10 | DR 110601 | 4725000 |  | 4725000
| CR 411001 SAD-FOMEMA-01SA |  | 5585889.8767 |  | -1357570.4495 |  | CR 524001 SAD-FOMEMA-03SH-ACC |  | 4725000 |  | 4725000
11 | DR 220001 DI | 6024270.9995 |  | 438381.1228 |  | 10 | DR 110601 | 4725000 |  | 4725000
| CR 411001 SAD-FOMEMA-01SA |  | 6024270.9995 |  | 438381.1228 |  | CR 524001 SAD-FOMEMA-03SH-ACC |  | 4725000 |  | 4725000
|  |  |  | 6024270.9995 | 6024270.9995
Revers Mac Posting
3 | DR 110601 DE | 557408.61
| CR 411001 SAD-FOMEMA-01SA |  | 557408.61
3 | DR 110601 DE | 557408.61
| CR 411001 SAD-FOMEMA-01SA |  | 557408.61

## costing
|  |  | Cost to HeiTech |  | Price to Fomema |  | Total
No | Desciptions | Vendor | Cost | Sub Total | Price | Sub Total | Margin |  | WBS | HSS10603
1 | Application Development, Training and Test | INTERNAL | 431200 |  | 1805509.434
|  | S5 | 1000000
|  | INTERNAL | 45000 | 1476200 | 0 | 1805509.434 | 329309.434 | 18.24% |  | SAD-FOMEMA-01SA
2 | Data Center Hardware and Services | VIP TOWER | 500000 |  | 1456000
|  | VIP TOWER | 228000 | 728000 | 910000 | 2366000 | 1638000 | 69.23% |  | SAD-FOMEMA-02DC
3 | FingerPrint Device and Deployment | S5 SDN BHD | 1984400 |  | 4892924.5283
|  | KHALIFAT 5 | 1621600 | 3606000 | 2485943.3962 | 7378867.9245 | 3772867.9245 | 51.13% |  | SAD-FOMEMA-03SH
4 | Consultancy Services | BEANS | 6336000 |  | 6370000
|  | CYBERTECH | 1550336.97 | 7886336.97 | 0 | 6370000 | -1516336.97 | -23.8% |  | SAD-FOMEMA-04SA
5 | Annual Maintenance for 10 Years | INTERNAL | 15038000 |  | 26164528.3019
|  | CYBERTECH | 6559663.03
|  | VIP TOWER | 500000 | 22097663.03 | 1415094.3396 | 27579622.6415 | 5481959.6115 | 19.88% |  | SAD-FOMEMA-05MS
| TOTAL |  |  | 35794200 |  | 45500000 | 9705800 | 21.33%
6 | Finance Charges |  | 600000 | 600000 | [5 empty] | SAD-FOMEMA-06SA
| GRAND TOTAL |  |  | 36394200 |  | 45500000 | 9105800 | 20.01%
| GST 6% |  |  | 2147652 |  | 2730000
|  |  |  | 38541852 |  | 48230000