## Project Status 2019 (hidden)
PROJECT STATUS AS OF 30 January 2020
No. | Customer | Project Name | Project Value (RM) | Project Start Date | Project End Date | Project Scope | Project Manager | Business Director/ Project Director | PMO Rep | Current Phase | New/Open Issue | Total Billed (RM) | Balance to Bill (RM) | Payment Received (RM) | Cost (RM) (as at 30/11/2019) | Status (as at 31 January 2019) | Status (as at 26 - 28/2/2019) | Status (as at 27/3/2019 & 28/3/2019) | Status (as at 31/5/2019) | Status (as at 31/8/2019) | Status (as at 30/9/2019) | Status (as at 31/10/2019) | Status (as at 30/11/2019) | Status (as at 31/12/2019) | Process Compliance November 2019
1 | JPJ | JPJ MAINTENANCE: MAINTENANCE AND TECHNICAL SUPPORT SERVICES FOR COMPUTER (HARDWARE AND SOFTWARE) AND RELATED PERIPHERALS | 6569161 | 2015-03-07 | 2016-03-06 | To provide maintenance services to JPJ & its business partners. Scope of maintenance works includes: 1. Provision of System Software License; 2. Equipment Maintenance Services; 3. JPJ Mini Disaster Recovery Facilities Services; 4. Data Centre Cleaning Services; and 5. On Request Maintenance Services. | Redzuan Abd Jalil | Abd Ghani Abdullah | NA | Closed | Pending payment to vendor. Finance to look into the matter (Closed) | 6569155.92 | 0 | 6569155.92
2 | JPJ | PRISM PROJECT: TO SUPPLY, DELIVER, INSTALL, CONFIGURE, TEST, COMMISSION AND MAINTAIN THE MAINFRAME SYSTEM HARDWARE AND SOFTWARE | 177000000 | 2014-09-12 | 2019-09-11 | 1. Data Centre Infrastructure Readiness 2. Supply, deliver, install, configure, test, commission and maintain the mainframe system hardware & software 3. Software upgrade services 4. Hardware & software Maintenance 5. Disaster Recovery Services 6. Hardware Decommission and Disposal 7. Training | Roslind Abd Rahman | Suhaizar Osman/ Azlan Abd Hamid | Mohd Hazly | Closed | 1. (PSC 9/2019) Related to IBM request to JPJ to perform software audit at JPJ, PUU of JPJ has responded not to allow the exercise to be done. IBM insisted to do it and has communicated to Project Team. To avoid any future implication to HeiTech, AM to meet and seek advice from Legal Team. (PSC 11/2019) Based on discussion with Legal, for this contract, IBM will not be able to take legal action for not allowing executing the software audit at JPJ Mainframe. To avoid Legal action for future project, AM to ensure in next contract must include necessary terms and condition on software audit to be in favor of HeiTech and customer. (Closed) | 176999773 | 227 | 176999773 | 119361623.75 | 1. Overall completion, Plan = 95%; Actual = 95% 2. Disaster Recovery = 84% 3. Corrective maintenance = 84% 4. Hardware preventive maintenance = 84% 5. Capacity Planning based on six months data done. Report preparation ready. Target presentation to JPJ on 30/1/2019. 6. Project Team planning to conduct workshop, PRISM five years way forward, target on 15 February 2019. | 1. Overall completion, Plan = 95%; Actual = 95% 2. Disaster Recovery = 84% 3. Corrective maintenance = 87% 4. Hardware preventive maintenance = 84% 5. Capacity Planning based on six months data done. Report preparation ready. Presentation to JPJ done on 11/2/2019. 6. PRISM five years way forward workshop, is planned to be conducted on 28/2/2019 - 1/3/2019. This is also as preparation for PRISM tender specification which current contract will be expiring in Sept 2019. | 1. Overall completion, Plan = 96%; Actual = 96% 2. Disaster Recovery = 89% 3. Corrective maintenance = 89% 4. Hardware preventive maintenance = 91%; Q1 PM activity and pending for report. Vendor will release report once payment is made. Finance to expedite payment. 5. PRISM five years way forward workshop, conducted on 28/2/2019 – 1/3/2019 | 1. Overall completion, Plan = 98%; Actual = 98% 2. Disaster Recovery = 94% 3. Corrective maintenance = 94% 4. Hardware preventive maintenance = 91%; Q1 PM activity and report completed. Work was approved for payment. Next PM activity target to be done in June 2019 and completed by 30/6/2019. | Note: No PSC slide for August 2019; no update from Project Team 1. Overall completion, Plan = 98%; Actual = 98% 2. Disaster Recovery = 97% 3. Corrective maintenance = 95% 4. Hardware preventive maintenance = 95% - Corrective maintenance on going – July 2019 – September 2019 - Disaster Recovery facility on going July 2019 – September 2019 - Report for CM & PM, problem log, system performance = July 2019 – September 2019 | Status update as at 27/9/2019 1. Overall completion = 100%; all work done. 2. Project closure with customer done. 3. Pending official Final Acceptance sign-off by customer. | Project closure. | Project Closure | Project Closure | NA
3 | JPJ | JPJ REVAMP PROJECT: PROJEK PEMBANGUNAN SEMULA SISTEM PENGKOMPUTERAN JABATAN | 282000000 | 2010-07-26 | 25-Jul-2015, 25-Jan-2016 | To provide development and maintenance services for the following areas: 1. Project Management 2. Test & Performance Management 3. Business Solutions Development 4. Organizational Change Management 5. Infrastructure, Integration & Implementation Services 6. Application Customization & Development (Core & Supporting Modules) | 1. Zuridah Hani 2. Hafazah Hafidz | Abd Ghani Abdullah | Lenny Ruby | Closed | Outstanding payment to vendors. To follow up with Finance.(Closed) | 282000000 | 0 | 281851000 | 1539950.356
4 | PUSPAKOM | PUSPAKOM: JPJ INTEGRATION | 824860.5 | 2012-07-11 | 2017-07-10 | 1. Development of web services for the integration 2. Deployment of hardware & software 3. Setup of network & infrastructure 4. Testing & commisioning | Azrul Saad | NA | Azrul Saad | Closed | 1. Puspakom don't want to sign-off closure acceptance since there is a module (Vehicle Plan) which JPJ has not implemented. PM to prepare a LOU stating that Project Team will support the module when JPJ decides to implement the module. LOU was submitted to PUSPAKOM on 5/4/2018 (Closed) | 837386.72 | -12526.22 | 795180.07 | 23033010.9773 |  |  | PCR for April 2018 not available (Jan 2018 = 93%) | PCR for April 2018 not available (Jan 2018 = 93%) | [5 empty] | PCR for April 2018 not available (Jan 2018 = 93%)
5 | JPJ | SURUHANJAYA PENGANGKUTAN AWAN DARAT | 458468 | 2013-06-18 | 2014-02-17 | 1. Application Development 2. System Integration - Internal System 3. System Integration - External System 4. Training & Documentation 5. Warranty Support 6. Network | Azrul Saad | NA | Azrul Saad | Closed | NA | 458468 | 0 | 458468 | 1354796.7345
6 | JPJ | eAuto eSTM (CR 2) | 194643 | 2015-12-02 | 2016-01-29 | To provide application development for eAuto eSTM system | Hafazah Hafidz | NA | NA | Closed | NA | 194643 | 0 | 194643 | 1088002.9668
7 | JIM | MyIMMs Application Maintenance | 27480000 | 2014-02-18 | 2016-02-17 | 1. Preventive Maintenance 2. Corrective Maintenance 3. Technical Support 4. Change Request 5. Training including Contract performance Review 6. Coordinate Technical Support Services 7. Reports | Ahmad Suryadi bin Abd Aziz | NA | A.Puzi, Sanuza | Closed | 1. SQL DB Locking Issue:Upgrade SQL Version to MSSQL 2012 – implemented at Menara Ikhlas, Kelana Jaya and Kajang Deployment of 1Chip project using a ‘straight thru’ process approach currently in progress. After One month monitoring, Straight Thru process identified had almost eliminated SQL DB Locking problem. Project team currently focus on hang symptom due to other sources. 2. Inaccuracy statistical report in eReporting Module. Resolution by the team in progress. 3. Pending payment of RM1.5mil due to SLA issue. Potential penalty for SLA breached and amount will be deducted from the RM1.5mil. (Closed) | 27480000 | 0 | 27480000 | 16018282.56
8 | JIM | MyIMMs Application Maintenance (2016-2017) | 21475600 | 2016-02-18 | 2017-08-17 | 1. Application Transformation 2. Corrective Maintenance & Enhancement 3. Training 4. Documentation 5. Fine tuning | Rohani Shariff Azlan Abd Hamid Selamat Ahmad (Transformasi) | Azlan Abd Hamid | A.Puzi, Sanuza | Closed | 1. Performance Issue: Taskforce lead by KDN has been created to resolve myIMMs performance issue at KLIA and KLIA2. Enhancement on Module of Kawalan has successfully deployed at both side. (Monitoring in progress). 2. CR on Rehiring Program issue. It has been decided that CR to be billed to KDN. BTMR urged to exclude 4 CR (RM133,475) which has been issued during last contract period ended 16/2/2016.(Closed) 3. Contract pending sign-off from JIM (Closed) 4. Delay in development activity under Transformation scope due to lack of resources. SDC and HR to assist on recruitment. (In Progress) 5. No. of SL records has identified not tally between local server and host. The downloading programs has enhanced to webservice methodology using IP instead of ordinary SNA. BTMR requires daily monitoring especially for main Entry Exit points KLIA, KLIA2, BSI, KSAB etc Webservice sometime found halted due to huge connection to local database. Rectification on UIDM program currently in progress.New proposal on mysql to be by solution team has been prepared.Implementation in progress under new contract. (In Progress) 6. Upload offline transaction records to host issue. Team to analyse and find solution to resolve. (In Progress) *Solution will be implemented in the new contract 7. Inaccuracy statistical report in eReporting Module. New timeline of 12 weeks action plan has submitted to JIM on 7 issues identified for major cause of inaccuracy reports. (Closed) 8. SOW for Perluasan dan Perpindahan has exceeded no. of location per year agreed in the contract. PBD request HTP to proceed with new branch installation activity as instructed by ministry. HTP to come out with a formal letter with the quotation to JIM. (Closed) 9. Potential penalty due to SLA breached. Total penalty as of end of contract period is RM442,893. PM to further negotiate for discount. Based on assessment, any further appeal will result in greater LAD. (Closed) 10. myIMM integration projects (PIB, eGate, ESD Portal and MBIKE) non-compliance issues: a) Tailoring checklist is not produced b) Project documentation is not present c) Contracts not available d) Risk list not updated Project team to close issue by mid October 2017. Project Team has provided the audit response to the issues raised (Closed) | 17398423.81 | 4077176.19 | 17398423.81 | 10737.06 |  |  | NA | NA | [5 empty] | NA
9 | JIM | S5 System Sdn Bhd: Projek Integrasi Biometrik (PIB) | 2175000 | 2012-06-12 | 2013-07-31 | 1. Application Development 2. Installation, Testing & Commisioning 3. Training 4. Onsite Support | Wan Suhaimi Wan Abd Hamid | NA | A.Puzi, Sanuza | Closed | 1. Audit non-compliance issues: a) Tailoring checklist is not produced b) Project documentation is not present c) Contracts not available d) Risk list not updated Project team to close issue and responded to auditor by end of August 2017. (In Progress) | 2175000 | 0 | 2175000 | 6815685.4647
10 | JIM | (PERLUASAN) Migrasi Data PATI Depoh For MKN | 668890 | 2012-10-29 | 2013-07-31 | 1. Project Management, Consultancy & PMO 2. Redo, Testing, Recustomise PPKP AFIS DB Data Extraction 3. NIST Development 4. Data Migration Services 5. myIMMs System Integration | Wan Suhaimi Wan Abd Hamid | NA | A.Puzi, Sanuza | Closed | NA | 668890 | 0 | 668890 | 14227282.6
11 | JIM | S5 System Sdn Bhd: eGate Integration (JIM) | 119987 | 2013-05-16 | 2013-08-06 | 1. System Requirement Study (SRS) 2. Develop Egate Registration Integration Service 3. Develop Egate Registration Integration Services (entry and exit) 4. Installation, testing and setup integration solution | Wan Suhaimi Wan Abd Hamid | Azlan Abd Hamid | A.Puzi, Sanuza | Closed | 1. S5 insist HTP to resolve the integration issue before project closure can be done. Closure notification has been sent to S5. (Closed) 2. Audit non-compliance issues: a) Tailoring checklist is not produced b) Project documentation is not present c) Contracts not available d) Risk list not updated Project team to close issue by mid October 2017. (In Progress) | 119987 | 0 | 119987 | 811218.48
12 | JIM | Education Malaysia Global Services (EMGS) Integration Service between STAR-EMGS and myIMMs System | 560000 | 2013-08-19 | 2017-06-10 | 1. Design, Develop, Test, Commission the Integration gateway between EMGS system with myIMMs system 2. Maintenance Year 1 3. Maintenance Year 2 4. Maintenance Year 3 | Wan Suhaimi Wan Abd Hamid | Azlan Abd Hamid | A.Puzi, Sanuza | Closed | Difficulties in getting JIAS support as it is previously supported by HeB. Immediate support will take some time as client required immediate resolution. (Closed. SDC take over) | 560000 | 0 | 560000 | 0
13 | JIM | MyIMMs Integration with Facial LIVE Capture | 498417 | 2013-11-20 | 2014-04-22 | 1. Requirement & Design Management (SRS, SDD) 2. Application Developmet 3. Testing 4. Pilot at 2 branches | Wan Suhaimi Wan Abd Hamid | NA | A.Puzi, Sanuza | Closed | NA | 498417 | 0 | 498417 | 422884.12
14 | BESTINET | BESTINET: Integration Service Between Foreign Worker Centralized Mgmt System (FWCMS) and myIMMs System | 3600000 | 2013-11-01 | 2018-10-31 | 1. Furnish Data from myIMMs to FWCMS 2. One Time and Incremental Data Update 3. Batch Jobs | Wan Suhaimi Wan Abd Hamid | Md Zaidan Md Zain/Azlan Abd Hamid | Ahmad Puzi, Azmin | Closed | 1. (PSC 1/2019) - Pending payment for GST for May 2015 & June 2015. Bestinet claimed payment has been paid. To get proof of payment. (In progress) To transfer issue to new contract | 3957454.26 | -357454.26 | 3676800 | NA | 1. Application support on going 2. Received payment for Sept and Oct 2018. 3. Pending payment for GST for May 2015 & June 2015. Project Team to follow-up. 4.Contract documentation preparation is still in progress. Bestinet has provide feedback, Project Team to respond. Target to complete by 15/2/2019. | 1. Application support on going 2. Contract is in stamping process by Bestinet | 1. Application support on going. 2. As at 8/4/2019, contract has been signed and stamped by Bestinet. New contract End Date shall be 31/10/2021. AM need to issue SEO to obtain new WBS for billing process. | 1. Status will be reported under new contract. | [5 empty] | 100%
15 | JIM | NZ Gemilang Sdn Bhd: Integration Service Between PDRM's Central Intelligence Unit (CIU) - PDRM and myIMMs System | 124087 | 2013-11-15 | 2014-02-15 | 1. Penghantaran, Pemasangan dan Pentauliahan Perisian dan Perkakasan 2. Melaksanakan integrasi 18 sistem Dalaman Jabatan-Jabatan PDRM & 6 sistem Luaran Jabatan di bawah KDN | Ahmad Suryadi bin Abd Aziz | NA | A.Puzi, Sanuza | Closed | NA | 124087 | 0 | 124087 | 1159.28
16 | JIM | ESD Talent Corp Malaysia: Integration Services Between Talent Corp's ESD Portal and myIMMs System | 150000 | 2013-01-27 | 2014-06-02 | 1. Provide Development Services 2. Perform System Requirements Specification 3. Provide Integration Design 4. Testing, Installation & Commisioning 5. Support and Maintenance Services | Wan Suhaimi Wan Abd Hamid | NA | A.Puzi, Sanuza | Closed | 1. Pending development for integration enhancement due to JIM approval. Team has communicated & email to TC regarding conditional closure and suggest enhancement during maintenance. (Closed) 2. Audit non-compliance issues: a) Tailoring checklist is not produced b) Project documentation is not present c) Contracts not available d) Risk list not updated Project team to close issue by mid October 2017. (Closed - Project Team has provided the audit response to the issues raised) | 151800 | 0 | 151800 | 49415.2563
17 | JIM | Innovezion Tech Sdn Bhd: Development services for Regula Integration and deployment services for selected sites | 203384.32 | 2015-10-01 | 2015-12-31 | 1. Project Management 2. Development Services 3. Requirement 4. Coding 5. Configuration 6. Testing 7. Deployment | Ahmad Suryadi bin Abd Aziz | NA | A.Puzi, Sanuza | Closed | NA | 203384.32 | 0 | 203384.32 | 2406529.56
18 | myEG | my EG Sevices Bhd: Working Permit Renewal of Foreign Workers | 2400000 | 2013-01-01 | 2015-01-01 | 1. Application Dev 2. Testing 3. Deployment 4. Support | Wan Suhaimi Wan Abd Hamid | Md Zaidan Md Zain/Azlan Abd Hamid | Ahmad Puzi, Azmin | Maintenance | 1. Subcontract for renewal is still pending review by myEG. Account Manager to follow-up. (In progress) | 2711883.08 | 0 | 2606857.22 | 1539950.356 | 1. Services on going. Concession basis (50 cent per transaction) 2. Invoice submitted until November 2018; pending payment October and November 2018 3. Account Manager is still in discussion with myEG on new contract. | 1. Services on going. Concession basis (50 cent per transaction) 2. Account Manager in progress to initiate subcontract preparation with Legal | 1. Services on going. Concession basis (50 cent per transaction) 2. Account Manager in progress working on subcontract preparation with Legal. | 1. Services on going. Concession basis (50 cent per transaction) 2. Subcontract has been passed to myEG for review. | 1. Services on going. Concession basis (50 cent per transaction) 2. Contract has been passed to myEG for reviewing. | 1. Services on going. Concession basis (50 cent per transaction) 2. Scope of work has been finalised and reviewed by Legal. PM to get MyEG to review and respond by 10/10/2019. | 1. Services on going. Concession basis (50 cent per transaction) | 1. Services on going. Concession basis (50 cent per transaction) | 1. Services on going. Concession basis (50 cent per transaction) | NA
19 | JIM | Vista Kencana: MBIKE Enhancement | 40280 | 2015-11-25 | 2016-01-12 | Integration service between Vista Kencana and myIMMs System for: Phase 1: 1.Inquiry SL & Passport during registration 2.Insert MBIKE record into myIMMs Phase 2: 1.Sheduler for MBIKE SL Data Extraction 2.Sheduler for MBIKE_PMA_HIST Data Extraction 3.Inquiry MBIKE_SL status unread 4.Inquiry MBIKE_SL status read 5.Inquiry SL & Passport Status 6.Create movement record in myIMMs | Wan Suhaimi Wan Abd Hamid | Azlan Abd Hamid | A.Puzi, Sanuza | Closed | 1. Audit non-compliance issues: a) Tailoring checklist is not produced b) Project documentation is not present c) Contracts not available d) Risk list not updated Project team to close issue by mid October 2017. (Closed - Project Team has provided the audit response to the issues raised) | 40280 | 0 | 40280 | 6628179.35
20 | JIM | MARDI | 50880 | 2016-03-24 | 2016-04-28 | Integration with myIMMs & AGF (Agro Intelligance System) | Wan Suhaimi Wan Abd Hamid | Azlan Abd Hamid | A.Puzi, Sanuza | Closed | Potential loss of RM50K due to MARDI unreadiness to complete the project. Account Manager will provide official letter to MARDI on the matter. Potential to terminate project as customer unwilling to proceed with payment. (Closed) | 0 | 50880 | 0 | 4850500.2415
21 | JPN | JPN Maintenance | 120628000 | 2015-07-01 | 2017-06-30 | JPN ICT Maintenance for Core Business | Selamat Ahmad | Ibrahim Yusoff | Hamid | Closed | 1. Pending payment to vendors and partners. Affected vendors refused to do Preventive Maintenance work because of payment issue.(Closed) 2. Insufficient resources. KIV until contract renewed. (Closed) 3. Collectors terminal (7 units) for e-debit and MEPS, still awaiting new vendor to perform preventive maintenance(Closed) 4. Unstable eJPN. JPN feel annoyed with our solution. Been piloted since 12 August 2015. eJPN team request SDC to help in providing solution and troubleshoot current problem/slow response issue. (Closed) 5. Network Upgrade Contract & Green Data Center awarded to other companies. Need to support these vendors or JPN will ask for credit note on cost savings. HMS is working on SOW to support this activity (Closed) 6. TDA demands for either Bank Guarantee or Coporate Guarantee. Customer concern on the delivery end date.Team to issue letter of appeal to TDA for exception. (Closed) 7. Archive Database: Number of records not tally between PDB and ADB potentially due to storage or problem on synchronization. Team will further discuss and investigate .(Closed) 8. Increase in GSCB Storage: Proposal submitted to BTM for the extra 4TB permanent storage for 5 year plan of growing databases. BTM agreed on 2TB for short term planning and suggest to take off ADB or SDB and use ODM at DRC as a backup storage. Team need further discussion. Additional 2 TB storage required licence for migrate to DRC (Closed) 9. Problem Photo in DB2: 2 Suggestion: 1)Check compress process in MyKad 2)Change photo column size in DB2 – HeiTech need to submit requirement study to BTM. On photo and thumbprint not found in DB2 issue, team need to verify with MyKad transaction. Photo size for branches decrease from 300x400 to 150x200. ESDC to amend the program for 3175 resolution compression. (Closed) 10. Data Centre Expansion under TDA. Issue on financial as vendor required payment before delivery. Delay in payment may affect factory test activities. Issue has been resolved by HMS. (Closed) 11. CR budget of RM3.5mil is still untouch and will affect overall project revenue. Team to relook on other possibility to utilize this budget. (Closed) 12. Technical/field support competency issue. IA need to undergo training to enhance skill and knowledge. PM will provide training requirement and tentative date to Mokhtar for further action. (Closed) 13. Insufficient advance for IA. Management approved lesser than the amount applied. IA unable to provide corrective support services when required due to insufficient fund. (Closed) 14. PO issuance to Optima still pending for approval. Optima has completed CR work and payment need to be made to the vendor. Team to obtain approval of PO from EVP immediately.(Closed) 15. Project non-compliance issue. Team to close all gaps by mid October 2017.(Closed) 16. JPN claimed source code handed over by HTP upon contract end is not latest version. PM to do the handover again with proper documentation. (Closed - second has been done ) | 119395613.72 | 1232386.28 | 112789733.02 | NA
22 | JPN | PERKHIDMATAN PENYELENGGARAAN SISTEM BOOMGATE MYKAD & BOOMGATE RFID JPN | 162687.5 | 2014-02-15 | 2016-02-14 | Boomgate MyKad & RFID maintenance | Jahir Hussin bin Othman | Ibrahim Yusoff | Hamid | Closed | NA | 162687.5 | 0 | 162687.5 | 532.8
23 | MOH | SPP V2.6 MAINTENANCE (Hospital Tuanku Ja'afar Seremban (HTJ) & Hospital Port Dickson) | 1050403 | 2014-04-01 | 2016-03-31 | SPPV2.6 SPD (Seremban-Port Dickson) Maintenance Project | Suradi Abd Rahman | Mokhtar Atan | Noor Aini | Closed | NA | 1050403 | 0 | 982324.75
24 | MOH | SPP V2.6 MAINTENANCE-eKL (Hospital Kuala Lumpur (HKL), Hospital Kajang (HKJG), Hospital Tengku Ampuan Rahimah (HTAR)) | 1245514 | 2014-01-29 | 2016-01-28 | Application SPP V2.6 and maintenance for infrastructure related | Suradi Abd Rahman | Mokhtar Atan | Noor Aini | Closed | NA | 1245514 | 0 | 1244625
25 | MOH | SPP V3 Rollout Project - Hospital Bentong Pahang | 13750000 | 2014-02-04 | 2015-10-31 | 1. Implementation of SPPV3.1 2. Integration 3. Operational & Support Services | Rosenizam Shah Jamaluddin | Mokhtar Atan | Noor Aini | Closed | NA | 13750000 | 0 | 13750000
26 | MOH | SPP V3 Rollout Project - Hospital Tuanku Jaafar Seremban |  | 2014-02-04 | 2015-12-09 | 1. Implementation of SPPV3.1 2. Integration 3. Operational & Support Services | Norashikin Baharuddin | Mokhtar Atan | Noor Aini | Closed | NA
27 | MOH | SPP V3 Rollout Project - Hospital Raja Perempuan Zainab II, Kota Bharu |  | 2014-02-04 | 2015-10-03 | 1. Implementation of SPPV3.1 2. Integration 3. Operational & Support Services | Redzuan Amiruddin | Mokhtar Atan | Noor Aini | Closed | NA
28 | MOH | SPP V3.1 Rollout Project - Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu (Extension of Time (EOT)) | 184229.97 | 2016-01-05 | 2016-06-30 | Warranty support for SPP V3.1 | Redzuan Amiruddin | Mokhtar Atan | Noor Aini | Closed | 1. “Power trip” at New Building ( ACC Building ). TNB has conducted assessment activities on 8 Apr 2016 due to unstable incoming power to Hospital Power source. On monitoring period until 31st May 2016 - closed 2. System Performance issue, conduct onsite monitoring by technical team from 13th March 2016 to 16th March 2016 with fine tuning on SQL Query, Bugs fixing, Domain synchronization and Pillot JVM domain setting. Create new domain D29 for O&G clinic on 13052016. On monitoring period until 26th May 2016-Closed | 184229.97 | 0 | 184229.97
29 | MOH | SPP V3 CR Med. Record - HRPZ | 48900 | 2015-11-04 | 2015-12-15 | Development of CR Medical record for SPP V3 | Redzuan Amiruddin B Abd Rahim | Mokhtar Atan | Noor Aini | Closed | NA | 48900 | 0 | 48900
30 | MOH | SPP PERLUASAN HARDWARE DELIVERY FOR HBEN, HRPZ AND HTJS | 5796069 | 2014-02-04 | 2015-10-03 | Membekal, Menghantar, Memasang, Menguji, Mengkonfigurasi dan Mentauliah Guna Peralatan ICT | HBEN - Rosenizam Shah Jamaluddin HRPZ II - Redzuan Amiruddin HTJS - Norashikin Baharuddin | Mokhtar Atan | Noor Aini | Closed | NA | 5796069 | 0 | 5796069
31 | MOH | SPP V2.6 Implementation Project - Hospital Taiping Perak (HTPG) | 449611.9 | 2015-09-14 | 2018-09-13 | Membekal, Menghantar, Memasang, Menguji, Mengkonfigurasi, Mentauliah Guna dan Sewaan Peralatan ICT untk Pelaksanaan Aplikasi Sistem Pengurusan Pesakit (SPP) Versi 2.6 | Redzuan Amiruddin | Ahmad Zamin Mahadzir/ Mokhtar Atan | Halimah/Sanuza | Closed | No open or new issues | 491098 | -41486.1 | 449611.91 | 393643.73 |  |  | NA | NA | [5 empty] | NA
32 | MOH | Data Center (DC) Queen Elizabeth Hospital Kota Kinabalu (HQE) | 859582 | 2015-07-10 | 2016-11-09 | Membekal, menghantar, menguji, mengkonfigurasi dan mentauliah guna komponen-komponen bilik server di Hospital Queen Elizabeth, Kota Kinabalu, Sabah | Redzuan Amiruddin B Abd Rahim | Mokhtar Atan | Noor Aini | Closed | NA | 859582 | 0 | 859582
33 | MOH | DC Hospital Sultanah Nora Ismail (HSNI), Batu Pahat | 934409 | 2015-09-13 | 2017-09-16 | Membekal, Menghantar, Memasang, Menguji, Mengkonfigurasi, dan Mentauliah Guna Komponen-komponen Bilik Server di HSNI | Norashikin Bt Baharudin | Mokhtar Atan | Noor Aini | Closed | KCSB temporary suspended works related to the system supports. (Closed) | 934409 | 0 | 934409
34 | MOH | DC Hospital Tengku Ampuan Rahimah Klang (HTAR) | 943381 | 2015-09-28 | 2016-09-03 | Membekal, Menghantar, Memasang, Menguji, Mengkonfigurasi dan Mentauliah Guna Komponen-komponen Bilik Server di Hospital Tengku Ampuan Rahimah Klang | Rosenizam Shah B Jamaludin | Mokhtar Atan | Noor Aini | Closed | Delayed in first partial payment amounted RM745,270.99. As at 10/05/2016, HTP has submitted a letter to HTAR with a copy to JKNS as reminder letter for full payment. Due to this issue/matter, project team are having hard time to ensure scheduled Preventive Maintenance activities by the vendors for the Precision Air Conditioning System and for the Uninterruptible Power Supply System. (Closed) 20/06/2016 – Unit Pembangunan JKNS (Pn Siti Hajar) has been informed by KKM, they still have not yet get any further solid information regarding the payment. JKNS will send another reminder letter KKM regarding this issue. (Closed) | 943381 | 0 | 943381
35 | MOH | SPP-PHIS Integration Project | 107073 | 2015-06-03 | 2015-08-03 | SPP-PHIS Integration Project (Hospital Raja Permaisuri Bainun Ipoh) | Norli Bt Mohd Masri | Mokhtar Atan | Noor Aini | Closed | NA | 107073 | 0 | 107073
36 | MOH | SPP Maintenance - Hospital Bentong | 952654.86 | 2016-03-01 | 2019-02-28 | Penyelenggaraan dan Sokongan Operasi Bagi Perkakasan, Perisian dan Rangkaian Untuk Sistem Pengurusan Pesakit (SPP) Hospital Bentong | Redzuan Amiruddin | Ahmad Zamin Mahadzir/ Mokhtar Atan | Halimah | Project Closure | No open or new issues | 895550.58 | 57104.28 | 895550.58 | 664564.36 | 1. Overall completion, Plan = 97%; Actual = 97% 2. Corrective Maintenance in progress. 3. CM Report for Dec 2018 - Feb 2019 target to complete by 28/2/2019 4. A total 10 problems related to Application (1) and Hardware Failure (9) were reported and closed. 5. Awaiting for tender for maintenance renewal. | 1. Overall completion, Plan = 97%; Actual = 97% 2. Corrective Maintenance in progress. 3. CM Report for Dec 2018 - Feb 2019 target to complete by 28/2/2019 4. Total problems = 10 and closed; Application = 1; Hardware Failure = 9 5. Awaiting for tender for maintenance renewal. | 1. Overall completion, Plan = 100%; Actual = 100% 2. Corrective Maintenance: Done 3. CM Report for Dec 2018 - Feb 2019 completed 4. Total problems = 9 and closed; Application = 4; Hardware Failure = 5 5. Project Closure with HBNTG done on 25/2/2019. 6. Letter of Claim submitted to HBEN on 6/3/19. Pending payment due to change password activity for SPP Svr & mysql schedule to 1st April 2019. 7. PM to do internal project closure upon completion of Item 6 target by 30/4/2019. | 1. Overall completion, Plan = 100%; Actual = 100% 2. Project Closure in progress. 3. Pending Letter of Claim from customer. User is in the process of examining the submitted documents as specified in the contract. 4. PM to do internal project closure upon completion of Item 3 target by 30/4/2019. | [5 empty] | NA
37 | MOH | Project Upgrade Server for HRPB | 443976.85 | 2015-05-29 | 2016-05-28 | Penggantian Server untuk Kegunaan Sistem Pengurusan Pesakit (SPP) Versi 3.1, Hospital Raja Permaisuri Bainun Ipoh, Perak | Jifpri Ahmad | Mokhtar Atan | Noor Aini | Closed | NA | 443976.85 | 0 | 443976.85
38 | DEFENSE | Enhanced Training Aid System (ETAS) | 31000000 | 2012-10-10 | 2016-10-09 | Application development and warranty services for ETAS | Kamaruddin Abd Hamid | NA | N/A | Closed | NA | 31000000 | 0 | 31000000
39 | DEFENSE | IGLA Weapon System | 2925240 | 2014-01-28 | 2017-01-27 | Membekal dan menghantar alat ganti IGLA Weapon System untuk Tentera Darat | Sapfie Sarju | NA | Halimah Din | Closed | 1. SST was rejected due to Forex – Team to advise Mindef to establish direct negotiation pricing base on current Forex. (Closed) | 2925240 | 0 | 2925240 | 2373438.98 |  |  | NA | NA | [5 empty] | NA
40 | DEFENSE | Arthur Radar Weapon Locating System (WLS) | 6890000 | 2015-06-05 | 2018-06-04 | Perolehan Perkhidmatan Senggaraan dan Alat ganti Radar Arthur WLS untuk Tentera Darat | Sapfie Sarju | Siti Shahwana Abdul Hamid | Halimah Din | Under PMC monitoring | No open/new issue | 5015484.55 | 1874515.45 | 3976324.55 | 3654460.77 |  |  | NA | NA | [5 empty] | NA
41 | DEFENSE | Action Speed Tactical Trainer (ASTT) | 4500000 | 2015-08-20 | 2018-08-19 | Perolehan Pembekalan Alat Ganti dan Perkhidmatan Selenggaraan bagi Action Speed Tactical Trainer (ASTT) Systems untuk Tentera Laut Diraja Malaysia | Sulaiman Husain | Siti Shahwana Abdul Hamid | Halimah Din | Under PMC monitoring | No open/new issue | 140093.84 | 4359906.16 | 129532 | 54694.31 |  |  | NA | NA | [5 empty] | NA
42 | DEFENSE | JHEV-Projek Penyelenggaraan Aplikasi (Sistem Pengurusan Pencen), Perisian & Perkakasan. | 196091 | 2016-03-15 | 2017-03-14 | Penyelenggaraan Aplikasi (Sistem Pengurusan Pencen), Perisian & Perkakasan. | Kamaruddin Abd Hamid | NA | Azrul Saad | Closed | 1. VIBES system developers have resigned. Junior developer does not have system knowledge to support JHEV. PM requested Norainon to be onsite for 2 days supporting account closing activity (VO basis).(Closed) 2. Support staff need to have knowledge in .C#.Net programming , DBA and network in order to support VIBES system. (Closed) 3.Issue on access level via remote access. Require assistance from Hamadi to resolve it. (Closed). | 196091 | 0 | 155239
43 | MOH | SPP V2.6 MAINTENANCE-eKL (Hospital Kuala Lumpur (HKL), Hospital Kajang (HKJG), Hospital Tengku Ampuan Rahimah (HTAR)) | 2332000 | 2016-03-15 | 2019-03-14 | Application SPP V2.6 and maintenance for infrastructure related | Mohd Yushan Abdul Wahab | Ahmad Zamin Mahadzir/ Mokhtar Atan | Halimah | Project Closure | No open or new issues | 2307221.18 | 24778.82 | 2307221.18 | 1316650.26 | 1. Overall completion Plan = 98%; Actual = 98%. 2. Corrective maintenance in progress. 3. Preventive maintenance #6 is in progress and target to complete by 1/2/2019. PM Report target to complete by 11/2/2019 4. Problems reported: i) HKL 23 reported problems were closed; Application (12) Hardware (11) ii) HTAR 11 reported problems were closed; Hardware (11) iii) HKajang 5 reported problems were closed; Application (1) Hardware (4) | 1. Overall completion Plan = 99%; Actual = 99%. 2. Corrective maintenance in progress. 3. Preventive maintenance #6 completed by 19/2/2019. 4. Problems reported: i) HKL Total reported problems = 18 and closed; Application = 9; Hardware = 9 ii) HTAR Total reported problems = 9 and closed; Hardware = 8; User Request = 1 iii) HKajang Total reported problems = 6 and closed; Application = 1; Hardware = 5 | 1. Overall completion Plan = 100%; Actual = 100%. 2. Corrective maintenance completed. 3. Preventive maintenance completed . 4. Problems reported: i) HKL Total reported problems = 10 and closed; Application = 5; Hardware = 5 ii) HTAR Total reported problems = 7 and closed; Hardware = 7; User Request = 0 iii) HKajang Total reported problems = 7 and closed; Application = 1; Hardware = 6 5. Project Closure in progress. Final Signoff is targeted on 30/4/2019. | 1. Project Closure in progress. Pending Final Signoff from customer. Reschedule targeted on 31/5/2019. | [5 empty] | 100%
44 | MOH | Clinical Documentation | 30101218.92 | 2016-03-21 | 2020-03-20 | 1. 2 years Development of CD module with 11 Disciplines 2. Enrichment of SPP via identified CR 3. Develop Application Programming Interface 4. Develop Mobile Version of SPP & CD 5. Verification & Validation services by 3rd party entity 6. Data Migration of Existing SPP at HRPB 7. Integration to 9 identified systems 8. Integration to 16 types of medical equipment at 24 identified location with a total of 50 units 9. Delivery & Installation of Hardware & Software 10. 1 year Pilot implementation at HRPB 11. Benefit Realization 12. Change Management 13. Training & ToT 14. Helpdesk, Operation & Technical Support | Norli Masri | Ahmad Zamin Mahadzir/TBA | Noor Aini, Nur Syuhadah, Rozaimi | Development | 1. (PSC 2/2019) Project Team requires second revised timeline since UAT 2 could not start as planned. Issue has been discussed with Pasukan Kerja KKM and agreed to revise with staggard implementation according to discipline. With revised timeline, FAT will be on 25/10/2019 and warranty support duration will be lesser i.e. 218 days. Project Team to ensure chronology and justification on the cause of delay are properly documented. if project timeline remain until 25/10/2020 does not change i.e. 218 days. (Slide update on 31/5/2019) Go-Live date is rescheduled to be on 16/6/2019 and 17/6/2019 for Lite version. (Slide update on 11/6/2019) Go-Live for Lite version was done as scheduled, however has been reverted to SPP due to system problem. New date to Go-Live is not determined yet by KKM. Project Team in process of rectifying issues. (PSC 5/2019) Go-Live for EMR Basic is rescheduled to be on 24/8/2019 and 12/10/2019, 23/11/2019,07/12/2019 and 26/12/2019 for EMR Plus. (PSC 7/2019) PAT Go-Live at HRPB was rescheduled to 05/10/2019. Entry criteria for PAT Go-Live set on 21/9/2019 was not fulfilled during Mesyuarat Penentuan PAT CD on 20/9/2019. PAT Go-Live HIS@KKM EMR Basic done on 23/11/2019. HIS@KKM EMR Plus will be implemented in stages from 1/2/2020 until 29/3/2020. (Closed) 3. Due to the delay of HIS@KKM EMR Basic, and not meeting the 25/10/2019 date, LAD is already imposed at RM3000+ per day. (PSC 9/2019) Project Team to submit letter for EOT to KKM in January 2020 with justification. (In progress) | 26191691.74 | 3909527.18 | 26191691.74 | 25176287.904 | 1. Overall completion: Plan = 88%; Actual = 81% Gaps due to infrastructure, coding and testing slight delay. 2. Application Development progress: Plan = 96% ; Actual = 93% i) Status: • Coding – 95% (+1%) • Unit Testing – 90% (+5%) • Internal QA – 93% (+7%) • IV&V – 87% (+7%) • Hardware/Software/Infra – 77% (+0%) • UAT – 33 (+16%) ii) UAT Phase 1 Cycle 2 completed on 7/1/2019 – 18/1/2019 iii) UAT Phase 1 Cycle 3 not required; all testing done during Cycle 2 iv) UAT Phase 2 target to start from 2/2/2019 – 15/5/2019 3. Infra/hardware/software status: i) Specification on material and schematic diagram for DB installation has been obtained from HRPB Engineer on 17/1/2019 ii) Testing on DICOM target to be done from 28 – 30/1/2019 at HRPB 3. PILOT Implementation preparation: Actual = 59%, Plan = 75% i) Training & TOT completed 62% from 71% planned; End-user training target on 25/3/2019 ii) Change Management completed 58% from 87% planned; iii) Infra/hardware/software completed 77% from 81% planned; iv) Data Migration completed 38% from 39% planned; v) Go Live and PAT target 18/5/2019 4. Benefits Realisation completed 43% from 43% planned | 1. Overall completion: Plan = 88%; Actual = 84% Gaps 4% due to infrastructure (6%), coding (Δ 2%) Unit Testing (Δ 5%), IQA (Δ 6%) and IV&V (Δ 5%). 2. Application Development progress: Plan = 100% ; Actual = 98% • Coding – 98% (+3%) • Unit Testing – 95% (+5%) • Internal QA – 94% (+1%) • IV&V – 87% (+0%) • Hardware/Software/Infra – 82% (+5%) 3. UAT – 33 (+0%) i) UAT Phase 2 is proposed as follows: • Lite Version (L/V) & Full Version (F/V) will be align with Pelan Perluasan HIS@KKM • L/V cover SPP Conversion, SPP Enrichment & CD General • F/V covers 11 other disciplines, medical equipment integration, API, mobile apps & BI Ii) UAT L/V proposed date: 18/3/19 – 26/4/19 iii) UAT F/V proposed date: • Batch 1 : 06/5/19 – 17/5/19 • Batch 2 : 24/6/19 – 05/7/19 • Batch 3 : 15/7/19 – 26/7/19 • Batch 4 : 26/8/19 – 06/9/19 • Batch 5 : 16/9/19 – 27/9/19 • Proposed system go-live to be in stages: • L/V: 27/4/19 • F/V: Batch 1 – 25/5/19, • Batch 2 – 13/7/19, • Batch 3 – 03/8/19, • Batch 4 – 14/9/19 & • Batch 5 – 05/10/19 (Note: updated as at 26/2/2019 4. Infra/hardware/software status: i) Testing on DICOM done from 28 – 30/1/2019 at HRPB 5. PILOT Implementation preparation: Actual = 59%, Plan = 75% i) Training & TOT completed 66% from 72% planned; End-user training target on 25/3/2019 ii) Change Management completed 70%; - Awareness Session and Mockup HIS@KKM target to be done on 12/3/2019 di HRPB to Champion & Users iii) Infra/hardware/software completed 82% from 88% planned; iv) Data Migration completed 49% from 51% planned; 6. Benefits Realisation completed 43% from 43% planned | 1. Overall completion: Plan = 89%; Actual = 85% (Revised timeline) Gaps 3% due to infrastructure (8%), coding (Δ 2%) Unit Testing (Δ 5%), IQA (Δ 6%) and IV&V (Δ 5%). 2. Application Development progress: Plan = 95% ; Actual = 92% (Revise percentage due to revise timeline) • Coding – 98% (+3%) • Unit Testing – 95% (+5%) • Internal QA – 94% (+1%) • IV&V – 87% (+0%) • Hardware/Software/Infra – 85% (+3%) 3. UAT – 44 (+0%) i) UAT Phase 2 is proposed as follows: • Lite Version (L/V) & Full Version (F/V) will be aligned with Pelan Perluasan HIS@KKM • L/V cover SPP Conversion, SPP Enrichment & CD General • F/V covers 11 other disciplines, medical equipment integration, API, mobile apps & BI Ii) UAT L/V proposed date: 18/3/19 – 25/4/19 iii) UAT F/V proposed date: • Batch 1 : 20/5/2019 – 31/5/2019 • Batch 2 : 17/6/2019 – 28/6/2019 • Batch 3 : 15/7/2019 – 26/7/2019 • Batch 4 : 26/8/2019 – 06/9/2019 • Batch 5 : 16/9/2019 – 27/9/2019 • Proposed system go-live to be in stages: • L/V: 27/4/19 • F/V: Release 1 – 15/6/2019 • Release 2: 6/7/2019 • Release 3: 3/8/2019 • Release 4 – 14/9/2019 • Release 5 – 05/10/2019 (Note: updated as at 24/3/2019) 4. System/Device Integration status: i) Plan SIT for system/device integration on 18-19/4/2019 and UAT planned on 22/4/2019 – 26/4/2019 5. PILOT Implementation preparation: Actual = 73%, Plan = 79% i) Training & TOT completed 68% from 75% planned; End-user training target date rescheduled to start on 8/4/2019 at HRPB ii) Change Management completed 89%; - Awareness Session and Mockup HIS@KKM was done on 15/3/2019 di HRPB to Champion & Users iii) Infra/hardware/software completed 85% from 93% planned; iv) Data Migration completed 65% from 65% planned; 6. Benefits Realisation completed 43% from 43% planned | 1. Overall completion: Plan = 88%; Actual = 85% (Revised timeline) Gaps 3% due to infrastructure (1%), coding (Δ 2%) Unit Testing (Δ 5%), IQA (Δ 6%) and IV&V (Δ 5%). 2. Application Development progress: Plan = 95%; Actual = 92% • Coding – 98% (+0%) • Unit Testing – 95% (+0%) • Internal QA – 94% (+0%) • IV&V – 87% (+0%) • Hardware/Software/Infra – 99% (+1%) 3. UAT & GO-LIVE HIS@KKM LITE VERSION • Bug Fixing & Fine Tuning 29/4 – 20/5/2019 • System & Regression Testing 13/5 – 01/6/2019 • User Acceptance Test Cycle 3 27/5 – 31/5/2019 • Data Preparation & System Readiness 09/6 – 14/6/2019 • System Go-Live Batch 1 (47 sites) System Go-Live Batch 1 (47 sites) 15/6/2019 @ 8am • System Go-Live Batch 2 (34 sites) 17/6/2019 @ 7am • System Monitoring & Onsite Standby 15/6 – 30/6/2019 4. Change Management completed 94% from 99%; 5. Infra/hardware/software completed 99% from 100% planned; 6. Data Migration completed 78% from 81% planned; | Note: No PSC slide for August 2019 Status as at July 2019: 1. Overall completion: Plan = 90%; Actual = 87% (Revised timeline) 2. Application Development progress: - System Requirement & Design – 100% - Programming – 98% - Quality Assurance & Independent Verification Validation Testing – 93% & 86% - UAT – 67% 3. Pilot Implementation: - Hardware/Software/Infra Setup – 100% - Training – 89% - Data Migration – 96% - Change Management & Benefit Realisation – 100% & 43% 4.Components & Disciplines - EMR Basic – PAT:24/8/2019 – 26/08/2019 - EMR Plus 1 – UAT: 03/09/2019 – 30/09/2019, PAT:12/10/2019 - EMR Plus 2 – UAT:01/10/2019-12/11/2019, PAT 23/11/2019 - EMR Plus 3 – UAT:04/11/2019-29/11/2019, PAT 07/12/2019 - EMR Plus 4 – UAT:25/11/2019-24/12/2019, PAT 26/12/2019 5. EMR basic timeline activities - Server - Review & fine tune on infrastructure setup, in progress-24/6/2019 - System Environment done on 26/6/2019 - Application rectification & fine tuning, in progress – 27/6/2019 - Function Test, in progress – 27/6/2019 - Dry Run/ Simulation (End to End), in progress – 30/7/2019 - Non Functional (Stress Test), in progress – 24/6/2019 - Application Fine Tuning (Application, Server & Database) based on stress test, in progress – 24/6/2019 - Data Migration Verification, in progress – 25/6/2019 | 1. Overall completion: Plan = 90%; Actual = 87% (Status is based on Anjakan Kedua) Difference is due to delay in PAT and FAT. 2. Application Development progress: - System Requirement & Design – 100% - Programming – 98% - Quality Assurance & Independent Verification Validation Testing – 93% & 87% - UAT – 90% 3. Pilot Implementation: - Hardware/Software/Infra Setup – 100% - Training – 90% - Data Migration – 96% - Change Management & Benefit Realisation – 100% & 43% 4. UAT for HIS@KKM EMR Plus 1 Cycle 1 has started on 18/09/2019. PAT Go-Live di HRPB need to be rescheduled to 05/10/2019. Entry Citeria for PAT Go-Live set on 21/09/2019 was not fulfilled during Mesyuarat Penentuan PAT CD on 20/09/2019. 5. Proposed new date: - EMR Basic – PAT: 5/10/2019 - EMR Plus 1 –UAT: 18/9/2019 – 31/20/2019; PAT: 6/11/2019 - EMR Plus 2 – UAT: 11/11/2019 – 13/12/2019; PAT = 20/12/2019 FAT: 27/12/2019 – 26/1/2020; Warranty Support: 27/1/2020 – 26/1/2021 | 1. Overall completion: Plan = 95%; Actual = 87% (Revised timeline # 2) Difference is due to delay in PAT and FAT. PAT could not proceed since entry criteria for PAT could not be met yet. 2. Application Development progress: - System Requirement & Design – 100% - Programming (coding) – 98% - Quality Assurance – 93%; Independent Verification Validation Testing – 88% - UAT – 72% 3. Pilot Implementation: - Hardware/Software/Infra Setup – 100% - Training – 75% - Data Migration – 96% - Change Management – 100%; Benefit Realisation – 50% 4.Proposal news date Implementation - User Acceptance Test: 18/9/2019-13/12/2019 - User Manual: 2/10/2019-20/12/2019 - System Go Live/PAT: i) EMR Basic: 23/11/2019 – 26/1/2020 ii) EMR Plus: 14/12/2019 – 26/12/2019 - FAT: 27/12/2019 – 26/22/2020 - Warranty Period: 26/2/2020 – 27/2/2021 | No report submission for month of November 2019 | No report submission for month of December 2019 | 93% (October = 93%) (September 2019 = 85%) (August 2019 = 92%)
45 | DEFENSE | Asean Customs Transit System (ACTS) | 1425000 | 2016-01-01 | 2019-12-31 | 1. Support for deployment, training and testing of ACTS at pilot sites: Malaysia, Singapore and Thailand. 2. Helpdesk 1st and 2nd levels for 6 months of pilot execution and subsequently for 12 months of warranty period and 24 months of maintenance period. 3. Central Services Hosting and Operation during the Pilot Execution of 6 months. | Sulaiman Husain | Siti Shahwana Abdul Hamid | Halimah Din | Under PMC monitoring | No open/ new issues | 914008.74 | 510991.26 | 914008.74 | 152073.39 |  |  | NA | NA | [5 empty] | NA
46 | MOH | SPP V3.1 Rollout Project - Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu | 2591208.16 | 2016-09-01 | 2019-08-31 | Preventive support for hardware, software, network and application (SPP V3.1) | Norashikin Baharudin | Ahmad Zamin Mahadzir/TBA | Halimah | Closed | 1. Server's Domain loading for Web services segment still giving intermittent/ slowness which disrupted operation at Clinical or Wards areas. (PSC 5/2019) Issue closed after technical done fine tuning at coding. One of the txn that cause slowness was Order list txn. (Closed) | 2534333.69 | 56874.47 | 2534333.69 | 1389541.5885 | 1. Overall completion, Plan = 94% Actual = 94% 2. Corrective maintenance in progress, CM Report for Dec 2018 completed on 10/1/2019. Report for Jan 2019 target to complete by 10/2/2019. 3. PM activity completed 68%; PM #5 started on 13/1/2019 and still in progress. Target to complete by 28/2/2019 and report target to complete by 14/3/2019. 4. SPA activities has completed and report has been submitted and presented to HRPZ and accepted. Project Team in process of preparing the findings and recommendation and target to present to KKM by 28/2/2019. 5. Network & CPU Utilization Report and Application/ Performance/ Database Utilization Tuning Report: Utilization Report #5 target completed on 15/2/2019. 6. Problems log: A total 103 reported and closed; Application (45), Hardware failure (58), | 1. Overall completion, Plan = 95% Actual = 95% 2. Corrective maintenance in progress, CM Report for Jan completed on 10/2/2019. Report for Feb 2019 target to complete by 10/3/2019. 3. PM activity completed 80%; PM #5 started on 13/1/2019 and still in progress. Activity target to complete by 28/2/2019 and report target to complete by 14/3/2019. 4. SPA activities has completed and report has been submitted and presented to HRPZ and accepted. Project Team has presented the report to KKM during the monthly February 2019 meeting. 5. Network & CPU Utilization Report and Application/ Performance/ Database Utilization Tuning Report: Utilization Report #5 target completed on 15/2/2019 is still in progress. New target date is by 15/3/2019. 6. Problems log: A total 66 reported and closed; Application (30), Hardware failure (33), | 1. Overall completion, Plan = 96% Actual = 96% 2. Corrective maintenance in progress, CM Report for February 2019 completed on 10/3/2019. Report for March 2019 target to complete by 10/4/2019. 3. PM activity completed 100%; PM #5 completed on 28/2/2019. 4. Network & CPU Utilization Report and Application/Performance/ Database Utilization Tuning Report: Utilization Report #5 completed on 12/3/2019. 6. Problem log: A total 93 reported and closed; Application (34), Hardware failure (57) Customer Equipment & User Request (2) | 1. Overall completion, Plan = 97% Actual = 97% 2. Corrective maintenance in progress, CM Report for April 2019 completed on 10/5/2019. Report for June 2019 target to complete by 10/6/2019. 3. Overall PM activity completed 83%; PM activities PM #6 Report completed on 31/7/2019. 4. Total problem reported for May 2019 and resolved = 97; Application = 37; Hardware Failure = 60 | 1. Overall completion, Plan = 100% Actual = 100% 2. Corrective maintenance in progress, CM Report for July 2019 completed on 6/8/2019. Report for August 2019 target to complete by 3/9/2019. 3. Overall PM activity completed 100%; PM activities PM #6 Report target to be completed by 27/8/2019. 4. Total problem reported for August 2019 and resolved = 0; Application = 45; Hardware Failure = 56 | Project closure in progress. | Project closed |  |  | 100% (June 2019 = 82%)
47 | MOH | HKL-Bekalan Perkhidmatan Penggantian Server | 438043 | 2016-10-01 | 2019-11-30 | Bekalan Perkhidmatan Penggantian Server untuk Kegunaan Sistem Pengurusan Pesakit (SPP) Versi 2.6 Hospital Kuala Lumpur (With 3 years Warranty) | Suradi Abd Rahman | Mokhtar Atan | Noor Aini | Closed | NA | 438043 | 0 | 438043 |  |  |  | NA | NA | [5 empty] | NA
48 | LPPKN | Sistem Reproductive Health Information System (RHIS) Membekal, Menghantar, Mengkaji, Merekabentuk, Membangun, Menginstalasi, Menguji, Mentauliah Dan Menyelenggara Bagi Naik Taraf Sistem Reproductive Health Information System (RHIS) di LPPKN | 1901901.21 | 2016-11-01 | 2020-12-31 | 1. Pertukaran persekitaran Client Server kepada Web Based 2. Migrasi pangkalan data dari server RHIS Client Based kepada Web Based 3. Pembangunan Modul Offline 4. Integrasi data di antara RHIS & LIS 5. Integrasi di antara RHIS & SAGA 6. Pembangunan Modul Pelaporan 7. Pemasangan dan konfigurasi pekakasan dan perisian 8. Latihan (Teknikal, Pentadbir Sistem & Pengguna) 9. Helpdesk, sokongan operasi dan teknikal | Redzuan Amiruddin | Ahmad Zamin Mahadzir/TBA | Halimah Din | Development | No open or new issues | 1901901.21 | 0 | 1901901.21 | 1194654.7883 | 1. Overall completion, Plan = 86%, Actual = 86% 2. Plan to go live at all sites on 7/2/2019. Project Team will be on standby at selected sites although it is not an obligation to do so. | 1. Overall completion, Plan = 87%, Actual = 87% 2. Go live at all sites on 7/2/2019. Stabilisation and system monitoring in progress. 3. Next activity is technical training, scheduled to finish on 31/5/2019 | 1. Overall completion, Plan = 88%, Actual = 88% 2. Corrective maintenance in progress. 3. Next activity is technical training, scheduled to finish on 31/5/2019 | 1. Overall completion, Plan = 90%, Actual = 90% 2. Corrective maintenance in progress. 3. Next activity is technical training, scheduled to finish on 31/5/2019 | 1. Overall completion, Plan = 93%, Actual = 93% 2. Corrective maintenance in progress. 3. Next activity: - Technical training is rescheduled and target to complete by 30/9/2019. - Post Implementation Review (PIR), schedule to finish on 30/9/2019 - Monitoring & Stability (Corrective Maintenance Activity), schedule to finish on 31/10/2019 | 1. Overall completion, Plan = 94%, Actual = 94% 2. Corrective maintenance in progress 3. Next activity: - Technical training is rescheduled and target to complete by 30/10/2019. - Post Implementation Review (PIR), schedule to finish on 30/10/2019 - Monitoring & Stability (Corrective Maintenance Activity), schedule to finish on 31/10/2019 | 1. Overall completion, Plan = 96%, Actual = 96% 2. Corrective maintenance in progress 3. Next activity: - Technical training is rescheduled and target to complete by 30/10/2019. - Post Implementation Review (PIR), schedule to finish on 30/10/2019 - Monitoring & Stability (Corrective Maintenance Activity), schedule to finish on 31/10/2019 | 1. Overall completion, Plan = 98%, Actual = 98% 2. Corrective maintenance in progress 3. Next activity: - Technical training completed on 20/11/2019 - Post Implementation Review (PIR) completed on 20/11/2019 - Monitoring & Stabilisation (Corrective Maintenance Activity), scheduled to finish on 31/10/2019 | 1. Overall completion, Plan = 98.8%, Actual = 98.8% 2. Corrective maintenance in progress 3. Monitoring & Stabilisation (Corrective Maintenance Activity), rescheduled to finish from 31/10/2019 to 6/2/2020 (end of contract) | 87% (October 2019 = 87%) (September 2019 = 93%)
49 | MOH | SPP Application Maintenance-Hospital Taiping, Perak | 182320 | 2016-11-18 | 2018-09-17 | Perkhidmatan Penyelenggaraan dan Sokongan Operasi Bagi Aplikasi Sistem Pengurusan Pesakit (SPP) di Hospital Taiping, Perak | Redzuan Amiruddin | Ahmad Zamin Mahadzir/ Mokhtar Atan | Halimah/Sanuza | Closed | No open/new issue | 179740 | 2580 | 136740 | 344 |  |  | NA | NA | [5 empty] | NA
50 | JPJ | mySIKAP Maintenance (Software License Renewal 2015) | 3399877 | 2015-08-01 | 2015-12-31 | License Renewal | Hafazah Hafidz | Abdul Ghani | Mohd Hazly | Closed | NA | 3399877 | 0 | 3399877
51 | JPJ | mySIKAP Maintenance (Software License Renewal-Jan-Oct 2016) | 11391672.66 | 2016-01-01 | 2016-10-31 | License Renewal & DR Service | Hafazah Hafidz | NA | Mohd Hazly | Closed | NA | 11391672.66 | 0 | 11391672.66
52 | JPJ | mySIKAP Maintenance | 79768327.34 | 2016-11-01 | (31-Dec-2018) 30-Jun-2019 | 1.Corrective Maintenance Support Services (Application) 2.Preventive & Corrective warranty Support Services (COTS HW & SW) 3.Onsite Branch Support 4.Maintenance Support Services for Kiosk 5.On Request (All components) 6.Preventive & Corrective Maintenance for Network Security, LAN HW & SW and Technical Support 7.Preventive & Corrective Maintenance for Data Center, HW, SW and Technical Support 8.Disaster Recovery Development, Facilities & Services | Roslind Abd Rahman | Abd Ghani Abdullah/Abd Ghani Abdullah | Azrul Saad, Mohd Hazly | Project Closure | 1. (PSC 2/2018) For a CR that SPANCO pay directly to HeiTech, JPJ decided in CCB dated 23-1-18 that JPJ will pick up the cost and HTP need to return the payment made by SPANCO since there is no legal act that allow this transaction. Project Team will only reimburse the payment when JPJ has sent official notification and pay to HTP. (PSC 3/2018) JPP Meeting decision to proceed with payment for April and hold reimbursement to Spanco until further instruction from JPJ. (PSC 8/2018) JPJ has paid CR for SPANCO to HTP. HTP to reimburse payment received earlier from SPANCO. (PSC 1/2019) HTP has reimbursed the payment to SPANCO on 28/12/2019. (Closed) | 17904486.5 | 61863840.84 | 17904486.5 | 42197728.15 | 1. Overall completion: Plan = 100%; Actual = 100% 2. Corrective Maintenance 100%. 3. Preventive Maintenance 100% 4. Data Centre Cleaning 100% 5. DR completed 100% 6. SLA Achievement: No SLA breached 7. On Request (OR) Status: i) RM1,635,051.10 of OR could not be claimed from total allocation amount of RM11,095,834.69, which is about 15%. ii) Activities for the OR which have been claimed through LOU have been completed except for the following: - 8/11 OR from applications still in progress due to pending action by JPJ - Implementation of System VDI Training Room, JPJ Cyberjaya – pending delivery of 30 units of Zero-Client which target to be delivered 2nd week of February 2019 mySIKAP Maintenance Extension Status: 1. Pending LOA from JPJ, target to receive by 1/2/2019 2. Support services from 1/1/2019 -30/6/2019 or until new contract renewal awarded by JPJ 3. Purchase of license renewal and 3rd party hardware and software support will be pending on the issuance of LOA from JPJ 4. Budget for OR identified and allocated in mySIKAP extension contract is amount of RM1,585,625 | Project Closure will be done with mySIKAP Maintenance Extension. | Report on extension of contract | Status is reported under mySIKAP Extension | [5 empty] | PCR for September 2018 not available (Jan 2018 = 75%)
53 | FOMEMA | FOMEMA MYIMM Biometric Integration | 48230000 | 2017-01-01 | 2026-12-31 | 1.Integration of FOMEMA application 2.Supply, delivery and deployment of 3.Biometric Fingerprint Scanner 4.Maintenance | Ahmad Suryadi bin Abd Aziz | Ibrahim Yusoff | Halimah Din | Implementation | 1. (PSC 7 2018 - 23/7/2018) Subcontract between HTP and S5 is still pending for signing due to payment term which is not agreeable and uncertainty of project. Finance advised to hold the signing. New CEO to sign the Agreement 1st week of Oct with partial payment to S5. (PSC 12/2018) Contract signing still pending. Payment term still not confirmed and awaiting for top management decision. Letter of Demand received from S5 for payment. PM awaiting for management decision. (PSC 3/2019) Contract is still not signed due to indecisive amount of payment term from HTP Management. PM to send email to Group Finance VP to get confirmation status. (PSC 6/2019) PM plan to discuss with CFO on 27/7/2019. (PSC 7/2019) Management has agreed with payment terms and Finance will pay to S5 as agreed by both party. Subcontract document in progress for signing. (In progress) 2. (PSC 12/2019) i. JIM data issues ii. Fingerprint below threshold iii. Matching profiles not found PBJ agreed to start with fingerprint reenrolment exercise. (In progress) | 19817957.9 | 28412042.1 | 18378011.47 | 17750363.62 | 1. Overall completion = 85% 2.Pilot at clinics at 234 clinics still ongoing. 3. Go-live target is on April 2019. CSE to revisit 1,820 clinics in Klang Valley as preparation to go-live. 4. Maintenance activities: a) Request for Installation from clinics -Total : 1 - Success: 1 b) Problem Logs January 2019 : - Total Received : 142 - Open : 3 - Closed: 137 - Resolved: 1 5. Monthly report for December 2018 submitted on 16/1/2019. | 1. Overall completion = 85% 2.Pilot at clinics at 234 clinics still ongoing. 3. Go-live target is on April 2019. CSE to revisit 1,820 clinics in Klang Valley as preparation to go-live. 4. Maintenance activities: a) Request for Installation from clinics -Total : 44 - Success: 14 b) Problem Logs January 2019 : - Total Received : 160 - Open : 30 - Resolved: 7 - Closed: 123 5. Monthly report for January 2019 submitted on 26/2/2019. | 1. Overall completion = 85% 2.Pilot at clinics at 234 clinics still ongoing. 3. Go-live target is on April 2019. CSE to revisit 1,820 clinics in Klang Valley as preparation to go-live. 4. Maintenance activities: a) Request for Installation from clinics -Total : 59 - Success: 4 b) Problem Logs March 2019 : - Total Received : 177 - Open : 14 - Resolved: 53 (request for installation) - Closed: 110 5. Monthly report preparation for February 2019 is still in progress. Target completion 15/4/2019. | 1. Overall completion = 85% 2. Stage 1: Pilot at 234 clinics still ongoing. 3. Stage 2: Go-Live for Klang Valley clinics/panels = 1,078 from 1820 clinics.Go-Live for Klang Valley clinics/panels = 1,078 from 1820 clinics. - Selangor = 781, KL = 294, Putrajaya = 3 Stage 3: Go-Live for other states target to complete in batches by 31/12/2019 ‒ Negeri Sembilan & Melaka ‒ Perlis, Kedah & Pulau Pinang ‒ Kelantan, Terengganu & Pahang ‒ Perak & Johor 4. Maintenance activities: a) Request for Installation from clinics (528 clinics which are not ready as at 27/5/2019) -Total request + installed = 38 - No response yet = 490 b) Problem Log May 2019: - Total Received = 259 - Open = 3 - Closed = 256 6. Monthly report preparation for April 2019 completed on 17/5/2019. | 1. Overall completion = 92% 2. Pilot Production stage 3 - Go-Live for clinics/panels = 15%, started on 10/6/2019 and target to completed on 10/7/2019. - Negeri Sembilan, Melaka, Pahang, Perak (761 panels) - Johor, Kelantan & Terengganu (In Plan) - Total Online Panels = 2,194 3. Maintenance activities: a) Request for new Installation on 528 panel Unreadiness clinics, start date 1/7/2019 and end 25/7/2019 -Total request + installed = 56 - No response yet = 472 -Installation in August 2019 =8 b) Problem Log July 2019: - Total Received = 284 - Open = 0 - Closed = 284 4. Monthly report preparation for July 2019 completed on 20/8/2019. | 1. Overall completion = 95% 2. Pilot Production stage 3 (761 panels) - Go-Live for clinics/panels = 75%, started on 10/6/2019 and target to completed on 10/7/2019. - Negeri Sembilan = 71%, Melaka = 74%, Pahang = 93%, Perak = 68% - Johor, Kelantan & Terengganu (In Plan) - Total Online Panels = 2,194 3. Maintenance activities: a) Request for new Installation on 528 panel Unreadiness clinics, start date 1/9/2019 and end 24/9/2019 -Total request + installed = 75 - No response yet = 453 -Installation in August 2019 =9 b) Problem Log Sept 2019: - Total Received = 219 - Open = 0 - Closed = 219 4. Monthly report preparation for August 2019 completed on 19/8/2019. | 1. Overall completion = 97% 2. Pilot Production stage 3 (761 panels) - Go-Live for clinics/panels = 98%, started on 10/7/2019 and target to complete on 31/12/2019. - Negeri Sembilan = 100%, Melaka = 100%, Pahang = 100%, Perak = 96% 3. Pilot Production stage 4 (566 panels) - Go-Live for clinics/panels = 65%, started on 1/10/2019 and target to complete on 31/12/2019. - Kedah = 35%, Penang = 33%, Kelantan = 100%, Terengganu = 95% - Total Online Panels = 2,760 3. Maintenance activities: a) Request for new Installation on 528 panel Unreadiness clinics, start date 1/10/2019 and end 31/10/2019 -Total request + installed To Date = 83 - No response yet = 438 - Installation in October 2019 =15 b) Problem Log Sept 2019: - Total Received = 269 - Open = 14 - Closed = 251 4. Monthly report preparation for September 2019 completed on 17/10/2019. | 1. Overall completion = 98% Pilot Production: Total Online Panels = 2,760 2. Stage 3 (761 panels) - Perak = 96% 3. Stage 4 (566 panels) - Go-Live for clinics/panels = 89%, started on 7/10/2019 and target to complete on 31/12/2019. - Kedah = 45%, Penang = 40%, Kelantan = 100%, Terengganu = 100% 4. Stage 5 (655 panels) - Go-Live for clinics/panels = 12%, started on 7/112019 and target to complete on 31/12/2019. - Johor = 12%, Perlis = 33%, Labuan = 0% 5. Maintenance activities: a) Request for new Installation on 528 panel non-ready clinics, start date 1/10/2019 and end 31/10/2019 - Total request + installed To Date = 96 - No response yet = 425 - Installation in November 2019 =13 b) Problem Log November 2019: - Total Received = 371 - Open = 75 - Closed = 282 6. Monthly report preparation for October 2019 completed on 19/11/2019. | 1. Overall completion = 99% Pilot Production: Total Online Panels = 3,415 2. Stage 3 (761 panels) - Perak = 100% 3. Stage 4 (566 panels) - Go-Live for clinics/panels = 93%, started on 7/10/2019 and target to complete on 31/12/2019. - Kedah = 100%, Penang = 87%, Kelantan = 100%, Terengganu = 100% 4. Stage 5 (655 panels) - Go-Live for clinics/panels = 81%, started on 7/112019 and target to complete on 31/12/2019. - Johor = 78%, Perlis = 100%, Labuan = 100% 5. Maintenance activities: a) New Installation on 528 panel, start date 1/12/2019 and end 20/12/2019 - Total request + installed To Date = 96 - No response yet = 425 - Installation in December 2019 =10 b) Problem Log December 2019: - Total Received = 229 - Open = 11 - Closed = 193 6. Monthly report preparation for November 2019 completed on 20/12/2019. | 93% (October 2019 = 93%) (September 2019 = 93%)
54 | DEFENSE | SUKHOI-30MKM - TOFT, CBT & Infra Maintenance | 258000000 | 2007-01-10 | 2020-11-30 | Maintenance and operational services for TOFT, CBT and Infra | Mohd Noor Ezan | Siti Shahwana Abdul Hamid | Halimah Din | Under PMC monitoring | 1. Old computer hardware already > than 5 years. All CPUs were in operation since 2009. Project Team has got approval from Management to proceed with MLU ( Mid-Life Upgrade) for critical components eg. Projectors, UPS, TOFTs. (n progress) | 216548000 | 41452000 | 207948000 | 189372096 |  |  | NA | NA | [5 empty] | NA
55 | JPJ | Next Generation Firewall | 2752960 | 2017-06-01 | 2017-09-21 | Delivery, Installation, Commisioning & Warranty Support for Next Generation Firewall Hardware & Software. | Reduzan Ab Jalil (Redzuan Amiruddin) | Abd Ghani Abdullah | Mohd Hazly | Closed | 1. Hardware delivery issue. PM to revise and finalise deployment plan and ensure timeline is within the agreed project duration.(Closed) 2. License supplied by Data Alliance required additional 25 days in order to comply with project requirement. PM to discuss with Data Alliance. Received updated license on 26/12/2017. Activated via remote on 27/12/2017. (Closed) | 2752960 | 0 | 2752960 | 2143034.49 |  |  | NA | NA | [5 empty] | NA
56 | MOH | SPP CAS PHIS Integration-Hospital Raja Permaisuri Bainun Ipoh | 396556.6 | 2017-06-01 | 2020-08-31 | 1. Reconfigure Glassfish SPP application server 2. SPP Database - Alter related database - Check and update mapping reference table 3. Perform Data migration for encounter active 4. Application SPP v3.5 - Integration with existing SPP sources code at Hospital - Configure contact patch 5. Install and configure Mirth Component 6. Install and configure CAS Component 7. Install CAS icon, url, ie setting and certificate at 1,100 workstation 8. On going support and maintenance services for 3 years upon go live | Suradi Abd Rahman | Ahmad Zamin Mahadzir/TBA | Halimah Din | Maintenance | 1. CMG technical team to investigate the TLS and PC setting issue and coming up with result or resolution before 15/2/2019. IT Team still doing the testing. Update: No additional setting done to TLC n PC since letsencrypt option is used to generate ssl cert instead of previously used option selfsign. (Closed) | 396556.6 | 0 | 293658.16 | 10737.06 | 1. Maintenance support is on going. 2. Upgrade CAS completed | 1. Maintenance support is on going. | 1. Maintenance support is on going. | 1. Maintenance support is on going. | 1. Maintenance support is on going. | 1. Maintenance support is on going. | 1. Maintenance support is on going. | 1. Maintenance support is on going. | 1. Maintenance support is on going. | NA
57 | MOH | RIS PACS HIS@KKM Fasa I | 10123738.82 | 2017-07-17 | 2020-01-16 | 1. Enhance& Implement RIS Module 2. Delivery & Installation of Picture Archiving Communication System (PACS) 3. Integration of Modalities, PACS and SPP RIS 4. Migration of Data & Mini PACS 5. Delivery & Installation of Hardware & Software 6. Installation of LAN/Fiber Optice cabling and upgrade Network Infrastructure 7. Installation of Electrical switch socket outlet and distribution board 8.Testing, UAT, PAT and FAT 9. Change Management and Benefit Realisation 10. Training & Transfer of Technology 11. Helpdesk ( i-DESK) 12. Implementation and Warranty Support at HRPZII will commence after 19/8/2019 (FAT date). | Suradi Abdul Rahman (Norashikin Bt Baharudin) | Ahmad Zamin Mahadzir/ Ibrahim Yusoff | Hamid Baharudin | Development | 1. (PSC 7/2019) Issue of slowness to the SPP system arised with implementation of RISPACS. Project team is required to take interim action to the issue and resolve during the FAT period. Failure to resolve the issue will cause no acceptance for FAT. Currently, project team is diagnosing and taking necessary action. Solution to be presented to HRPZII on 7/10/2019. (PSC 8/2019) Solution presented to KKM to use load balancer since source code of SPP couldn't be touch. (In progress) 2. (PSC 8/2019) Cabling at HRPZ was not properly arrange and the cable rack door couldn't be closed. HRPZ requested for the cable to be arranged properly. Project Team need to get new contractor to execute the exercise since the previous contractor is no longer available. (In progress) | 7455217.95 | 2668520.87 | 7455217.95 | 7844494.5106 | 1. Overall status completion: Plan = 80%. Actual = 74%, 2. Application Development status: overall status 100% - SDD 100% - Database design 100% - Coding & Unit test 100% 3. UAT conducted from 30/12/2018 - 21/1/2019 was unsuccessful. System not fully ready to be tested. i) UAT Cycle 1: 30/12/2018 – 3/1/2019 - Total test cases = 121; Success = 6 (5%), Fail = 108 + Not tested = 7 (95%), No of logs = 444 ii) UAT Cycle 2: 20 - 23/1/2019 - Project Team in process of compiling test result and rectifying bugs and errors. 4. Performance test plan presented to KKM on 6/1/2019; feedback from KKM is for Project Team to also use tool which KKM have. Project Team need to further discuss internally. 5. Based on UAT activities result, training and subsequent activities will be delayed accordingly. Go Live may be delayed to April 2019. Risk of being imposed to LAD for 2 months delay. 6. PACS Installation & Modality Integration 100% PACS has been changed from MedWeb to Fuji Synapse 5 to resolve issues. Project Team to formally inform KKM of the changes. The new PACS has been installed on 24- 25/1/2019. Project Team to check on back-to-back SLA with ViaMed. 7. Change Management Program completed 71% ; Benefits Realisation activity completed 58% | 1. Overall status completion: Plan = 82%. Actual = 73%, (as at 26/2/2019) 2. Application Development status: overall status 100% - SDD 100% - Database design 100% - Coding & Unit test 100% 3. UAT Cycle 3 Status: Bug fixing status as at 26/2/2019: Total = 378, Resolved = 173, Closed = 178, Open 27 Test script status as at 22/2/2019: Total test scirpt = 155, Ready to review = 142, Not ready = 13 Internal system testing status: Total test script: 155, Tested=17, Success = 11, Fail 6 4. Based on UAT activities result, training and subsequent activities will be delayed accordingly. Go Live will be delayed. 5. PACS Installation & Modality Integration 100% PACS has been changed from MedWeb to Fuji Synapse 5 to resolve issues. Project Team to formally inform KKM of the changes. The new PACS has been installed on 24- 25/1/2019. Project Team to check on back-to-back SLA with ViaMed. 6. Change Management Program completed 71% ; Benefits Realisation activity completed 58% | 1. Overall status completion: Plan = 85%. Actual = 74%, (as at 26/3/2019) 2. Application Development status: overall status 100% - SDD 100% - Database design 100% - Coding & Unit test 90% 3. UAT completed 80% i) UAT Cycle 2 Status as at 13/3/2019: Bug fixing: Done = 377 Test script : Done = 161 Internal system testing: Done = 161 ii) UAT Cycle 3 target to start from 22/4/2019 – 29/4/2019 4. Training target to be done 16/6/2019 – 8/7/2019 5. PACS Installation & Modality Integration completed 99%. Percentage change due to change of PACS from MedWeb to Fuji Synapse 5. 6. Change Management Program completed 73%; Benefits Realisation activity completed 58% | 1. Overall status completion: Plan = 87%. Actual = 74%, 2. Application Development status: overall status 100% - SDD 100% - Database design 100% - Coding & Unit test 90% 3. UAT completed 80% i) Result for UAT Cycle 3: Total fail test case = 49/164 with 252 logs; Fail result was divided into critical (13) and non-critical (36); Testing and verifying with KKM to continue from 27 – 30/6/2019. ii) Meeting with KKM on 15/5/2019: To go-live when 100% pass for critical test script and 100% pass for non-critical before FAT 4. Training target to be done 16/6/2019 – 8/7/2019 5. PACS Installation & Modality Integration completed 99%. T&C of Fuji Synapse 5 is in progress and target to complete by 17/5/2019. | 1. Overall status completion: Plan = 87%. Actual = 86% 2. Application Development status: overall status 100% - SDD 100% - Database design 100% - Coding & Unit test 100% - UAT completed 100% 3. Result for UAT Cycle 3: As at 1/8/2019 Total test case = 164, Critical test case = 96, Pass = 96 (100%) Non-critical = 68, Pass = 60, Fail = 8 4. Result PAT sessions: Total = 16, Pass = 14, Fail = 2 5. Issue log summary by Category: Total = 835, SPP =105, RIS = 523, PACS = 74, MIRTH = 96, CONFIG = 9, Network = 6, Hardware=3, Others = 21 6. Issue log summary by status: Total = 835, Resolved = 656, Closed = 102, Open = 77 7. SPP Billing Issue Logs from 18/7/2019 - 28/8/2019 - Number of logs by status: Total = 52, Closed = 11, Open = 41 - Open Logs by category & Month: Total = 41, - July (Data Error = 8, User Error = 1), - August (Data Error = 31, User Error = 0) 8. Proposal on Project Timeline Changes to KKM for approval - Provisional Acceptance Test (PAT): 18/7/2019 – 24/9/2019 - Final Acceptance Test (PAT): 25/9/2019 – 15/10/2019 - Warranty & Support: 16/10/2019 – 15/10/2019 | 1. Overall status completion: Plan = 86%. Actual = 84% 2. Application Development status: overall status 100% - SDD 100% - Database design completed 100% - Coding & Unit test completed 100% - UAT completed 100% - Training completed 100% - PAT completed 100% - Change Management completed 80% 3. Result for Test Case As at 24/9/2019 Total test case = 164, Critical test case = 96, Pass = 100% Non-critical = 68, Pass = 65, Fail = 3 4. Result PAT sessions: Total = 16, Pass 16, Fail 0 5. SPP Billing Issue Logs - Number of logs by status: Total = 66, Closed 66, Open 0 6. Proposal Project Timeline changes - Provisional Acceptance Test (PAT): 18/7/2019 – 24/9/2019 - Final Acceptance Test (PAT): 25/9/2019 – 15/10/2019 - Warranty & Support: 16/10/2019 – 15/10/2019 | 1. Overall status completion: Plan = 87%. Actual = 85% 2. Application Development status: overall status 100% - SDD 100% - Database design completed 100% - Coding & Unit test completed 100% - UAT completed 100% - Change Management completed 80% - Benefits Realisation 88% - Training completed 100% - PAT completed 100% - FAT completed 90% 3. Result for FAT transaction scenario as at 30/10/2019 Transaction/Scenario = 40, Pass = 37 (93%), Fail/Retest = 4 (7%) 4. Total logs by category = 1,107, SPP = 232, RIS = 748, PAC = 88, Network = 6, Hardware = 8, Other = 25 5. Total logs by status = 1,107, Closed =1,027, Resolved = 16, Open= 64 | 1. Overall status completion: Plan = 100%. Actual = 90% 2. Application Development status: overall status 100% - SDD 100% - Database design completed 100% - Coding & Unit test completed 100% - UAT completed 100% - Change Management completed 80% - Benefits Realisation 90% - Training completed 100% - PAT completed 100% - FAT completed 100% - Warranty & Support completed 8% 3. Activities in warranty & support period: - Auto Login completed 90%, target completion 21/12/2019 - SMRP completed 29%, target completion 24/1/2020 - RFR completed 6%, target completion 7/5/2020 - Forensic completed 22%, target completion 9/7/2020 - Stand Alone not started 0%; target completion 21/8/2020 | 1. Overall status completion: Plan = 100%. Actual = 91% 2. Application Development status: overall status 100% - SDD 100% - Database design completed 100% - Coding & Unit test completed 100% - UAT completed 100% - Change Management completed 80% - Benefits Realisation 90% - Training completed 100% - PAT completed 100% - FAT completed 100% - Warranty & Support completed 8% 3. Activities in warranty & support period: - Auto Login completed 100%, completed on 21/12/2019 - SMRP completed 29%, target completion 24/1/2020 - RFR completed 6%, target completion 7/5/2020 - Forensic completed 22%, target completion 9/7/2020 - Stand Alone not started 0%; target completion 21/8/2020 | 55% (November 2019 = 55%) (October 2019 = 60%) (September 2019 = 50%) (August 2019 = 64%)
58 | JIM | MyIMMs Application Maintenance (2017-2020) | 42430740 | 2017-08-18 | 2020-08-17 | 1. Applications Corrective Maintenance 2. Preventive Maintenance at 254 JIM branches (local & overseas) 2. Change Request and Integration 3. Installation, testing and monitoring of system at new location for not more than 30 locations 4. Training, Contract Performance Review session, Certification Program and Workshop for users and IT personnel of JIM 5. System Audit Services at least once in contract duration | Rohani Shariff | Md Zaidan Md Zain/ Azlan Abd Hamid | Ahmad Puzi, Azmin | Maintenance | 1. (PSC 7/2018 - 25/7/2018) System slow response which may be due to high bandwidth utilisation. Project team need to measure myIMMS bandwidth requirement and submit to JIM BTMR. (PSC 10/2018) BTMR still has not given the required bandwidth to be tested. (PSC 12/2018) Project Team has installed a few tools to collect the information that might caused the slow response and will come out with the following: - Optimum size of bandwidth required by myIMMs Web - Any process/SQL that can be enhanced/optimized (PSC 1/2019) Project Team need a license monitoring tool to investigate application slow response/hang issues. - SDC proposed to use the trial version temporarily. (Latest update as at 31/12/2019) - Bandwidth has been shared with JIM and most main JIM branches have been upgraded except for small branches. Upgrading of bandwidth is under JIM action. (Closed) 2. (PSC 11/2018) - KPI raised concern that Transformation not completing as target in August 2018. HTP had send justification letter for the delays on 13/11/2018. But, pending reply from KDN. (PSC 1/2019) - Project Team has revised the timeline and target to complete the project by 31/5/2019. PM was given the budget to pay for extra effort done by Project team as motivation to expedite activities and successfully done for preparation of program specification. It will be extended to application development. PM to monitor the quality of work done. (PSC 6/2019) Roll-out of all systems except Sistem Kawalan have been done successfully. Kawalan is target to complete in August 2019. (PSC 10/2019) Roll-out for Sistem Kawalan A (17 transactions) has already completed and pilot at KLIA2 since 8/8/2019. Roll-out will be done when 27 transactions in Kawalan B complete. Kawalan B was delayed since user won’t accept. Project team in process of fulfilling the requirement. Target completion pilot 2 on15/11/2019. (PSC 12/2019)- Target pilot 2 at KLIA2 is rescheduled to 10/1/2020 and rollout will be from 13/1/2020 until 31/1/2020. (In progress) 3. (PSC 12/2019) - XML Injection must be completed by 30/3/2020 but the project team is facing technical errors during internal testing and need help from HTP technical experts. (In progress) | 29230993.19 | 13199746.81 | 29161603.19 | 15425784.14 | myIMMS Maintenance Status as at 25/1/2019: 1. Overall completio: Plan = 49.97%; Actual = 49.97% 2. Technical Support Services: i) Problem Log: Total log = 19,760. Resolved = 19,700 and In progress = 60 ii) Corrective Maintenance: Total log =186. New = 0, In progress =5, Closed = 177, Drop = 4 3. Preventive maintenance: PM activities for Year 2 completed 182/259 branches 4. CR and Integration: Total CR = 133. New= 3, In progress= 4, Done UAT = 24, Completed = 82, KIV = 4, Drop = 13 5. Peluasan & perpindahan: Year 2 Completed Cameron Highland (9/10/2018) and Besut (7/12/2018); next branch in planning is Jempol (NS) 6. Training Year 2: Completed User Training=7/28, Technical training = 2/4, CPR workshop=1/5, Professional certification = 0/8, Technical workshop conf/seminar = 0/3 7. System Audit services: Target to start from January - June 2019. Transformation: 1. Overall completion: Plan = 74%; Actual = 67 2. Phase 1 progress i) Passport Module (25 txns) - development completed 100% ii) Roll-out status completion: 90/99 branches have been implemented. Target completion is by March 2019 (as per PM activity schedule). 3. Phase 2 progress i) Pasport (10 txns) - development completed 100% - Roll-out in progress with Phase 1 implementation ii) Permit (22 txns) - development completed 100% - Roll-out in progress, completed 43/43 branches (previously 44 permit branches, but JPJ Keningau doesn’t received permit application) iii) Border Control (39 txns) - development completed 78% - Roll-out to be done with other Border Control transactions of Phase 3 in May 2019 iv) zCon-32K – pending testing and deployment to production 4. Phase 3 progress i) Development completion status: - Passport + Maintenance: 67% completed development - Border Control & Perkapalan: 30% completed development - Permit: 75% completed development - Revenue: 35% completed development - Stock Control: 37% ii) Roll-out completed 4%; 5 txn/347 txn roll out. iii) Development activities target to complete by April 2019 iv) Roll-out for Phase 3 will be done upon development completion of all modules and target to complete by May 2019 | myIMMS Maintenance Status as at 26/2/2019: 1. Overall completion: Plan = 50%; Actual = 50% 2. Technical Support Services: i) Problem Log: Total log = 20,266. Resolved = 20,206 and In progress = 60 ii) Corrective Maintenance: Total log =267. New = 0, In progress =40, Closed = 227, Drop = 4 3. Preventive maintenance: PM activities for Year 2 completed 207/259 branches 4. CR and Integration: Total CR = 134. New= 3, In progress= 7, Done UAT = 22, Completed = 85, KIV = 4, Drop = 13 5. Peluasan & perpindahan: Year 2 Completed Cameron Highland (9/10/2018) and Besut (7/12/2018); next branch in planning is Jempol (NS) 6. Training Year 2: Completed User Training=8/28, Technical training = 2/4, CPR workshop=2/5, Professional certification = 1/8, Technical workshop conf/seminar = 0/3 7. System Audit services: Target to start from January - June 2019. Transformation: 1. Overall completion: Plan = 78%; Actual = 71% 2. Phase 1 progress i) Passport Module (25 txns) - development completed 100% ii) Roll-out status completion: 92/99 branches have been implemented. Target completion is by March 2019 (as per PM activity schedule). 3. Phase 2 progress i) Pasport (10 txns) - development completed 100% - Roll-out in progress with Phase 1 implementation ii) Permit (22 txns) - development completed 100% - Roll-out completed iii) Border Control (39 txns) - development completed 78% - Roll-out to be done with other Border Control transactions of Phase 3 in May 2019 iv) zCon-32K – pending testing and deployment to production 4. Phase 3 progress i) Development completion status: - Passport + Maintenance: 70% completed development - Border Control & Perkapalan: 56% completed development - Permit: 77% completed development - Revenue: 50% completed development - Stock Control: 42% ii) Roll-out completed 4%; 5 txn/347 txn roll out. iii) Development activities target to complete by April 2019 iv) Roll-out for Phase 3 will be done upon development completion of all modules and target to complete by May 2019 | myIMMS Maintenance Status as at 23/3/2019: 1. Overall completion: Plan = 52.41%; Actual = 52.41% 2. Technical Support Services: i) Problem Log: Total log (until 22/3/2019) = 22,311. Resolved = 22,267; In progress = 4; Total log for March 2019 = 1,060. Resolved = 1,016; In progress = 42 ii) Corrective Maintenance: Total log =199. New = 0, In progress = 5, Closed = 190, Drop = 4 3. Preventive maintenance: PM activities for Year 2 completed 238/259 branches (92%) 4. CR and Integration: Total CR = 134. New= 3, In progress= 7, Done UAT = 22, Completed = 85, KIV = 4, Drop = 13 5. Peluasan & perpindahan: Year 2 Completed Cameron Highland (9/10/2018) and Besut (7/12/2018); next branch in planning is Jempol (NS) still no instruction from JIM 6. Training Year 2: Completed User Training = 15/28, Technical training = 2/4, CPR workshop=2/5, Professional certification = 2/8, Technical workshop conference/seminar = 0/3 7. System Audit services: Target to execute from April - June 2019. Transformation: 1. Overall completion: Plan = 82%; Actual = 75% 2. Phase 1 progress i) Passport Module (25 txns) - development completed 100% ii) Roll-out status completion: 97/99 branches have been implemented. Target completion is first week of April 2019 (as per PM activity schedule). 3. Phase 2 progress i) Pasport (10 txns) - development completed 100% - Roll-out in progress with Phase 1 implementation ii) Permit (22 txns) - development completed 100% - Roll-out completed iii) Border Control (39 txns) - development completed 83% - Roll-out to be done with other Border Control transactions of Phase 3 in May 2019 iv) zCon-32K – pending testing and deployment to production 4. Phase 3 progress i) Development completion status: - Passport + Maintenance: 76% completed development - Border Control & Perkapalan: 65% completed development - Permit: 84% completed development - Revenue: 59% completed development - Stock Control: 50% ii) Roll-out completed 4%; 5 txn/347 txn roll out. iii) Development activities target to complete by April 2019 iv) Roll-out for Phase 3 will be done upon development completion of all modules and target to complete by May 2019 | myIMMS Maintenance Status as at 24/5/2019: 1. Overall completion: Plan = 58%; Actual = 58% 2. Technical Support Services: i) Problem Log: Total log (until 24/5/2019) = 23,907, Resolved = 23,234; In progress = 49; Total log for May 2019 = 722. Resolved = 673; In progress = 49 ii) Corrective Maintenance: Total log =219. Closed = 211, In progress = 4, Cancel = 4 3. Preventive maintenance: PM activities for Year 2 completed 259/259 branches, 100% completed 4. CR and Integration: Total CR = 169. New= 3, In progress= 17, Done UAT = 25, Completed = 102, KIV = 7, Drop = 15 5. Peluasan & perpindahan: Year 2 Completed Cameron Highland (9/10/2018) and Besut (7/12/2018); next branch in planning is Jempol (NS) still no instruction from JIM 6. Training Year 2: Completed User Training = 22/28, Technical training = 2/4, CPR workshop= 3/5, Professional certification = 3.5/9, Technical workshop conference/seminar = 0/3 7. System Audit services: Project Team can start work with Cybersecurity based on email sent to AM on 24/5/2019. AM to initiate for purchase requisition for PO issuance. Transformation: 1. Overall completion: Plan = 91%; Actual = 85% 2. Phase 1 progress: Passport Module (25 txns) - completed 100% 3. Phase 2 progress i) Passport (10 txns) - completed 100% ii) Permit (22 txns) – completed 100% iii) Border Control (39 txns) - development completed 96%, pending UAT date. - Roll-out to be done with other Border Control transactions of Phase 3 iv) zCon-32K – 100% completed 4. Phase 3 progress i) Development completion status: - Passport + Maintenance: 100% completed development; target complete roll-out 31/5/2019 - Border Control & Perkapalan: 73% completed development, SIT 23 – 31/5/2019 - Permit: 100% completed development; - Revenue: 89% completed development, UAT done by 28/5/2019, - Stock Control: 98% completed development; UAT done by 28/5/2019, ii) Roll-out status: - Passport + Maintenance and Permit: target to complete by 31/5/2019, - Stock Control: target pilot 18/6/2019, target roll-out 25/6/2019; - Revenue: target pilot 18/6, target roll-out 25//6/2019 - Sistem Kawalan: SIT in progress 23-31/5/2019, UAT and roll-out yet to be confirmed. | myIMMS Maintenance Status as at 20/8/2019 1. Overall completion: Plan = 65%; Actual = 65% 2. Technical Support Services: i) Problem Log: Total log for August 2019 = 967. Resolved = 855; In progress = 112 ii) Corrective Maintenance: Total log =231. Closed = 219, In progress = 7, Cancel = 5 3. Preventive maintenance: PM activities for Year 2 completed 259/259 branches, 100% completed 4. CR and Integration: Total CR = 191. New= 1, In progress= 10, Done UAT = 22, Completed = 135, KIV = 8, Drop = 15 5. Peluasan & Perpindahan: Year 2 Completed Cameron Highland (9/10/2018) and Besut (7/12/2018); next branch in planning is for year 3, start 18/8/2019. 6. Training Year 2: Completed User Training = 28/28, Technical training = 3/4, CPR workshop= 3/5, Professional certification = 6.5/9, Technical workshop conference/seminar = 0/2 7. Training Year 2: Completed User Training = 2/24, Technical training = 0/4, CPR workshop= 0/5, Professional certification = 0/7, Technical workshop conference/seminar = 0/2 8. System Audit services: PO has been submitted to CSM in July 2019. | myIMMS Maintenance Status as at 19/9/2019: 1. Overall completion: Plan = 66%; Actual = 66% 2. Technical Support Services: i) Problem Log: Total log for September 2019 = 678. Resolved = 607; In progress = 71 ii) Corrective Maintenance: Total log =240. Closed = 221, In progress = 14, Cancel = 5 3. Preventive maintenance: i) PM activities for Year 2 completed 259/259 branches, 100% completed ii) PM activities for Year 3 completed 248/6 branches, 2% completed 4. CR and Integration: Total CR = 195. New= 1, In progress= 10, Done UAT = 23, Completed = 139, KIV = 6, Drop = 16 5. Peluasan & Perpindahan: Year 2 Completed Cameron Highland (9/10/2018) and Besut (7/12/2018); next branch in planning is for year 3, start 18/8/2019. 6. Training Year 2: Completed User Training = 28/28, Technical training = 3/4, CPR workshop= 4/5, Professional certification = 7.5/9, Technical workshop conference/seminar = 0/2 7. Training Year 3: Completed User Training = 2/24, Technical training = 0/4, CPR workshop= 0/5, Professional certification = 0/7, Technical workshop conference/seminar = 0/2 8. System Audit services on going 15/7/2019 and target completed 30/11/2019 Transformation: 1. Overall completion: Plan = 100%; Actual = 88% 2. Phase 1 progress: i. Passport Module (26 txns) - completed 100% 3. Phase 2 progress i. Permit (10 txns) - completed 100% 4. Phase 3 progress i. Kawalan A (17 txns) – completed 100% ii. Passport & Selenggara (95 txns) – completed 100% iii. Kawalan B & kapal (129 txns) – completed 74% iv. Permit (67 txns) – completed 100% v. Kutipan Hasil (34 txns) – completed 100% vi. Kawalan Stok (28 txns) – completed 100% 3. Remaining transactions in Phase 2 and Phase 3 is reported according to module as follows: - Kawalan A: Pilot = 08/08/2019, Roll- out = 15/10/2019 - Passport & Selenggara: roll-out done = 27/06/2019-15/07/2019 - Kawalan B & Perkapalan : i) SIT 1: 13-27/9/2019 (27 Transactions), UAT 1= 02-04/10/2019, Pilot =14-18/10/2019 ii) SIT 2: 09-18/10/2019 (78 Transactions), UAT 2= 29-31/10.2019, Pilot 2=11-15/11/2019 | myIMMS Maintenance Status as at 29/10/2019: 1. Overall completion: Plan = 72%; Actual = 72% 2. Technical Support Services: i) Problem Log: Total log for October 2019 = 980. Resolved = 840; In progress = 80 ii) Corrective Maintenance: Total log =240. Closed = 223, In progress = 12, Cancel = 5 3. Preventive maintenance: i) PM activities for Year 2 completed 259/259 branches, 100% completed ii) PM activities for Year 3 completed 247/25 branches, 10% completed 4. CR and Integration: Total CR = 197. New= 1, In progress= 9, Done UAT = 23, Completed = 145, KIV = 6, Drop = 16 5. Peluasan & Perpindahan: Year 2 Completed Cameron Highland (9/10/2018) and Besut (7/12/2018); next branch (Jempol, Negeri Sembilan) in planning is for year 3, start 18/8/2019. 6. Training Year 2: Completed User Training = 28/28, Technical training = 4/4, CPR workshop= 4/5, Professional certification = 7.5/9, Technical workshop conference/seminar = 0/2 7. Training Year 3: Completed User Training = 2/24, Technical training = 0/4, CPR workshop= 0/5, Professional certification = 0/7, Technical workshop conference/seminar = 0/2 8. System Audit services on going 15/7/2019 and target completed 30/11/2019. Transformation: 1. Overall completion: Plan = 100%; Actual = 88% 2. Phase 1 progress: i. Passport Module (26 txns) - completed 100% 3. Phase 2 progress i. Permit (10 txns) - completed 100% 4. Phase 3 progress i. Kawalan A (17 txns) – completed 100% ii. Passport & Selenggara (95 txns) – completed 100% iii. Kawalan B & kapal (129 txns) – completed 74% iv. Permit (67 txns) – completed 100% v. Kutipan Hasil (34 txns) – completed 100% vi. Kawalan Stok (28 txns) – completed 100% 3. Remaining transactions in Phase 2 and Phase 3 is reported according to module as follows: - Kawalan A: Pilot = 08/08/2019, Roll- out = 15/10/2019 - Passport & Selenggara: roll-out done = 27/06/2019-15/07/2019 - Kawalan B & Perkapalan : i) SIT 1: 13-27/9/2019 (27 Transactions), UAT 1=02-04/10/2019, Pilot =14-18/10/2019 (Pending) ii) SIT 2: 09-18/10/2019 (78 Transactions), UAT 2= 29-31/10.2019, Pilot2=11-15/11/2019 (Pending) - Permit: Roll-out done for 14 branches, to roll-out 30 branches with passport roll-out - Revenue: Pilot = 09/07/2019, roll-out = 15/07/2019 - Kawalan Stok: Pilot = 21/08/2019, roll-out =30/09/2019 | myIMMS Maintenance Status as at 20/11/2019: 1. Overall completion: Plan = 75%; Actual = 75% 2. Technical Support Services: i) Problem Log: Total log for November 2019 = 717. Resolved = 615; In progress = 65 ii) Corrective Maintenance: Total log =257. Closed = 235, In progress = 14, Cancel = 5 3. Preventive maintenance: i) PM activities for Year 2 completed 259/259 branches, 100% completed ii) PM activities for Year 3 completed 247/74 branches, 30% completed 4. CR and Integration: Total CR = 212 New= 2, In progress= 12, Done UAT = 25, Completed = 150, KIV = 7, Drop = 16 5. Peluasan & Perpindahan: Year 2 Completed Cameron Highland (9/10/2018) and Besut (7/12/2018); next branch (Jempol, Negeri Sembilan) in planning is for year 3, start 18/8/2019. 6. Training Year 2: Completed User Training = 28/28, Technical training = 4/4, CPR workshop= 4/5, Professional certification = 9/9, Technical workshop conference/seminar = 0/2 7. Training Year 3: Completed User Training = 2/24, Technical training = 0/4, CPR workshop= 0/5, Professional certification = 0/7, Technical workshop conference/seminar = 0/2 8. System Audit services on going 15/7/2019 and target completed 30/11/2019. Transformation: 1. Overall completion: Plan = 100%; Actual = 90% 2. Progress: i. Passport & Selenggara – completed ii. Permit– completed iii. Kutipan Hasil – completed iv. Kawalan Stok: Target Pilot = 21/08/2019, New Target Date = 06/12/2019 v. Change Request = 16/10/2019-8/11/2019, SIT = 02-06/12/2019, UAT = 11-18/12/2019, Pilot = 02/01/2020 vi. Kawalan A: Pilot = 08/08/2019, Roll- out = 15/10/2019 vii. Kawalan B: Total Transactions = 127, SIT Done = 52, SIT In Progress = 6, Pilot = 1, SIT-Ready (Test Done) = 25, In Progress = 43 - SIT final = 02-06/12/2019, UAT= 11-20/12/2019, Pilot = 23-31/12/2019 (Preparation), 02-10/01/2020 (Pilot@KLIA2), RollOut = 13/01/2020 – 31/01/2020 (16 lokasi) | myIMMS Maintenance Status as at 18/12/2019: 1. Overall completion: Plan = 77%; Actual = 77% 2. Technical Support Services: i) Problem Log: Total log for December 2019 = 751. Resolved = 637; In progress = 79, Monitoring = 35 ii) Corrective Maintenance: Total log =264. Closed = 238, In progress = 18, Cancel = 5 3. Preventive maintenance: i) PM activities for Year 2 completed 259/259 branches, 100% completed ii) PM activities for Year 3 completed 147/247/ branches,60% completed 4. CR and Integration: Total CR = 215, New= 2, In progress= 7, Done UAT = 24, Completed = 159, KIV = 7, Drop = 16 5. Peluasan & Perpindahan: Year 2 Completed Cameron Highland (9/10/2018) and Besut (7/12/2018); JIM has not decided on the next branch for peluasan/ perpindahan. Year 3, will start 18/8/2019. 6. Training for Year 2: User Training = 28/28, Technical training = 4/4, CPR workshop= 4/5, Professional certification = 7/9, Technical workshop conference/seminar = 0/2 7. Training for Year 3: User Training = 7/24, Technical training = 0/4, CPR workshop= 1/5, Professional certification = 0/7, Technical workshop conference/seminar = 0/2 8. System Audit services done by Cybersecurity. Report was submitted by Cybersecurity to BTMR. Project Team to request a copy of report from Cybersecurity. Transformation: 1. Overall completion: Plan = 100%; Actual = 90% 2. Progress: i. Passport & Selenggara – completed ii. Permit– completed iii. Kutipan Hasil – completed iv. Kawalan Stok: Target Pilot = 21/08/2019, New Target Date = 30/12/2019 v. Change Request = 16/12/2019-17/01/2019, SIT = 20/01/2020-22/01/2020, Pilot = 27/01/2020 vi. Kawalan A: Pilot = 08/08/2019, Roll- out = 13/01/2020 vii. Kawalan B: Total Transactions = 127, SIT Done = 15, SIT In Progress = 11, Pilot = 1, SIT-Ready (Test Done) = 44, In Progress = 18 - SIT final = 02-06/12/2019, UAT= 11-20/12/2019, Pilot = 23-31/12/2019 (Preparation), 02-10/01/2020 (Pilot@KLIA2), RollOut = 13/01/2020 – 31/01/2020 (16 lokasi) | 100% (November 2019 =100% ) (October 2019 = 100%) (September 2019 = 100%)
59 | JPJ | JPJ Mobile Handheld Enforcement | 931350 | 2017-10-01 | 2017-11-30 | 1. Supply 150 units Handheld Devices Samsung A7 2017 with accessories 2. Mobile Application Development 3. Installation and Configuration 4. Training - Centralised and On-site 5. Handheld devices distribution to JPJ State Offices 6. 1 year warranty and support | Azrul Saad | Suhaizar Osman/TBA | Azrul Saad, Mohd Hazly | Closed | No open or new issues | 931350 | 0 | 931350 | 811218.48 | 1. On going warranty support 2. Approval from JPJ to swap auto notification using Mobilefirst with development of PCID has been obtained. Vendor has been appointed and development is in progress. Target to complete by 15/2/2019. | 1. On going warranty support 2. PCID development completed. Target to UAT on 8/3/2019. | 1. PCID implementation completed. 2. Project closure in progress. | Project closure in progress. | Project closure in progress. | Project closure in progress. | Project closure in progress. |  |  | NA
60 | JTKSM | JTKSM WNP | 304856 | 2017-10-26 | 2020-11-15 | Membekal, menghantar, memasang, mengkonfigurasi, menguji, mentauliah dan mengelenggara perkakasan dan perisian ICT di JTKN | Redzuan Amiruddin B Abd Rahim | NA | Mohd Hazly | Closed | NA | 5446704 | -5141848 | 0 |  |  |  | NA | NA | [5 empty] | NA
61 | JTKWP | JTKN Hardware Supply | 45468 | 2017-10-13 | 2017-10-31 | Membekal, menghantar, memasang, mengkonfigurasi, menguji, mentauliah dan mengelenggara perkakasan dan perisian ICT di JTKWPKL | Redzuan Abd Jalil | NA | Mohd Hazly | Closed | NA | 212610 | 0 | 0
62 | DATASONIC | DATASONIC SMART SOLUTIONS: DTSB Onechip Integration with myIMMs | 491098 | 2017-09-01 | Oct 2017 | 1. Deployment services at JIM Bhg Passport 2. Deployment servcies at Attache London, New York, Melbourne, Singapore, Hong Kong and Jakarta 3. Training at JIM HQ for 20 pax, 2 days | Wan Suhaimi Wan Abd Hamid | Azlan Abd Hamid | Azmin, Ahmad Puzi | Project Closure | No open or new issues | 491098 | 0 | 0 | 0 | Work done. Payment will be knocked of with work done for Transformation | Work done. Payment will be knocked of with work done for Transformation | NA | Project closed once payment Datasonic owe HTP is knocked off with amount of work they execute for MyIMMS Transformation which is already done. Datasonic to invoice for work done.. | [5 empty] | NA
63 | BORDERPASS TRAVEL | BORDERPASS TRAVEL: Integration between myIMMs and eGate ASEAN Borderpass | 55000 | 2017-09-01 | 2017-11-01 | 1. Requirement & Design 2. Coding & testing 2. Testing (FT, UAT) 3. Deployment at pilot sites KLIA 1 & KLIA2 (onsite and offsite support) | Wan Suhaimi Wan Abd Hamid | Azlan Abd Hamid | Azmin, Ahmad Puzi | Project Closure | No open or new issues | 55000 | 0 | 0 | 0 | Project Closure | Project Closure | NA | Acceptance of temporary closure has already been obtained. PM to advise Finance of WBS closure by email. | [5 empty] | NA
64 | ITSB | INTIPADU TECHNOLOGY: Integration with myIMMs PLKS & Enforcement modules | 83184 | 2017-09-01 | Dec 2017 | 1. Requirement & Design 2. Coding & testing 2. Testing (FT, UAT) 3. Deployment | Wan Suhaimi Wan Abd Hamid | Md Zaidan Md Zain/ Azlan Abd Hamid | Ahmad Puzi, Azmin | Closed | No open or new issues | 23542.5 | 59641.5 | 0 | 0 | Payment for 30% work done is still pending. Finance to assist follow-up with Finance Intipadu. | Payment for 30% work done is still pending.To send official letter to pay by 26/2/2019 | Payment for 30% work done is still pending.To send official letter to pay by 26/2/2019 (In progress) | Conditional closure done | [5 empty] | NA
65 | MDEC | MALAYSIA DIGITAL ECONOMY CORPORATION (MDEC): Development of webservices for integration between eXpat system and myIMMs | 137588 | 2017-09-01 | 2017-11-01 | 1. Requirement & Design 2. Coding & testing 2. Testing (FT, UAT) 3. Deployment (pilot at Putrajaya) | Wan Suhaimi Wan Abd Hamid | Md Zaidan Md Zain/ Azlan Abd Hamid | Azmin, Sanuza | Closed | NA | 73394 | 64194 | 137588 | 0 |  |  | NA | NA | [5 empty] | NA
66 | JPJ | PUSPAKOM: IBM Websphere Subscription + Renewal | 150382.5 | 2017-09-01 | 2017-09-01 | Supply of IBM Wepshere subscription and renewal for 3 years | Azrul Saad | NA |  | Closed
67 | TALENTCORP | TALENTCORP: RP-T System Integration with myIMMs | 79500 | 2017-06-01 | Aug 2017 | 1. Requirement & Design 2. Coding & testing 2. Testing (FT, UAT) 3. Deployment | Wan Suhaimi Wan Abd Hamid | Md Zaidan Md Zain/ Azlan Abd Hamid | Azmin, Sanuza | Closed | NA | 491098 | -411598 | 79500 | 0 |  |  | NA | NA | [5 empty] | NA
68 | MDEC | MALAYSIA DIGITAL ECONOMY CORPORATION (MDEC): Development of webservices for integration between MTEP system and myIMMs | 73394 | 2017-10-14 | 2018-03-15 | 1. Requirement & Design 2. Coding & testing 2. Testing (FT, UAT) 3. Deployment | Wan Suhaimi Wan Abd Hamid | Md Zaidan Md Zain/ Azlan Abd Hamid | Ahmad Puzi, Azmin | Closed | No open or new issues | 73394 | 0 | 73394 | 0 | 1. All invoices submitted to MDEC on 23/12/2018 2. Pending payment due to payment schedule discrepancies 3. Amendment to contract done by AM & legal. MDEC currently verifying the amendment. | 2 invoices sent are waiting for payment. Last invoice HTP to resend invoice. | 1. Still pending payment for 2 invoices. Finance to follow-up. 2. Last invoice HTP to resend invoice. PM to advise Finance to issue Credit Note | Payment received | Payment received. In process of requesting 5% retention sum. | 5% retention sum has been released by MDEC. | 5% retention sum has been released by MDEC. | 5% retention sum has been released by MDEC. |  | NA
69 | MAHB | MALAYSIA AIRPORT HOLDINGS BERHAD (MAHB): SKI Automated QMS Integration with myIMMs | 625292 | 29 Dec 2017 | 23 Mar 2018 | 1. Supply, install, configure, test and commission of hardware and software w/ 3 years warranty 2. Integration services and application maintenance for 3 yrs | Wan Suhaimi Wan Abd Hamid | Md Zaidan Md Zain/ Azlan Abd Hamid | Ahmad Puzi, Azmin | Development | No open or new issues | 657223.5 | -31931.5 | 640285.76 | 422884.12 | 1. Rollout at KLIA completed on 26/11/18 2.Rollout at KLIA2 done from 3-17/12/2018. Monitoring is is progress. 3.Still pending payment on Integration on deployment and 3 months warranty. | Work done. Warranty until 23/3/2019. Remaining payment will be made 3 months after warranty period. | 1. Work done. Warranty already ended on 23/3/2019. AM to finalise contract with MAHB for balance payment to proceed. 2. PM to conduct project closure. | Maintenance on going | Maintenance on going | Maintenance on going | Maintenance on going | Maintenance on going | Maintenance on going | NA
70 | EMGS - STAR | EDUCATION MALAYSIA GLOBAL SERVICES (EMGS): Annual lMaintenance Support IntegrationBetween EMGS and MYIMMS | 160000 | 1 July 2017 | 30 June 2019 | Support and Maintenance for JIAS Integration System for 2 years | Wan Suhaimi Wan Abd Hamid | Md Zaidan Md Zain/ Azlan Abd Hamid | Ahmad Puzi, Azmin | Closed | No open or new issues | 164800 | -4800 | 164800 | 0 | Maintenance on going | Maintenance on going | Maintenance on going | Maintenance on going | Maintenance on going | Project Closure. To follow-up on outstanding payment. | Project Closure. To follow-up on outstanding payment. | Project Closed |  | NA
71 | MOH | SPP V2.6 Implementation Project - Hospital Taiping Perak (2018 - 2020) | 123275.4 | 2018-09-14 | 2020-09-13 | Membekal, Menghantar, Memasang, Menguji, Mengkonfigurasi, Mentauliah Guna dan Sewaan Peralatan ICT untk Pelaksanaan Aplikasi Sistem Pengurusan Pesakit (SPP) Versi 2.6 | Redzuan Amiruddin | Ahmad Zamin Mahadzir/ TBA | Halimah Din | Maintenance | No open or new issues | 61637.7 | 61637.7 | 61637.7 | 1481.96 | 1. Overall completion: Plan = 19%; Actual = 19% 2. Corrective Maintenance in progress. 3.CM Report for Sept - Nov 2018 completed on 30/11/2018. 4. CM Report for Dec 2018 - Feb 2019 target to completed on 28/2/2019 5. No problems reported. | 1. Overall completion: Plan = 22%; Actual = 22% 2. Corrective Maintenance in progress. 3. CM Report for Dec 2018 - Feb 2019 target to complete by 28/2/2019. 4. No problems reported. | 1. Overall completion: Plan = 26%; Actual = 26% 2. Corrective Maintenance in progress. 3. CM Report for Dec 2018 - Feb 2019 completed on 28/2/2019. CM Report for March - May target to complete by 31/5/2019. 4. No problems reported. | 1. Overall completion: Plan = 33%; Actual = 33% 2. Corrective Maintenance in progress. 3.CM Report for March - May target to complete by 31/5/2019. 4. No problems reported. | 1. Overall completion: Plan = 44%; Actual = 44% 2. Corrective Maintenance in progress. 3.CM Report for September – November target completed by 30/11/2019 | 1. Overall completion: Plan = 48%; Actual = 48% 2. Corrective Maintenance in progress. 3.CM Report for September – November target completed by 30/11/2019 | 1. Overall completion: Plan = 52%; Actual = 52% 2. Corrective Maintenance in progress. 3.CM Report for September – November target completed by 30/11/2019 4. Total one (1) Hardware Failure problems reported and closed. | 1. Overall completion: Plan = 56%; Actual = 56% 2. Corrective Maintenance in progress. 3.CM Report for December 2019 , January - February 2020 target completed by 28/2/2020 4. Total one (1) Hardware Failure problems reported and closed. | 1. Overall completion: Plan = 49%; Actual = 49% 2. Corrective Maintenance in progress. 3.CM Report for December 2019 , January - February 2020 target completed by 28/2/2020 4. Total one (2) Hardware Failure problems reported and closed. | NA
72 | MOH | SPP Application Maintenance-Hospital Taiping, Perak (2018 - 2020) | 170000 | 2018-09-18 | 2020-09-17 | 1. Melaksanakan perkhidmatan penyelenggaraan pencegahan bagi perisian SPP sebanyak empat (4) kali sepanjang tempoh kontrak. 2. Melaksanakan penyelenggaraan pembaikan terhadap perisian mengikut SLA yang telah ditetapkan. 3. Menyediakan dokumen prosedur pelan kontigensi bagi aplikasi SPP. 4. Menyediakan kakitangan sokongan secara offsite secara sepenuh masa sepanjang tempoh kontrak. 5. Menyediakan laporan dan dokumentasi berkaitan aplikasi. | Redzuan Amiruddin | Ahmad Zamin Mahadzir/ TBA | Halimah Din | Maintenance | No open or new issues | 90100.22 | 79899.78 | 90100.22 | 71445.6206 | 1. Overall completion: Plan = 19%; Actual = 19% 2. Corrective Maintenance in progress. 3.CM Report for Sept - Nov 2018 completed on 30/11/2018. 4. CM Report for Dec 2018 - Feb 2019 target to completed on 28/2/2019 5. A total of 9 application problems reported and closed. | 1. Overall completion: Plan = 22%; Actual = 22% 2. Corrective Maintenance in progress. 3. CM Report for Dec 2018 - Feb 2019 target to complete by 28/2/2019. 4. No problems reported. | 1. Overall completion: Plan = 26%; Actual = 26% 2. Corrective Maintenance in progress. 3. CM Report for Dec 2018 - Feb 2019 completed on 28/2/2019. CM Report for March - May target to complete by 31/5/2019. 4. Total four (4) Application problems reported and closed. | 1. Overall completion: Plan = 33%; Actual = 33% 2. Corrective Maintenance in progress. 3.CM Report for March - May target to complete by 31/5/2019. 4. Total six (6) Application problems reported and closed. | 1. Overall completion: Plan = 44%; Actual = 44% 2. Corrective Maintenance in progress. 3.CM Report for September – November target completed by 30/11/2019 4. Total two (2) Application problems reported and closed. | 1. Overall completion: Plan = 48%; Actual = 48% 2. Corrective Maintenance in progress. 3.CM Report for September – November target completed by 30/11/2019 4. Total two (2) Application problems reported and closed. | 1. Overall completion: Plan = 52%; Actual = 52% 2. Corrective Maintenance in progress. 3.CM Report for September – November target completed by 30/11/2019 4. Total two (2) Application problems reported and closed. | 1. Overall completion: Plan = 56%; Actual = 56% 2. Corrective Maintenance in progress. 3.CM Report for December 2019 , January - February 2020 target completed by 28/2/2020 4. Total three (3 Application problems reported and closed. | 1. Overall completion: Plan = 49%; Actual = 49% 2. Corrective Maintenance in progress. 3.CM Report for December 2019 , January - February 2020 target completed by 28/2/2020 | NA
73 | JPJ | Next Generation FireWall - NGFW (2018 - 2020) | 2810525.87 | 2018-10-01 | 2020-12-31 | 1. Supply, Install & Commissioning of 5 New Sangfor Firewall. 2. Renewal of Warranty and Hardware Maintenance for Sangfor Firewall, Efficient IP and PRTG. 3. License Renewal for Panda Adaptive Defence. 4. Maintenance Services & Technical Support 5. Helpdesk. | Rahiza Abdul Rahim | Suhaizar Osman/ TBA | Mohd Hazly | Implementation | No open or new issues | 1647031.88 | 1163493.99 | 1647031.88 | 2478244.12 | Status as at 24/1/2019 1. Overall completion = 6% 2. Corrective Maintenance = 33% 3. Preventive Maintenance target to start in February 2019 4. License Renewal & Hardware Warranty Renewal are partially delivered. (refer issue) 5. New implementation at 5 sites: i) UTC Selangor (20/2/19 - 21/2/19) ii) UTC Pasir Gudang (26/2/19-27/2/19) iii) UTC N. Sembilan (28/2/19-01/3/19) iv) UTC Arau (04/3/19-05/3/18) v) JPJ Caw. Cameron Highland (06/3/19-07/3/19) | 1. Overall completion = 19% actual from 24% plan 2. License Renewal for SANGFOR Firewall- 160: License Received 1/2/2019 3. License Renewal for EFFICIENT IP: Software Support Renewal Received 1/2/2019; Key activation completed 4. Maintenance of Hardware & Software Paessler PRTG: License Key Activation completed 5. Maintenance of Software for Panda Security Adaptive Defense: License Key Activation completed 6. Hardware and Software Maintenance for Next Generation Firewall SANGFOR at JPJ Offices without security hardware ICT NGFW: started on 4/2/2019 i) Completed - Pre-config ii) Completed - Installation for UTC Shah Alam 7. NGFW BBC Management Implementation: Started on 14/2/2019 8. Alien Vault Installation: Started on14/2/2019 9. Preventive Maintenance #1/2019 in progress February – April 2019 : i) Sangfor Firewall – 160 JPJ branches ii) EIP – 14 State Offices iii) PRTG - Cyberjaya | 1. Overall completion; Plan = 42%; Actual = 44% - Positive variance due to PM activities completed ahead of plan. 2. License Renewal & Hardware Support for Next Generation Firewall, EIP, PRTG & PANDA: Plan =50%; Actual = 50% 3.Sangfor Firewall Deployment at 5 new branches: Completed 100% i) Start Date : 4/2/2019 ii) Installation : 20/2/2019 -7/3/2019 iii) Documentation : 11/3/2019 - 20/3/2019 4.Technical Support: Plan = 22%; Actual = 22% 5. Helpdesk: Plan = 22%; Actual = 22% 6. Preventive Maintenance: Plan = 17%; Actual = 25% PM#1/2019 February – April 2019: Preventive Maintenance Activity completed . In the midst of compiling Service Report and Preventive Maintenance Report from Regional CSE. | 1. Overall completion; Plan = 47%; Actual = 57% 2. License Renewal & Hardware Support for Next Generation Firewall, EIP, PRTG & PANDA: Plan =50%; Actual = 100% 3.Sangfor Firewall Deployment at 5 new branches: Completed 100% 4.Technical Support: Plan = 30%; Actual = 30% 5. Helpdesk: Plan = 30%; Actual = 30% 6. Preventive Maintenance: Plan = 25%; Actual = 25% | 1. Overall completion; Plan = 48%; Actual = 58% 2. License Renewal & Hardware Support for Next Generation Firewall, EIP, PRTG & PANDA: Plan =50%; Actual = 100% 3.Sangfor Firewall Deployment at 5 new branches: Completed 100% 4.Technical Support: Plan = 33%; Actual = 33% 5. Helpdesk: Plan = 30%; Actual = 25% 6. Preventive Maintenance: Plan = 25%; Actual = 25% | No report submission for month of September 2019 | No report submission for month of October 2019 | 1. Overall completion; Plan = 61%; Actual = 71% 2. License Renewal & Hardware Support for Next Generation Firewall, EIP, PRTG & PANDA: Plan =50%; Actual = 100% 3.Sangfor Firewall Deployment at 5 new branches: Completed 100% 4.Technical Support: Plan = 52%; Actual = 52% 5. Helpdesk: Plan = 52%; Actual = 52% 6. Preventive Maintenance: Plan = 50%; Actual = 50% | 1. Overall completion; Plan = 62%; Actual = 72% 2. License Renewal & Hardware Support for Next Generation Firewall, EIP, PRTG & PANDA completed 100% on 20 February 2019 3.Sangfor Firewall Implementation at 5 new branches completed 100% on March 2019 4.Technical Support (15 month over 27 month): Plan = 56%; Actual = 56% 5. Helpdesk (15 month over 27 month): Plan = 56%; Actual = 56% 6. Preventive Maintenance: Plan = 56%; Actual = 56% | NA
74 | BESTINET | BESTINET: Integration Service Between Foreign Worker Centralized Mgmt System (FWCMS) and myIMMs System (2018 - 2020) | 2289600 | 2018-11-01 | 2021-10-31 | 1. Furnish Data from myIMMs to FWCMS 2. One Time and Incremental Data Update 3. Batch Jobs | Wan Suhaimi Wan Abd Hamid | Md Zaidan Md Zain/Azlan Abd Hamid | Ahmad Puzi, Azmin | Maintenance | 1. (PSC 1/2019) - Pending payment for GST for May 2015 & June 2015. Bestinet claimed payment has been paid. To get proof of payment. (PSC 4/2019) - Bestinet claimed they had paid with cheque. Finance to follow up with Bestinet on the outstanding GST payment. (PSC 9/2019) - Finance to discuss with Bestinet on payment plan for outstanding payment. (PSC 12/2019) - Bestinet did not make payment to HTP as agreed. Finance to follow-up (In progress) | 890400 | 1399200 | 318000 | 0 | 1. Application support on going 2. Received payment for Sept and Oct 2018. 3. Pending payment for GST for May 2015 & June 2015. Project Team to follow-up. 4.Contract documentation preparation is still in progress. Bestinet has provide feedback, Project Team to respond. Target to complete by 15/2/2019. | 1. Application support on going 2. Contract is in stamping process by Bestinet | 1. Application support on going. 2. As at 8/4/2019, contract to extend project duration has been signed. AM to issue SEO since new project value, in order to bill. Project Start date is backdated to 1/11/2018. | 1. Application support on going. | 1. Application support on going. | 1. Application support on going. | 1. Application support on going. | Application support on going. | Application support on going. | 100% (November 2019 =100%) (October 2019 = 100%) (September 2019 = 100%)
74 | JPJ | mySIKAP Maintenance Extension (Jan - June 2019) | 18724343.5 | 2019-01-01 | 2019-06-30 | 1. Perkhidmatan Penyelenggaraan Aplikasi Sistem mySIKAP 2. Perkhidmatan Penyelenggaraan Peralatan Dan Perisian Commercial-Of-The-Shelf (COTS) 3. Perkhidmatan Penyelenggaraan Keselamatan Rangkaian dan LAN Pusat Data 4. Perkhidmatan Penyelenggaraan Peralatan Dan Perisian Pusat Data 5. Perkhidmatan Ujian dan Fasiliti Pemulihan Bencana 6. Perkhidmatan Sokongan Cawangan 7. Perkhidmatan Penyelenggaraan Sistem Kiosk 8. On Request | Roslind Abd Rahman | Suhaizar Osman/TBA | Mohd Hazly | Maintenance | 1. (PSC 11/2019) TCSEN has not paid for the work done during mySIKAP main maintenance contract. Business Director has sent official letter with copy of TCSEN invoice to SUB Kewangan (MOT) in December 2019. If no feedback obtained, matter will be escalated to KSU of MOT. (Closed) | 17904486.5 | 819857 | 17904486.5 | 6396267.83 | 1. Pending LOA from JPJ, target to receive by 1/2/2019 2. Support services from 1/1/2019 -30/6/2019 or until new contract renewal awarded by JPJ 3. Purchase of license renewal and 3rd party hardware and software support will be pending on the issuance of LOA from JPJ 4. Budget for OR identified and allocated in mySIKAP extension contract is amount of RM1,585,625 | 1. Overall completion: Plan = 25%, Actual = 15%; Variance due to delay in purchase of software since LOA was received from JPJ on 31/1/2019 and procurement approval obtained on 13/2/2019. 2. License Renewal = 30% from 100% - Procurement for license renewal and 3rd party hardware and software support is in progress; Project Team is working with Finance for vendor upfront payment in order to get paper licence so that billing approval can be included during JTP Meeting on 2nd week March 2019. 3. Corrective Maintenance = 17% 4. Preventive Maintenance Plan = 0% i) COTS Maintenance Services: Planned to be done in Feb - Apr; Status = 0% ii) Network Security Hardware & Software Maintenance: Planned to be done in Feb - Apr; Status = 0% iii) LAN DC Hardware & Software Maintenance: Planned to be done in Feb - Apr; Status = 0% iv) Data Centre Maintenance Services: Planned to be done in Feb - Apr; Status = 0% v) Kiosk Maintenance Services: Planned to be done in Feb - Apr; Status = 0% 5. Data Centre Cleaning Service = 0%; plan to start 25/2/2019 - 15/3/2019 6. Disaster Recovery Facilities = 17% 7. Disaster Recovery Test = 25% - Discussion on DR Test have been done. Pre-test target to be done from 5-7/3/2019 and DR Test 1/2019 target from 9-12/4/2019 8. Branch Support & Kiosk Support = 17% 9. Carry forward tasks from 2018 i) Implementation of DynaTrace - End User & Core Application Monitoring (carry forward actvity from 2018 due to unavailable of JPJ staff) - UAT done and sign-off obtained on 25/2/2019. ii) Deliverable under LOU: Implementation of System VDI Training Room, JPJ Cyberjaya – done delivery of 30 units of Zero-Client (RM iii) On Request: 12 CR from 2018 (638,133) and e-Bidding (RM967,500) - Work In progress Resource Requirement: Software Developer = 2 Configuration Management Analyst = 1 Software Tester = 1 | 1. Overall completion: Plan = 41%, Actual = 37%; Variance due to delay in purchase of software due to pending payment to vendor to obtain paper licence. 2. License Renewal = 69% from 100%; 36 from 62 licences have been renewed. Finance to expedite payment to vendor get to get paper licence and hence, billing can be made. 3. Corrective Maintenance = 33% 4. Preventive Maintenance Plan = 33% 5. Data Centre Cleaning Service = 17%; plan to start 25/2/2019 - 15/3/2019 6. Disaster Recovery Facilities = 17% 7. Disaster Recovery Test = 38% - Discussion on DR Test have been done. Pre-test target to be done from 5-7/3/2019 and DR Test 1/2019 target from 9-12/4/2019 8. Branch Support & Kiosk Support = 17% 9. Carry forward tasks from 2018 - On Request: 12 CR from 2018 (RM641,560) and e-Bidding (RM967,500) - Work In progress 10. Resource Requirement: i) Technical/System Engineer = 1 ii) Software Developer = 2 iv) Software Tester = 1 v) Project Administration = 1 | 1. Overall completion: Plan = 82%, Actual = 82%; 2. License Renewal = 98% 3. Corrective Maintenance = 67% 4. Preventive Maintenance Plan = 100% 5. Data Centre Cleaning Service = 100%; 6. Disaster Recovery Facilities = 67% 7. Disaster Recovery Test = 75% 8. Branch Support & Kiosk Support = 67% 9. Resource Requirement: i) Configuration Management Analyst = 1 iv) Software Tester = 1 | Project Closure in progress. Project Team is in process of fulfilling project compliance documentation. | Project Closure in progress. Project Team is in process of fulfilling project compliance documentation. | Project Closure in progress. Project Team is in process of fulfilling project compliance documentation. | Project Closure in progress. Project Team is in process of fulfilling project compliance documentation. | Project Closure in progress. Project Team is in process of fulfilling project compliance documentation. | NA
75 | MOH | Critical Care Information System (CCIS) | 33179367.26 | 2019-02-01 | 2022-01-31 | 1. To supply, deliver, install, configure, testing and commission ICT Hardware and Software including network and integration 2. To supply, delivery, install, configure, testing and commission Critical Care Information System (CCIS) 3. To integrate CCIS with Sistem Pengurusan Pesakit (SPP) at 3 Hospitals i.e. Hospital Raja Permaisuri Bainun(HRPB), Hospital Raja Perempuan Zainab II (HRPZ II) and Hospital Tuanku Jaafar, Seremban. 4. To implement Critical Care Information System Project 5. To provide Service Support Operation, Helpdesk and Maintenance services during warranty period 6. To provide other related services with the implementation of CCIS i.e - Business Continuity Plan - Training and Transfer of Technology (ToT) - Change Management - Benefit Realization - Project Management Services | Mazwin Idris | Ahmad Zamin Mahadzir/Ibrahim Yusoff | Abu Yazid (Head PMO) Sanuza Zahari | Development | 1. (PSC 6/2019) Delay in approval of hardware brand change have caused delay to hardware delivery and sign-off. The following hardware:- i . Change of Printer brand from HP to Canon Change of printer brand was not approved by MOH. They insisted on using HP printer as per specified in the tender document. (in progress) ii . Change of UPS for Switch brand from Liebert to Vertiv due to discountinue sales iii. Change of UPS Servers (10Kval) (PSC DEC 2019 - to obtain latest design. Approved by MOH PSC on 14/10/2019 (closed) (PSC 7/2019) Change of printer brand still not approved. Project Team to have further comparison. (Open) Change for UPS for Switch and for servers have been approved in MOH PSC on 14/10/2019. (Closed) 2.(PSC 6/2019) Project Team need to identify non related CCIS medical devices/equipment in the tender list that will cause non 100% integration medical device status. MOH has reviewed but decision still pending at MOH. (In progress) 3.(PSC 6/2019) Project Team need to identify listed equipment that are able to be integrated but these devices are not able to service all allocated bed as per tender specification.i.e HTAR has 32 ICU beds but medical devices that are able to integrate only 5 monitor. (PSC 9/2019) Equipment has already been identified and will be confirmed during implementation. (Closed) 4. (PSC 7/2019) KCSB has installed a 63AMP electrical DB at the sites without the official agreement with HeiTech and KKM, whereas in the contract with KKM it has already agreed in the tender/contract for 250AMP. Since work was already done, HeiTech need to get the agreement from KKM. PM to propose to KKM on how to counter the reduction in the contract. (PSC 8/2019) KCSB has already explained the reason which indicated that Project has provided more than the tender requirement. PM will present the explanation to KKM accordingly. (PSC 9/2019) PM has presented the explanation to KKM. (Closed) | 0 | 33179367.26 | 0 | 5454902.093 | NA | NA | 1. Project Initiation Meeting (Internal) done on 14/2/2019 2. Project Kick Off Meeting with KKM done on 12/3/2019 3. Procurement done 13/3/2019 4. Site Visit Meeting with KKM 15/3/2019 5. PO to Netlee Software, Fortesysy Distribution and KCSB done on 20/3/2019 6. Site visit in progress; site visit to HTAR done on 25 – 26/3/2019 | 1. Overall completion: Plan = 10%, Actual = 5% - Gap due to delay in site assessment work. due to KKM fault. 2. Contract Management: i) Contract preparation with Government is in progress, target to sign by 31/5/2019 - Meeting with KKM on 17/5/2019 and received a new template. - Email to Legal on 17/5/2019 and received feedback on 27/5/2019 ii) Contract preparation with Netlee is in progress, target completion by 30/6/2019 3. Site Assessment: i) Site Assessment Report preparation in progress from 22/4/2019 – 31/5/2019. ii) Meeting with Bahagian Perkhidmatan Kejuruteraan on 27/5/2019 to discuss on infra work issues iii) Change Management: ‒ Change Management (Process Side) Workshop 1 for Non SPP Hospital: 2 – 4/5/2019 ‒ Change Management (Process Side) Workshop 2 Non SPP Hospital: 23 – 24/5/2019 4. Next activities: ‒ Infrastructure work at HTAR: target from11 – 28/6/2019 ‒ Change Management Workshop for SPP Hospital: target 27 – 28/6/2019 | 1. Overall completion: Plan = 21%, Actual = 16% 2. Contract Management: i) Contract preparation with Government is in progress, target to sign by 31/7/2019 - Revised contract sent to PUU on 28/05/19 - 1st review on the revised contract done on 14/06/19 - Sent Letter to KKM Perolehan on 22 August 2019, seeking the status of contract ii) Sub-contract with Netlee, still no progress from Netlee. iii) Sub-contract preparation with Kayangan Cahaya is in progress, target completion by 30/8/2019 3. Implementation Infrastucture: i) Phase 1 Infra Impementation – HTF, HRP, HPRB, HQEI is in progress, target completion by 8/8/2019 ii) Phase 2 Infra Impementation – HTJS, HTAA, HRPZII, HUS is in progress, target completion by 6/9/2019 iii) Pilot Phase – HTAR is in progress, target completion by 3/9/2019 4. Change Management: i) Change Management (Process Side) Workshop 2 Non SPP Hospital: Proposing stage to be conducted in September/ October 2019. ii) Change Management Awareness for HTAR, in planning 13/9/2019 5. Immediate Activity i) Delivery of Hardware and peripherals for HTAR, target to completed by 3/9/2019 ii) Configuration of servers in HTAR, target to completed by 6/9/2019 iii) Documentation and Sign off for Infra work, (HTF Kangar, HPP Penang, HRPB Ipoh, HQEII Kota Kinabalu, target to completed by 3/9/2019 6. Immediate Activity – HTAR – CM&Training Plan - Change Management Awareness Session, started on 13/9/2019 - End-user training for Nurses, started on 1-4/10/2019 - End-user training for Doctor, started on 1-4/10/2019 - Hand-on training for nurses /doctor, started on 17-19/9/2019 | 1. Overall completion: Plan = 26%, Actual = 17% 2. Contract Management: i) Contract preparation with Government is in progress, target to sign by 31/7/2019 - Revised contract sent to PUU on 28/05/19 - 1st review on the revised contract done on 14/06/19 - Sent Letter to KKM Perolehan on 22 August 2019, seeking the status of contract ii) Sub-contract with Netlee, still no progress from Netlee, target completion by 30/10/2019 iii) Sub-contract preparation with Kayangan Cahaya is in progress, target completion by 30/10/2019 3. Implementation Infrastucture: i) Phase 2 Infra Impementation - Hmelaka, target completion by 3/11/2019 - HAS, Johor, target completion by 25/11/2019 - PDSA, Putrajaya, target completion by 8/11/2019 4. Immediate Activity – HTAR - Fine tune Sangfor & VM, started on 30/7/2019 – 9/10/2019 - License Windows from Prestaring, started on 10/10/2019 - Activate license, started on 11/10/2019 - Install SQL & PICIS, started on 14/10/2019-18/10/2019 - Training, started on 21/10/2019-25/10/2019 - Unit Testing, started on 29/10/2019-31/10/2019 - UAT, started on 5/11/2019-7/11/2019 - Rework if required, started on 8/11/2019-11/11/2019 - Prepare for Go Live, started on 12/11/2019-15/11/2019 - Parallel Go Live, started on 18/11/2019 | 1. Overall completion: Plan = 26%, Actual = 17% i. Project Management: Plan= 32%, Completed = 18% ii. Site Evaluation & Solutions Planning, Completed = 100% iii. CCIS Software Implementation = 22%, Completed = 18% iv. Change Management: Plan = 45%, completed = 40% v. Business Continuity Plan: Plan 11%, Completed = 11% vi. Benefit Realization Plan (BRP): Plan 19%, Completed = 19% 2. Contract Management: i) Contract preparation with Government is in progress, target to sign by 30/8/2019 - Revised contract sent to PUU on 28/05/19 - 1st review on the revised contract done on 14/06/19 - Sent Letter to KKM Perolehan on 22 August 2019, seeking the status of contract - Meet Pn Nuha BPM seeking advice on Contact and queried from Pejabat Menteri - Raised in MOH PSC meeting on 14 October 2019 ii) Sub-contract with Netlee, still no progress from Netlee, target completion by 30/11/2019 iii) Sub-contract preparation with Kayangan Cahaya is in progress, target completion by 15/11/2019 3. Implementation Infrastucture: i) Phase 2 Infra Impementation - Hmelaka, target completion by 3/11/2019 - HAA, Johor, target completion by 25/11/2019 - PDSA, Putrajaya, target completion by 8/11/2019 4. Immediate Activity – HTAR - Fine tune Sangfor & VM, completed on 30/7/2019 – 9/10/2019 - License Windows from Prestaring, completed on 10/10/2019 - Activate license (Netvalut & Anti Virus)started on 11/10/2019 - Install SQL & PICIS, completed on 14/10/2019-18/10/2019 - Training, started on 31/10/2019-4/11/2019 - UAT, started on 5/11/2019-7/11/2019 - Rework if required, started on 8/11/2019-11/11/2019 - Prepare for Go Live, started on 12/11/2019-15/11/2019 - Parallel Go Live, started on 18/11/2019 | 1. Overall completion: Plan = 35%, Actual = 24% (as at 2/12/2019). Delay due to: a. 3% delay due to MOH Postponement of Kick Off CCIS Project, planned 4/2/2019 actual 12/3/2019 b. 10% delay on Change of Hardware Model (EOF) • MOH Approval on Reduction of BQ for Hospital Melaka • MOH Approval on Usage of Hard Material Cable vs GI • Partner (LKL) delay in delivery of Trolley • Partner (Prestaring) delay on license key and requires MOH approval c. 1% MOH Finalization of CCIS Flow Sheet Template from 11 hospitals 2. Activity Status: i. Project Management: Plan= 32%, Completed = 18% ii. Site Evaluation & Solutions Planning: Completed = 100% iii. Infra structure implementation: Plan = 73%, Actual = 38% iv. CCIS Software Implementation: Plan = 22%, Actual = 18% v. Interfacing Medical Equipment: Plan = 5%, Actual = 5% vi. Change Management: Plan = 45%, Actual = 40% vii. Business Continuity Plan: Plan = 11%, Actual = 11% viii. Benefit Realization Plan (BRP): Plan = 19%, Actual = 19% 3. Contract Management: i. Contract preparation with Government is still pending with KKM. ii. Sub-contract with Netlee, still no progress from Netlee, target completion by 30/12/2019 iii. Sub-contract preparation with KCSB is in progress, target completion by 15/12/2019 4. Infrastucture Implementation: i. Completed for all hospitals except for HSA Johor, HRPZII Kota Bharu and PDSA Putrajaya ii. Hospital Melaka, completed, target hardware delivery on 25/11/2019; confirmation on reduction of scope in PSC with MOH on 14/11/2019 due to power shortage iii. HSA, Johor, work in progress, delay due to confirmation on cabling material in MOH PSC on 14/11/2019; target hardware delivery 23/12/2019 – 29/12/2019. iv. HUS, Sarawak completed infrastructure work, hardware delivery target on 16/12/2019 – 20/12/2019. v. Other hospitals hardware delivery will be done in January and February 2020. 5. Project Deployment Activities in December 2019: i. HTAR, Klang – Pilot site; completed infrastructure work, hardware delivery and CCIS installation. Parallel run target from 29/11/2019 – 28/12/2019, not started yet. ii. H Melaka – completed infrastructure work and hardware delivery iii. HTJS, NS – completed infrastructure work, hardware delivery target on 9/12/2019 – 13/12/2019, preparation for Change Awareness program scheduled on 9/12/2019 is in progress. iv. HTAA, Kuantan – completed infrastructure work, hardware delivery target on 2/12/2019 – 6/12/2019, PICIS installation 2/12/2019 – 13/12/2019. Preparation for Change Awareness program scheduled on 13/12/2019 is in progress. | 1. Overall completion: Plan = 35%, Actual = 25% (as at 26/12/2019). Delay due to: a. 3% delay due to MOH Postponement of Kick Off CCIS Project, planned 4/2/2019 actual 12/3/2019 b. 10% delay on Change of Hardware Model (EOF) • MOH Approval on Reduction of BQ for Hospital Melaka • MOH Approval on Usage of Hard Material Cable vs GI • Partner (LKL) delay in delivery of Trolley • Partner (Prestaring) delay on license key and requires MOH approval c. 1% MOH Finalization of CCIS Flow Sheet Template from 11 hospitals 2. Activity Status: i. Project Management: Plan= 32%, Completed = 25% ii. Site Evaluation & Solutions Planning, Completed = 100% iii. Infrastructure Implementation: Plan = 100%, Completed = 60% iv. CCIS Software Implementation = 22%, Completed = 18% v. Interfacing Medical Equipment: Plan = 5%, Completed = 5% vi. UAT: Plan = 1%, Completed = 1% vii. Integration with SPP: Plan = 9%, Completed = 3% viii. Training & ToT: Plan = 10%, Completed = 5% ix. Change Management: Plan = 48%, completed = 40% 3. Contract Management: i. Contract preparation with Government is still pending with KKM. ii. Sub-contract with Netlee, still in progress, discussion with Netlee on 16/1/2020, target completion by 31/01/2020 iii. Sub-contract preparation with KCSB is in progress, target completion by 15/01/2020 4. Infrastucture Implementation: i. Completed for all hospitals except for HSA Johor, HRPZII Kota Bharu and PDSA Putrajaya ii. Hospital Melaka, completed, target hardware delivery on 25/11/2019; confirmation on reduction of scope in PSC with MOH on 14/11/2019 due to power shortage iii. HSA, Johor, work in progress, delay due to confirmation on cabling material in MOH PSC on 14/11/2019; target hardware delivery 23/12/2019 – 29/12/2019. iv. HUS, Sarawak completed infrastructure work, hardware delivery target on 16/12/2019 – 20/12/2019. v. Other hospitals hardware delivery will be done in January and February 2020. 5. Project Deployment Activities in December 2019: i. HTAR, Klang – Pilot site; completed infrastructure work, hardware delivery and CCIS installation. Parallel run target from 29/11/2019 – 28/12/2019. ii. H Melaka – completed infrastructure work and hardware delivery. Change Awareness program done on 28/11/2019. iii. HTJS, NS – completed infrastructure work, hardware delivery target on 9/12/2019 – 13/12/2019, Change Awareness program done on 9/12/2019. iv. HTAA, Kuantan – completed infrastructure work, hardware delivery target on 2/12/2019 – 6/12/2019, PICIS installation 2/12/2019 – 13/12/2019. Change Awareness program done on 13/12/2019. | 91% (October 2019 = 91%) (September 2019 = 91%)
76 | - Majlis Bandaraya Pulau Pinang (MBPP) - Majlis Perbandaran Seberang Prai (MPSP) | Penang Smart Parking (PSP) | 259686000 | 2019-05-01 | 2026-04-30 | 1. Application Development : - Smart Parking for Public - Parking Enforcement - Collection & Payment 2. System Integration to JPJ & internal systems 3. Training 4. Advertising & Promotion 5. Smart Parking Sensor & Infrastructure - 12,000 Parking Lots MBPP - 24,000 Parking Lots MPSP 6. Enforcement Handheld Device, 120 units : - Point Mobile PM80ID (Android) - Woosim i450 Thermal Printer 7. Cloud Hosting 8. Operation & Maintenance : - Application - Enforcement Handheld Device - Smart Parking Sensor & Infrastructure - Helpdesk | Selamat Ahmed | Suhaizar Osman/ Safarudin Ban | Lenny Ruby (Head PMO) Azrul Saad Yusairi | Development | 1. (PSC 8/2019) - Dependency on Gerbang Bestari for bugs fixing and resolution. Recruitment of three developers is in progress. Minimal support from mySIKAP due to project commitment. (PSC 8/2019) - Interview is in progress. Target to get the developer in early November 2019. (In progress) 2. (PSC 8/2019) - Lack of resources. Pending vacancy: AD Manager (1), SA (1), SE (1), Infra Lead (1), Developer (3). (PSC 11/2019) Vacancy filled from new recruitment (closed) 3. (PSC 8/2019) - Lack of versioning control/poor configuration management caused uncontrol deployment of source code to production. Team is strengthening the process, including executing final test before release, and preparing release note. Formulation of Configuration Management process is in progress. (In progress) 4. (PSC 11/2019 )- Sensor accuracy issue. Sensor not giving right occupancy ( vacant or not vacant) (In progress) | 85518.42 | 259600481.58 | 85518.42 | 1691379.98 |  |  |  | Status as at 30/5/2019 Phase 1: 1. Project Kick-off done on 2/5/2019 2. URS Workshop done on 2-3/5/2019 3. Prototype Presentation to be done on 31/5/2019 4. SRS Sign-off completed 10%, target to sign-off by 28/6/2019 5. Application development (public & enforcement) completed 70% 6. SDD Sign-off target by 19/7/2019 7. UAT Sign-off target by 26/7/2019 8.Training target to be done on 29/7/2019 9. Phase 1 Go-Live (Pilot) target on 1/8/2019 | Note: No PSC Slide for August 2019 was submitted. Update obtained was based on slide presentation for Mesyuarat Jawatankuasa Teknikal dated 3/9/2019 . Overall completion: 27% Phase 1: Status Project 1. Application development (User) completed 100% on 12/7/2019 2. Application development (Enforcement-Officer) completed 100% on 12/7/2019 3.Application development (enforcement -Mgmt) completed 90% 4. System Kompaun MBPP (Integration) completed 100% on 12/7/2019 5. Integration to System MPSP completed 50%, new target completion 18/10/2019 6. Application development (revenue) completed 90%, new target completion 27/9/2019. 7. RazerPay completed 100% on 31/7/2019 8. Unit Testing completed 100% on 26/7/2019 9. Integration Testing completed 100% on 26/7/2019 10. Acceptance Testing (UAT) completed100% on 2/8/2019 11. User Manual Development completed 100% on 7/8/2019 12. System Go-Live completed 100% on 19/8/2019 13. Infra TLK (997 Lot) completed 73% on 2/8/2019 14. Application Agent Coupon completed 90%, new target completion 27/9/2019. | Status Project Overall completion: 27% Phase 1: 1. Application development (User) completed 100% on 12/7/2019 2. Application development (Enforcement-Officer) completed 100% on 12/7/2019 3.Application development (enforcement -Mgmt) completed 100% on 18/8/2019 4. System Kompaun MBPP (Integration) completed 100% on 12/7/2019 5. Integration to System MPSP completed 50%, new target completion 18/10/2019 6. Application development (revenue) completed 100%, on18/8/2019. 7. RazerPay completed 100% on 31/7/2019 8. Unit Testing completed 100% on 26/7/2019 9. Integration Testing completed 100% on 26/7/2019 10. Acceptance Testing (UAT) completed100% on 2/8/2019 11. User Manual Development completed 100% on 7/8/2019 12. System Go-Live completed 100% on 19/8/2019 13. Infra TLK (997 Lot) completed100% on 24/9/2019 14. Application Agent Coupon completed 100%, on 12/9/2019. 13. Project Team is in process of bug fixing. | Overall completion: 38% Phase 1: 100% completed 1. Application development (User) completed 100% 2. System Go-Live completed 100% on 19/8/2019 3. Integration to System MPSP completed 80%, new target completion 15/11/2019 Phase 2: 17% completed as planned 1. Requirement Anaysis Study completed 70%, target to complete 11/11/2019 2. Infrastructure Implementation (Sensor & Getway – Planning, Delivery, Installation) completed 5% target completion 30/7/2020 3. Change Management & Promotion completed 20% 4. PSP Incident Log Total = 231, Closed = 213, Resolved = 6, Open = 12 | Overall completion: 40% Phase 1:100% completed 1. Application development (User) completed 100% 2. System Go-Live completed 100% on 19/8/2019 3.Development to System MPSP completed 100% on 15/11/2019 Phase 2:20% completed as planned 1. Requirement Anaysis Study completed 80%, started on 2/9/2019 – 8/12/2019 3. Infrastructure Implementation (Sensor & Getway – Planning, Delivery, Installation) completed 8% target completion 30/7/2020 4. Change Management & Promotion completed 30% - PSP Incident Log Total = 500, Closed = 445, Resolved = 17, Open = 38 - Total Incident Logs Recevied by Channel = Phone 270, Email = 188, Social Media = 42 - Total Incident Logs by Month = August = 50, Septmber =78, October = 146, November = 226 | Overall completion: 43% Phase 1:100% completed 1. Application development (User) completed 100% 2. System Go-Live completed 100% on 19/8/2019 3.Development to System MPSP completed 100% on 15/11/2019 Phase 2:25% completed 1. Requirement Anaysis Study completed 50%, started on 2/9/2019 – 29/2/2020 2. Infrastructure Implementation (Sensor & Getway – Planning, Delivery, Installation) completed 8% target completion 30/7/2020 3. Change Management & Promotion completed 35% - PSP Incident Log Total = 734 Closed = 639, Resolved = 43, Open = 52 - Total Incident Logs Recevied by Channel = Phone 415, Email = 265, Social Media = 54 - Total Incident Logs by Month = August = 50, Septmber =78, October = 146, November = 240, December = 220 | 67%
77 | MOH | SPP Maintenance HRPB, Ipoh (16 June 2019 - 15 June 2020) | 480755.16 | 2019-06-16 | 2020-06-15 | Perkhidmatan Penyelenggaraan dan Sokongan Operasi Bagi Perkakasan, Perisian, Aplikasi Dan Peralatan Rangkian untuk Sistem Pengurusan Pesakit (SPP) di Hospital Raja Permaisuri Bainun (HRPB), Ipoh | Redzuan Amiruddin | Ahmad Zamin Mahadzir/ TBA | Halimah Din | Maintenance | No open or new issues | 283848.22 | 196906.94 | 283848.22 | 2237.69 |  |  |  |  | 1. Overall completion: Plan = 44%; Actual = 44% 2. Corrective Maintenance in progress. 3.CM Report for July – August target completed by 31/08/2019 4. No problems reported. | 1. Overall completion: Plan = 28%; Actual = 28% 2. Corrective Maintenance in progress. 3. CM Report for September, October, November 2019 target completed by 30/11/2019 4. Problems reported September 2019 - Total Received = 39 - Open = 0 - Closed = 39 | 1. Overall completion: Plan = 28%; Actual = 28% 2. Corrective Maintenance in progress. 3. CM Report for September, October, November 2019 target completed by 30/11/2019 4. Problems reported September 2019 - Total Received = 27 - Open = 0 - Closed = 27 | 1. Overall completion: Plan = 33%; Actual = 33% 2. Corrective Maintenance in progress. 3. CM Report for December 2019, January & February 2020 target completed by 29/02/2020 4. Problems reported November 2019 - Total Received = 41 - Open = 0 - Closed = 41 | 1. Overall completion: Plan = 27%; Actual = 27% 2. Corrective Maintenance in progress. 3. CM Report for December 2019, January & February 2020 target completed by 29/02/2020 4. Problems reported December 2019 - Total Received = 3 - Open = 0 - Closed = 3 | NA
78 | JPJ | mySIKAP Maintenance Extension (July-Oct 2019) | 7016592 | 2019-07-01 | 2019-10-30 | Pelanjutan Tempoh Bagi Tender Perkhidmatan Penyelenggaran Sistem mySIKAP, Jabatan Pengangkutan Jalan Bagi Tempoh 1 Julai 2019 Sehingga 30 Oktober 2019 Secara Month-To-Month Basis | Roslind Abd Rahman | Suhaizar Osman/TBA | Mohd Hazly | Maintenance | No open or new issues | 4833869.24 | 2182722.76 | 4833869.24 | 1341225.04 | [5 empty] | NA | 1. License Renewal = 100% 2. Corrective Maintenance = 100% 3. Disaster Recovery Facilities = 100% 4. Branch Support & Kiosk Support = 100% | NA | NA | NA
79 | JPJ | mySIKAP Maintenance Extension (Nov-Dis 2019) | 3508296.13 | 2019-11-01 | 2019-12-30 | Pelanjutan Tempoh Bagi Tender Perkhidmatan Penyelenggaran Sistem mySIKAP, Jabatan Pengangkutan Jalan Bagi Tempoh 1 November 2019 Sehingga 30 Disember 2019 Secara Month-To-Month Basis | Roslind Abd Rahman | Suhaizar Osman/TBA | Mohd Hazly | Maintenance | No open or new issues | 1764232.2 | 1744063.93 | 1764232.2 | 20469 |  | 1. Pembaharuan Perkhidmatan = 100% 2. Corrective Maintenance = 41.7% 3. Disaster Recovery Facilities = 41.7% | NA |  |  |  | NA | Overall status = 95.7% 1. License Renewal = 100% 2. Corrective Maintenance = 90% 3. Disaster Recovery Facilities = 90% 4. Branch Support & Kiosk Support = 90% | Overall status = 94% 1. Pembaharuan Perkhidmatan = 100% 2. Corrective Maintenance = 92% 3. Disaster Recovery Facilities = 92% 4. Branch Support & Kiosk Support = 92% | NA
80 | MOH | Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu 01 Nov 2019 - 28 Feb 2020 (4 mths) | 496000 | 2019-11-01 | 2020-02-28 | Perolehan Peralatan, Aksesori Rangkaian, Perkhidmatan Integrasi Modaliti Tambahan Dan Deployment Laporan SS RA1019 bagi Projeck RISPACS di Hospital Raja Perempuan Zainab II Kota Bharu | Suradi Abdul Rahman | Ahmad Zamin Mahadzir | Hamid Baharudin | Implementation | No open or new issues | 0 | 496000 | 0 | 134 | [7 empty] | NA | - Hardware procurement and deployment is in progress. Target completion by 29/2/2020 - Infrastructure and LAN cabling work has completed on 25/12/2019 | NA
81 | MOH | Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu 01 Oct 2019 - 31 Dec 2019 (3 mths) | 226639 | 2019-10-01 | 2019-12-31 | Perkhidmatan Penyelenggaran Dan Sokongan Operasi Bagi Perkakasan, Perisian, Aplikasi Dan Rangkaian Untuk Sistem Pengurusan Pesakit (SPP) di Hospital Raja Perempuan Zainab II Kota Bharu Bagi Tempoh 3 Bulan | Suradi Abdul Rahman | Ahmad Zamin Mahadzir | Hamid Baharudin | Maintenance | No open or new issues | 187492.8 | 39146.2 | 187492.8 | 55004.0232 | [7 empty] | NA | - Project Team in process of compiling report for December 2019. - Project closing will be on 16/1/2020. | NA
Note on Q8: Norhasina Hamzah: April data = RM1,170,411.81 May = RM1,132,584.45 Reduction of cost = RM37,827 Checking with Finance if there the data is correct (Jasina)
Note on E21: Norhasina Hamzah: Ceiling value: RM2,400,000 (concession transaction base)
Note on E43: Norhasina Hamzah: RM6,500,000 without GST RM6,6890,000 with GST
Note on Q43: Norhasina Hamzah: July figure RM3,897,986.77 was mistakenly included accrued cost RM252,280 Cost without accrued cost = RM3,645,706.77
Note on Q49: Norhasina Hamzah: April data = RM1,170,411.81 May = RM1,132,584.45 Reduction of cost = RM37,827 Checking with Finance if there the data is correct (Jasina)
Note on Q55: Norhasina Hamzah: Correction to cost as t31/12/2019 previously RM55,977,486.00
Note on F57: Based on project initiation date.
Note on Q76: Aida Rashid: The cost decrease from last mth due to some arrangement on the cost as at Sept.
Note on N80: Norhasina Hamzah: Based on collection made.
Note on Q80: Norhasina Hamzah: Cost for Oct 2019 is not accurate because there were duplicate entries. Rectification done for figure of Nov 2019.

## Project Status 2020
PROJECT STATUS AS OF 30 SEPT 2020
No. | Customer | Project Name | Project Value (RM) | Project Start Date | Project End Date | Project Scope | Project Manager | Business Director/ Project Director | PMO Rep | Current Phase | New/Open Issue | Total Billed (RM) | Balance to Bill (RM) | Payment Received (RM) | Cost (RM) (as at 31/08/2020) | Status (as at 31/12/2019) | Status (as at 31/01/2020) | Status (as at 29/02/2020) | Status (as at 31/03/2020) | Status (as at 30/04/2020) | Status (as at 31/05/2020) | Status (as at 30/06/2020) | Status (as 31/07/2020) | Status (as 31/08/2020) | Status (as 30/09/2020) | Process Compliance September 2020
Transport
1 | JPJ | Next Generation FireWall - NGFW (2018 - 2020) | 2979157.4222 | 2018-10-01 | 2020-12-31 | 1. Supply, Install & Commissioning of 5 New Sangfor Firewall. 2. Renewal of Warranty and Hardware Maintenance for Sangfor Firewall, Efficient IP and PRTG. 3. License Renewal for Panda Adaptive Defence. 4. Maintenance Services & Technical Support 5. Helpdesk. | Siti Noor atiqah Osman | Suhaizar Osman/ TBA | Mohd Hazly | Implementation | No open or new issues | 2888682.11 | 90475.3122 | 2888682.11 | 2480698.85 | 1. Overall completion; Plan = 62%; Actual = 72% 2. License Renewal & Hardware Support for Next Generation Firewall, EIP, PRTG & PANDA completed 100% on 20 February 2019 3.Sangfor Firewall Implementation at 5 new branches completed 100% on March 2019 4.Technical Support (15 month over 27 month): Plan = 56%; Actual = 56% 5. Helpdesk (15 month over 27 month): Plan = 56%; Actual = 56% 6. Preventive Maintenance: Plan = 56%; Actual = 56% | Next Generation Firewall 1. Overall completion; Plan = 75%; Actual = 75% 2. License Renewal & Hardware Support for Next Generation Firewall, EIP, PRTG & PANDA completed 100% on 20 February 2019 3. Sangfor Firewall Implementation at 5 new branches completed 100% on March 2019 4.Technical Support (15 month over 27 month): Plan = 59%; Actual = 59% 5. Helpdesk (15 month over 27 month): Plan = 59%; Actual = 59% 6. Preventive Maintenance: Plan = 58%; Actual = 58% | No report submission for month of February | Overall completion; Plan = 82%; Actual = 82% 1. License Renewal & Hardware Support for Next Generation Firewall, EIP, PRTG & PANDA completed 100% in 20 February 2019 2. Sangfor Firewall Implementation at 5 new branches completed 100% in March 2019 3.Technical Support (15 month over 27 month): Plan = 67%; Actual = 67% 4. Helpdesk (15 month over 27 month): Plan = 67%; Actual = 67% 5. Preventive Maintenance: Plan = 75%; Actual =75% | Overall completion; Plan = 85%; Actual = 85% 1. License Renewal & Hardware Support for Next Generation Firewall, EIP, PRTG & PANDA completed 100% on 20 February 2019 2. Sangfor Firewall Implementation at 5 new branches completed 100% on March 2019 3.Technical Support (15 month over 27 month): Plan = 70%; Actual = 70% 4. Helpdesk (15 month over 27 month): Plan = 70%; Actual = 70% 5. Preventive Maintenance (PM Activity #1/2020 – Complete): Plan = 75%; Actual = 75% | Overall completion; Plan = 85%; Actual = 85% 1. License Renewal & Hardware Support for Next Generation Firewall, EIP, PRTG & PANDA Completed 100% on 20 February 2019. 2. Sangfor Firewall Implementation at 5 new branches completed 100% on March 2019 3. Technical Support (16 months over 27 month): Plan = 74%; Actual = 74% 4. Helpdesk (16 months over 27 month): Plan = 74%;Actual = 74% 5. Preventive Maintenance (PM Activity #1/2020 – Complete): Plan = 75%; Actual = 75% 6. Problem Log April 2020 Total Received = 5, Closed + Resolved = 5 | NA | NA | NA | NA | NA
2 | JPJ | mySIKAP Maintenance Extension (July-Oct 2019) | 7016592 | 2019-07-01 | 2019-10-30 | Pelanjutan Tempoh Bagi Tender Perkhidmatan Penyelenggaran Sistem mySIKAP, Jabatan Pengangkutan Jalan Bagi Tempoh 1 Julai 2019 Sehingga 30 Oktober 2019 Secara Month-To-Month Basis | Roslind Abd Rahman | Suhaizar Osman/TBA | Mohd Hazly | Maintenance | No open or new issues | 6107574.63 | 909017.37 | 6107574.63 | 1036932.4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | JPJ | mySIKAP Maintenance Extension (Nov-Dis 2019) | 3508296.13 | 2019-11-01 | 2019-12-30 | Pelanjutan Tempoh Bagi Tender Perkhidmatan Penyelenggaran Sistem mySIKAP, Jabatan Pengangkutan Jalan Bagi Tempoh 1 Januari 2019 Sehingga 30 Disember 2019 Secara Month-To-Month Basis | Roslind Abd Rahman | Suhaizar Osman/TBA | Mohd Hazly | Maintenance | No open or new issues | 3508296.13 | 0 | 3508296.13 | 1370880.91 | Overall status = 94% 1. Pembaharuan Perkhidmatan = 100% 2. Corrective Maintenance = 92% 3. Disaster Recovery Facilities = 92% 4. Branch Support & Kiosk Support = 92% | Overall status = 100% 1. Pembaharuan Perkhidmatan = 100% 2. Corrective Maintenance = 100% 3. Disaster Recovery Facilities = 100% 4. Branch Support & Kiosk Support = 100% | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | JPJ | mySIKAP Maintenance Extension (Jan-Jun 2020) | 10524888.4 |  | 2020-06-30 | Pelanjutan Tempoh Bagi Tender Perkhidmatan Penyelenggaran Sistem mySIKAP, Jabatan Pengangkutan Jalan Bagi Tempoh 1 Januari 2020 Sehingga 30 Jun 2020 Secara Month-To-Month Basis | Roslind Abd Rahman | Mohd Nizam Atim | Mohd Hazly | Maintenance | 1. (PSC 3/2020) - Due to MCO, support staff movement is limited including response to a log call. This could impact SLA (OPEN). (PSC 4/2020)- Official letter for the support staff to travel to JPJ offices and branches Discuss with JPJ reason of late response ie due to MCO (OPEN) 2. (PSC 3/2020) - Due to MCO, mySIKAP developers travel to BTD IT building at Cyberjaya are limited. Access to mySIKAP system can only be done inside BTD IT building. Current CR development is put on hold since mySIKAP developers can’t access mySIKAP ystem outside BTD IT building (OPEN). (PSC 4/2020) - Inform JPJ BTD that CR development will be on hold due to MCO Get approval from BTD IT for VPN access so that mySIKAP developers can develop the CR from home (open) | 7727962.23 | 2796926.17 | 7727962.23 | 0 |  | NA | Overall status = 18% 1. License Renewal and Third Party Support = 0% 2. Corrective Maintenance = 20% 3. Disaster Recovery Facilities = 33% 4. Branch Support & Kiosk Support = 20% | Overall status = 40% 1. License Renewal and Third Party Support =50% 2. Corrective Maintenance = 40% 3. Disaster Recovery Facilities = 50% 4. Branch Support & Kiosk Support = 40% | Overall status = 45% 1. License Renewal and Third Party Support = 50% 2. Corrective Maintenance = 40% 3. Disaster Recovery Facilities = 50% 4. Branch Support & Kiosk Support = 40% | Overall status = 75% 1. License Renewal and Support = 100% 2. Corrective Maintenance = 60% 3. Disaster Recovery Facilities = 67% 4. Branch Support & Kiosk Support = 60% | NA | NA | NA | NA | NA
5 | PSP | Penang Smart Parking (PSP) | 259686000 | 2019-05-01 | 2026-04-30 | 1. Application Development : - Smart Parking for Public - Parking Enforcement - Collection & Payment 2. System Integration to JPJ & internal systems 3. Training 4. Advertising & Promotion 5. Smart Parking Sensor & Infrastructure - 12,000 Parking Lots MBPP - 24,000 Parking Lots MPSP 6. Enforcement Handheld Device, 120 units : - Point Mobile PM80ID (Android) - Woosim i450 Thermal Printer 7. Cloud Hosting 8. Operation & Maintenance : - Application - Enforcement Handheld Device - Smart Parking Sensor & Infrastructure - Helpdesk | Selamat Ahmed | Ibrahim Yusoff | Lenny Ruby (Head PMO) Azrul Saad Yusairi | Development | 1. (PSC 8/2019) - Lack of versioning control/poor configuration management aused uncontrol deployment of source code to production. Team is strengthening the process, including executing final test before release, and preparing release note. Formulation of Configuration Management process is in progress. (open) 2. (PSC 1/2020) PSP Call Centre, public raised their unsatisfactorily due to Helpdesk contact number which is not reside in penang area. Enforcement nad Counter Officer suggest HTP to have support Centre in Penang. PSC 4/2020)- Highlighted to CC and they will further discuss with management on the possibility to use toll free number or mobile number (open) (PSP 6/2020)- CCC had tested the new line (mobile number) . Setup and configuration work by Celcom is in progress and target to complete by 3/7/2020 (PWC1/2020) CCC had tested the new line (mobile number). Setup and configuration work by Celcom cannot be done due to payment issue (HTP to Celcom). PSC 2/2020 16/10/2020 2 alternatives available ( toll free RM100K/ year and mobile (RM8K/year). But for mobile need to increase booster and overcome gsm infra issue (open) 3. ( PSC 6/2020) - Pending order or Batch 2 & 3 (15,000 and 8,000) sensors. The delay may effect overall sensor delivery and installation time line.Order must be made before 6/7/2020 to avoid delay. Issues has been highlighted to management in a meeting on 26/6/2020. Issues will be circulated and presented to CEO by 3/7/2020 for decision. (PWC 1/2020) Issue has been highlighted to management in a meeting conducted on 26/6/2020. Issue has been presented to CEO on 23/7/2020 PSC 1/2020 16/10/2020 Issue has been highlighted to management and councils accordingly. For MBSP, approval on sensor type must be obtained before end of October as the earliest delivery period is by May 2021 (open) 4. (PWC1/2020) - Installation of sensor at MBSP is put on hold due public safety issues. MBSP Council members requested HeiTech to follow the tender spec and original proposal to use a flush mounted sensor 1. Preparation for Alternative Solution in progress 2. Already request for additional time PSC 1/2020 16/10/2020 HeiTech decision is to proceed with surface mounted sensor only. There will be no installation at any road/street that is identified as not suitable . MBSP to come out with no of parking lot affected. Awaiting feedback from MBSP. (open) 5. PSC 1/2020 16/10/2020 Public complaint on PSP Apps crash (version 2.0.1) mainly on Samsung Android 5,6 and 7 users. Potential root cause are: Low RAM Huawei Library Action 1: CE is currently providing onsite support at both MBPP and MBSP. Action 2: Team to propose the alternative solution to Council for approval on 16/10/2020. Manually re installed those problematic device with V1.7.8 or to be named as Lite Version(for parking payment only) (open) 6. PSC 1/2020 16/10/2020 PSP Public Apps (V2.0.1) is not accessible on 1-3 September 2020 due to apps and DB server issue. All action items has been performed to recover the system problem. Continuous monitoring of system and servers capacity and performance is currently done in daily basis (open) 7. PSC 1/2020 16/10/2020 CE team lack of man-power due to concurrent activities to support :- Sensor deployment activities, TLK maintenance activities, PSP Public queries (on-site), PSP Enforcement apps and hardware support. To highlight and obtain decision from management for additional two CE have submitted requisition for 2 IA but was told CD would release 2 IA. (in progress) 8. PSC 1/2020 16/10/2020 Poor quality of deliverables from Change Management vendor may affect customer satisfaction. This is a risk that has become an issue (open) 9. PSC 1/2020 16/10/2020 Late delivery of sensor from manufacturer due to COVID19 Pandemic may affect overall timeline which was targeted by End-July2020 contractually This is orinally a eisl that has become an issue. (open) | 4760314.44 | 254925685.56 | 4760314.44 | 8606261.25 | Overall completion: 43% Phase 1:100% completed 1. Application development (User) completed 100% 2. System Go-Live completed 100% on 19/8/2019 3.Development to System MPSP completed 100% on 15/11/2019 Phase 2:25% completed 1. Requirement Anaysis Study completed 50%, started on 2/9/2019 – 29/2/2020 2. Infrastructure Implementation (Sensor & Getway – Planning, Delivery, Installation) completed 8% target completion 30/7/2020 3. Change Management & Promotion completed 35% - PSP Incident Log Total = 734 Closed = 639, Resolved = 43, Open = 52 - Total Incident Logs Recevied by Channel = Phone 415, Email = 265, Social Media = 54 - Total Incident Logs by Month = August = 50, Septmber =78, October = 146, November = 240, December = 220 | Overall completion: 45% Phase 1:100% completed 1. Application development (User) completed 100% 2. System Go-Live completed 100% on 19/8/2019 3.Development to System MPSP completed 100% on 15/11/2019 Phase 2:35% completed 1. Requirement Anaysis Study; completed 49%, started on 2/9/2019 – 29/2/2020 2. Development & Design (Public Apps, Enforcement & Back Office); completed 37%, started on 1/11/2019 – 30/06/2020 3. Testing, Training & Commissioning; completed 8%, started on 1/2/2020 – 31/07/2020 4. Infrastructure Implementation (Sensor & Getway – Planning, Delivery, Installation); completed 10%, started 01/09/2020 - 31/7/2020 5. Change Management & Promotion; completed 46%, started on 19/08/2019 – 31/08/2020 - PSP Incident Log Total = 1707, Closed = 1475, Resolved = 50, Open = 182 - Total Incident Logs Recevied by Channel = Phone 1039 Email = 575, Social Media = 93 - Total Incident Logs by Month = August = 50, Septmber =78, October = 146, November = 240, December = 519, January = 674 | Overall completion: 50% Phase 1:100% completed 1. Application development (User) completed 100% 2. System Go-Live completed 100% on 19/8/2019 3.Development to System MPSP completed 100% on 15/11/2019 Phase 2:40% completed 1. Requirement Anaysis Study; completed 80%, started on 2/9/2019 – 29/2/2020 2. Development & Design (Public Apps, Enforcement & Back Office); completed 45%, started on 1/11/2019 – 30/06/2020 3. Testing, Training & Commissioning; completed 15%, started on 26/12/2019 – 31/07/2020 4. Infrastructure Implementation (Sensor & Getway – Planning, Delivery, Installation); completed 20%, started 01/09/2020 - 31/7/2020 5. Change Management & Promotion; completed 55%, started on 19/08/2019 – 31/08/2020 - PSP Incident Log Total = 2575, Closed = 2260, Open = 315 - Total Incident Logs Recevied by Channel = Phone 1655,Email = 782, Social Media = 138 - Total Incident Logs by Month = August = 50, Septmber =78, October = 146, November = 240, December = 519, January = 819, February = 723 | Overall completion: 60% Phase 1:100% completed 1. Application development (User) completed 100% 2. System Go-Live completed 100% on 19/8/2019 3.Development to System MPSP completed 100% on 15/11/2019 Phase 2:48% completed 1. Requirement Analysis Study; completed 85%, started on 2/9/2019 – 30/4/2020 2. Development & Design (Public Apps, Enforcement & Back Office); completed 53%, started on 1/11/2019 – 30/06/2020 3. Testing, Training & Commissioning; completed 20%, started on 26/12/2019 – 31/07/2020 4. Infrastructure Implementation (Sensor & Getway – Planning, Delivery, Installation); completed 25%, started 01/09/2020 - 31/7/2020 5. Change Management & Promotion; completed 60%, started on 19/08/2019 – 31/08/2020 - PSP Incident Log Total = 3404, Closed = 3243, Open = 161 - Total Incident Logs Recevied by Channel = Phone 2255, Email = 1011, Social Media = 167 - Total Incident Logs by Month = August = 50, September =78, October = 146, November = 240, December = 519, January = 819, February = 723, March = 604 | Overall completion: 62% Phase 1:100% completed 1. Application development (User) completed 100% 2. System Go-Live completed 100% on 19/8/2019 3.Development to System MPSP completed 100% on 15/11/2019 Phase 2:53% completed 1. Requirement Anaysis Study; completed 90%, started on 2/9/2019 – 30/4/2020 2. Development & Design (Public Apps, Enforcement & Back Office); completed 64%, started on 1/11/2019 – 30/06/2020 3. Testing, Training & Commissioning; completed 60%, started on 26/12/2019 – 31/07/2020 4. Infrastructure Implementation (Sensor & Getway – Planning, Delivery, Installation); completed 25%, started 01/09/2020 - 31/7/2020 5. Change Management & Promotion; completed 60%, started on 19/08/2019 – 31/08/2020 Phase 2 Application Target Deployment 1. Fiz-Manual; completed 100% by 31/01/2020 2. Hasil – Penambahbaikan Laporan (1); completed 100% by 31/01/2020 3. Sewa Petak Khas;(MBSP) completed 100% by 22/03/2020 & MBPP, completed 100% 29/02/2020. 4. Topup di Web; completed 100% by 10/02/2020 5. Integrasi MBSP; completed 100% by 15/02/2020(PSP) 6. Hasil-Penambahbaikan Laporan 2; completed 100% by 26/03/2020 7. Pendakwaan TLK (1); completed 100% by 26/03/2020 8. FIZ-File Upload; completed 100% by 31/03/2020 9. Warden Trafik; completed 90%, target testing/pilot by 17/04/2020 10. Pendakwaan TLK(2); completed 100% by 23/04/2020 11. Integrasi MBSP; completed 90%, target testing/pilot by 23/04/2020(No PSP) 12. Pas Khas; completed 100% by 30/04/2020 13. Integrasi MBPP eBayar; completed 90%, target testing/pilot by 30/04/2020 14. Dashboard Prngurusan & Penguatkuasa; completed 80%, target testing/pilot by 30/04/2020 15. UI/UX Enhancement; completed 80%, target testing/pilot by 15/05/2020 - PSP Incident Log Total (April 2020) = 3476, Closed = 3045, Resolved = 333, Open = 98 - Total Incident Logs Recevied by Channel (19 August – 30 April 2020 = Phone 2261, Email = 1041, Social Media = 174 - Total Incident Logs by Month = August 2019 = 50, September 2019 =78, October 2019 = 146, November 2019 = 240, December 2019 = 519, January 2020 = 819, February 2020 = 948, March 2020 = 604, April 2020 = 71 | Overall completion: 64% Phase 1:100% completed 1. Application development (User) completed 100% 2. System Go-Live completed 100% on 19/8/2019 3. Development to System MPSP completed 100% on 15/11/2019 Phase 2:57% completed 1. Requirement Anaysis Study; completed 95%, started on 2/9/2019 – 30/4/2020. 2. Development & Design (Public Apps, Enforcement & Back Office); completed 71%, started on 1/11/2019 – 30/06/2020 3. Testing, Training & Commissioning; completed 65%, started on 26/12/2019 – 31/07/2020 4. Infrastructure Implementation (Sensor & Getway – Planning, Delivery, Installation); completed 25%, started 01/09/2020 - 31/7/2020 5. Change Management & Promotion; completed 60%, started on 19/08/2019 – 31/07/2020 Phase 2 Application Target Deployment 1. Fiz-Manual; completed 100% by 31/01/2020 2. Hasil – Penambahbaikan Laporan (1); completed 100% by 31/01/2020 3. Sewa Petak Khas;(MBSP) completed 100% by 22/03/2020 & MBPP, completed 100% 29/02/2020. 4. Topup di Web; completed 100% by 10/02/2020 5. Integrasi MBSP; completed 100% by 15/02/2020(PSP) 6. Hasil-Penambahbaikan Laporan 2; completed 100% by 26/03/2020 7. Pendakwaan TLK (1); completed 100% by 26/03/2020 8. FIZ-File Upload; completed 100% by 31/03/2020 9. Pendakwaan TLK(2); completed 100% by 23/04/2020 10. Pas Khas; completed 100% by 30/04/2020 11. Integrasi MBPP eBayar; completed 100% by 30/04/2020 12. Dashboard Prngurusan & Penguatkuasa; completed 100% by 30/04/2020 13. UI/UX Enhancement; completed 87%, target testing/pilot by 15/05/2020 14. Integrasi MBSP; completed 90%, target testing/pilot by 29/05/2020(No PSP) 15. Warden Trafik; completed 90%, target testing/pilot by 10/06/2020 16. Clamping/Towing; completed 90%, target testing/pilot by 16/06/2020 17. Hasil – Laporan Tambahan; completed 90%, target testing/pilot by 16/06/2020 18. JPP; completed 90%, target testing/pilot by 16/06/2020 19. Perlesenan; completed 90%, target testing/pilot by 16/06/2020 20. Kesihatan; completed 90%, target testing/pilot by 16/06/2020 21. Veterinar; completed 90%, target testing/pilot by 16/06/2020 22. Jabatan Bangunan; completed 10%, target testing/pilot by 16/07/2020 23. Jabatan Perancangan; completed 10%, target testing/pilot by 16/07/2020 24. Dashboard Infrastruktur; completed 10%, target testing/pilot by 31/07/2020 25. ANPR; completed 80%, target testing/pilot by 31/07/2020 26. Integerasi JPJ; completed 10%, target testing/pilot by 31/07/2020 - PSP Incident Log Total (May 2020) = 3644, Closed = 3167, Resolved = 418, Open = 59 - Total Incident Logs Recevied by Channel (19 August – 31 May 2020 = Phone 2381, Email = 1089, Social Media = 172, Other = 2 - Total Incident Logs by Month = August 2019 = 50, September 2019 =78, October 2019 = 146, November 2019 = 240, December 2019 = 519, January 2020 = 819, February 2020 = 948, March 2020 = 604, April 2020 = 71, May = 164 | Overall completion: 64% Phase 1:100% completed 1. Application development (User) completed 100% 2. System Go-Live completed 100% on 19/8/2019 3.Development to System MPSP completed 100% on 15/11/2019 Phase 2: 64% completed 1. Requirement Anaysis Study; completed 90%, started on 2/9/2019 – 30/6/2020 2. Development & Design (Public Apps, Enforcement & Back Office); completed 73%, started on 1/11/2019 – 19/07/2020 3. Testing, Training & Commissioning; completed 68%, started on 01/2/2019 – 31/07/2020 4. Infrastructure Implementation (Sensor & Getway – Planning, Delivery, Installation); completed 28%, started 01/09/2020 - 28/2/2021 5. Change Management & Promotion; completed 60%, started on 19/08/2019 – 31/07/2020 Phase 2 Application Target Deployment 1. Fiz-Manual; completed 100% by 31/01/2020 2. Hasil – Penambahbaikan Laporan (1); completed 100% by 31/01/2020 3. Sewa Petak Khas;(MBSP) completed 100% by 22/03/2020 & MBPP, completed 100% 29/02/2020. 4. Topup di Web; completed 100% by 10/02/2020 5. Integrasi MBSP; completed 100% by 15/02/2020(PSP) 6. Hasil-Penambahbaikan Laporan 2; completed 100% by 26/03/2020 7. Pendakwaan TLK (1); completed 100% by 26/03/2020 8. FIZ-File Upload; completed 100% by 31/03/2020 9. Pendakwaan TLK(2); completed 100% by 23/04/2020 10. Pas Khas; completed 100% by 30/04/2020 11. Integrasi MBPP eBayar; completed 100% by 30/04/2020 12.Dashboard Prngurusan & Penguatkuasa; completed 100% by 30/04/2020 13. Integrasi MBSP; completed 90%, Dev by 17/04/2020(No PSP) 14.UI/UX Enhancement; completed 90%, target testing/pilot by 30/06/2020 15. Warden Trafik; completed 100% by 30/06/2020 16. Clamping/Towing; completed 100% by 30/06/2020 17. Hasil – Laporan Tambahan; completed 100%, by 30/06/2020 18. JPP; completed 90%, target testing/pilot by 9/07/2020 19. Perlesenan; completed 60%, target testing/pilot by 23/07/2020 20. Kesihatan (Veterina); completed 45%, target testing/pilot by 23/07/2020 21. Veterinar (Vektor); completed 45%, target testing/pilot by 23/07/2020 22. Jabatan Bangunan; completed 10%, target testing/pilot by 31/07/2020 23. Jabatan Perancangan; completed 10%, target testing/pilot by 31/07/2020 24. Dashboard Infrastruktur; completed 10%, target testing/pilot by 31/07/2020 25. ANPR; completed 60%, target testing/pilot by 31/07/2020 26. Integerasi JPJ; completed 10%, target testing/pilot by 31/07/2020 - PSP Incident Log Total (June 2020) = Resolved = 98%, In Progress = 2% - Total Incident Logs Recevied by Channel (19 August – 22 June 2020 = Phone 2640, Email = 1184, Social Media = 190, Other = 2 - Total Incident Logs by Month = August 2019 = 50, September 2019 =78, October 2019 = 146, November 2019 = 240, December 2019 = 519, January 2020 = 819, February 2020 = 948, March 2020 = 604, April 2020 = 71, May = 164, June = 373 | Overall completion: Plan = 83%, Actual = 70%, Phase 1:100% completed 1. Requirement Anaysis, Development & Testing ; completed 100% 2. Installation of 1031 Sensor; completed 100% Phase 2: 66% completed 1. Requirement Anaysis; completed 90%, started on 2/9/2019- 30/6/2020 2. Development & Design; completed 89%, started on 1/11/2019- 19/07/2020 3. Testing, Training & Commissioning; completed 80%, started on 01/2/2019 – 15/08/2020 4. Infrastructure Implementation (Sensor Mgmt, Bay Marketing & Time Control Board Installation); completed 30%, started 01/09/2020 - 28/2/2021 5. Change Management; completed 65%, started on 19/08/2019- 31/11/2020 6. Promotion Activites; completed 13%, started on 19/08/2019- 31/12/2026 7. Maintenance & Support; completed 13%, started on 19/08/2019 – 31/12/2026 Phase 2 Application Target Deployment 1. Fiz-Manual; completed 100% by 31/01/2020 2. Hasil – Penambahbaikan Laporan (1); completed 100% by 31/01/2020 3. Sewa Petak Khas;(MBSP) completed 100% by 22/03/2020 & MBPP, completed 100% 29/02/2020. 4. Topup di Web; completed 100% by 10/02/2020 5. Integrasi MBSP; completed 100% by 15/02/2020(PSP) 6. Hasil-Penambahbaikan Laporan 2; completed 100% by 26/03/2020 7. Pendakwaan TLK (1); completed 100% by 26/03/2020 8. FIZ-File Upload; completed 100% by 31/03/2020 9. Pendakwaan TLK(2); completed 100% by 23/04/2020 10. Pas Khas; completed 100% by 30/04/2020 11. Integrasi MBPP eBayar; completed 100% by 30/04/2020 12. Dashboard Prngurusan & Penguatkuasa; completed 100% by 30/04/2020 13. Integrasi MBSP; completed 100%, Dev by 17/04/2020(No PSP) 14. Warden Trafik; completed 100% by 30/06/2020 15. Clamping/Towing; completed 100% by 30/06/2020 16. Hasil – Laporan Tambahan; completed 100%, by 30/06/2020 17. JPP; completed 100%, target testing/pilot by 13/07/2020 18. Perlesenan; completed 100%, target testing/pilot by 20/07/2020 19. Kesihatan (Veterina); completed 100%, target testing/pilot by 27/07/2020 20. Veterinar (Vektor); completed 100%, target testing/pilot by 27/07/2020 21.UI/UX Enhancement Huawei; completed 100%, target testing/pilot by 13/07/2020 22.UI/UX Enhancement IOS & Android; completed 90%, target testing/pilot by 13/07/2020 23.Jabatan Bangunan; completed 90%, target testing/pilot by 14/08/2020 24.Jabatan Perancangan; completed 90%, target testing/pilot by 14/08/2020 25.Dashboard Infrastruktur; completed 90%, target testing/pilot by 14/08/2020 26. ANPR; completed 70%, target testing/pilot by 12/08/2020 27. Integerasi JPJ; completed 10%, target testing/pilot TBC 28. Integerasi MBSP (Non PSP); completed 90%, - Payment Non PSP target testing/pilot TBC Phase 2 – Infrastructure Sensor installation status i. MBPP: 2,629/ 7,500 unit (35%) ii. MBSP: 2,466/ 7,500 unit (35%) Change Management Activity 1. Change Awareness Session i. Key Stakeholder (Ahli Majlis Dato’ Bandar & Exco); target completed by August 2020 ii. Warga Kakitangan MBPP; completed by 16/1/2020 iii. Warga MPKK; completed by 3/3/2020 iv. Warga Kakitangan MBSP;completed by 11/3/2020 2. Public Awareness Campaign via Promotional Program i. Agent e-Coupon & Public (Served and under Served); completed by 31/7/2020 3. Change Impact Analysis i. Public Readiness & Acceptance Survey; completed by 13/4/2020 4. Change Agent Training i. Change Agent Training MBPP & MBSP; completed by August 2020 5. Post Implementation Review i. Public Acceptance Post Online Survey; target completed by September 2020 | NA- PWC2 yet to commence | Overall completion: Plan = 86%, Actual = 70%, Phase 1:100% completed 1. Requirement Anaysis, Development & Testing ; completed on 19/8/2019 100% 2. Installation of 1031 Sensor; completed on 24/9/2019 100% Phase 2: 66% completed 1. Requirement Anaysis; completed 100%, started on 2/9/2019- 30/6/2020 2. Development & Design; completed 70%, started on 1/11/2019- 31/12/2020 3. Testing, Training & Commissioning; completed 70%, started on 01/2/2019 – 31/12/2020 4. Infrastructure Implementation (Sensor Mgmt, Bay Marketing & Time Control Board Installation); completed 42%, started 01/09/2019 - 28/2/2021 5. Change Management; completed 65%, started on 19/08/2019- 31/12/2020 6. Promotion Activites; completed 16%, started on 19/08/2019- 31/12/2026 7. Maintenance & Support; completed 16%, started on 19/08/2019 – 31/12/2026 Phase 2 Application Target Deployment 1. Fiz-Manual; completed 100% by 31/01/2020 2. Hasil – Penambahbaikan Laporan (1); completed 100% by 31/01/2020 3. Sewa Petak Khas;(MBSP) completed 100% by 22/02/2020 & MBPP, completed 100% 29/02/2020. 4. Topup di Web; completed 100% by 10/2/2020 5. Integrasi MBSP; completed 100% by 15/02/2020(PSP) 6. Hasil-Penambahbaikan Laporan 2; completed 100% by 26/3/2020 7. Pendakwaan TLK (1); completed 100% by 26/03/2020 8. FIZ-File Upload; completed 100% by 31/03/2020 9. Pendakwaan TLK(2); completed 100% by 23/04/2020 10. Pas Khas; completed 100% by 30/04/2020 11. Integrasi MBPP eBayar; completed 100% by 30/04/2020 12. Dashboard Prngurusan & Penguatkuasa; completed 100% by 30/4/2020 13. Integrasi MBSP; completed 100%, Dev by 17/05/2020(No PSP) 14. Warden Trafik; completed 100% by 30/06/2020 15. Clamping/Towing; completed 100% by 30/06/2020 16. Hasil – Laporan Tambahan; completed 100%, by 23/06/2020 17. JPP; completed 100%, target testing/pilot by 13/07/2020 18. Perlesenan; completed 100%, target testing/pilot by 20/07/2020 19. Kesihatan (Veterina); completed 100%, target testing/pilot by 27/07/2020 20. Veterinar (Vektor); completed 100%, target testing/pilot by 27/07/2020 21.UI/UX Enhancement Huawei; completed 100%, target testing/pilot by 13/07/2020 22.UI/UX Enhancement IOS & Android; completed 100%, target testing/pilot by 13/07/2020 23.Jabatan Bangunan; completed 90%, target testing/pilot by 14/08/2020 24.Jabatan Perancangan; completed 90%, target testing/pilot by 14/08/2020 25.Dashboard Infrastruktur; completed 90%, target testing/pilot by 14/08/2020 26. ANPR; completed 70%, target testing/pilot by 26/08/2020 27. Integerasi JPJ; completed 10%, target testing/pilot TBC 28. Integerasi MBSP (Non PSP); completed 90%, - Payment Non PSP target testing/pilot TBC Phase 2 – Infrastructure Sensor installation status i. MBPP 1A: 6,270/ 7,500 unit (83.6%) ii. MBPP 1B: 1,756/4,500 unit (39%) ii. MBSP: 3,330/3,330 unit (100%) Change Management Activity 1. Change Awareness Session i. Key Stakeholder (Ahli Majlis Dato’ Bandar & Exco); target completed by October 2020 ii. Warga Kakitangan MBPP; completed by 16/1/2020 iii. Warga MPKK; completed by 3/3/2020 iv. Warga Kakitangan MBSP;completed by 11/3/2020 2. Public Awareness Campaign via Promotional Program i. Agent e-Coupon & Public (Served and under Served); will complete until 2026 3. Change Impact Analysis i. Public Readiness & Acceptance Survey; completed by 13/4/2020 4. Change Agent Training i. Change Agent Training MBPP & MBSP; completed by October 2020 5. Post Implementation Review i. Public Acceptance Post Online Survey; target completed by Disember 2020 | 80% (August 2020 =) (July 2020 =80%) (June 2020 = 80%) (May 2020 =67%) (April 2020=67%) (March 2020 =67%) (February 2020=67%) (January 2020=67%) (December 2019 - 67%) (November 2019 =67%)
INTERNAL SECURITY
1 | JIM | MyIMMs Application Maintenance (2017-2020) | 42430740 | 2017-08-18 | 2020-08-17 | 1. Applications Corrective Maintenance 2. Preventive Maintenance at 254 JIM branches (local & overseas) 2. Change Request and Integration 3. Installation, testing and monitoring of system at new location for not more than 30 locations 4. Training, Contract Performance Review session, Certification Program and Workshop for users and IT personnel of JIM 5. System Audit Services at least once in contract duration | Rohani Shariff | Hatta Mohd Ali/ Azlan Abd Hamid | Muhammad Fahrussyakirin, Azmin | Maintenance | No open or new issues | 40146056.71 | 2284683.29 | 35615862.26 | 19171847.69 | myIMMS Maintenance Status as at 18/12/2019: 1. Overall completion: Plan = 77%; Actual = 77% 2. Technical Support Services: i) Problem Log: Total log for December 2019 = 751. Resolved = 637; In progress = 79, Monitoring = 35 ii) Corrective Maintenance: Total log =264. Closed = 238, In progress = 18, Cancel = 5 3. Preventive maintenance: i) PM activities for Year 2 completed 259/259 branches, 100% completed ii) PM activities for Year 3 completed 147/247/ branches,60% completed 4. CR and Integration: Total CR = 215, New= 2, In progress= 7, Done UAT = 24, Completed = 159, KIV = 7, Drop = 16 5. Peluasan & Perpindahan: Year 2 Completed Cameron Highland (9/10/2018) and Besut (7/12/2018); JIM has not decided on the next branch for peluasan/ perpindahan. Year 3, will start 18/8/2019. 6. Training for Year 2: User Training = 28/28, Technical training = 4/4, CPR workshop= 4/5, Professional certification = 7/9, Technical workshop conference/seminar = 0/2 7. Training for Year 3: User Training = 7/24, Technical training = 0/4, CPR workshop= 1/5, Professional certification = 0/7, Technical workshop conference/seminar = 0/2 8. System Audit services done by Cybersecurity. Report was submitted by Cybersecurity to BTMR. Project Team to request a copy of report from Cybersecurity. Transformation: 1. Overall completion: Plan = 100%; Actual = 90% 2. Progress: i. Passport & Selenggara – completed ii. Permit– completed iii. Kutipan Hasil – completed iv. Kawalan Stok: Target Pilot = 21/08/2019, New Target Date = 30/12/2019 v. Change Request = 16/12/2019-17/01/2019, SIT = 20/01/2020-22/01/2020, Pilot = 27/01/2020 vi. Kawalan A: Pilot = 08/08/2019, Roll- out = 13/01/2020 vii. Kawalan B: Total Transactions = 127, SIT Done = 15, SIT In Progress = 11, Pilot = 1, SIT-Ready (Test Done) = 44, In Progress = 18 - SIT final = 02-06/12/2019, UAT= 11-20/12/2019, Pilot = 23-31/12/2019 (Preparation), 02-10/01/2020 (Pilot@KLIA2), RollOut = 13/01/2020 – 31/01/2020 (16 lokasi) | myIMMS Maintenance Status as at 30/01/2020: 1. Overall completion: Plan = 80%; Actual = 80% 2. Technical Support Services: i) Problem Log: Total log for January 2020 = 884. Resolved = 765; In progress = 86, Monitoring = 33 ii) Corrective Maintenance: Total log =273. Closed = 254, In progress = 11, New = 3, Cancel = 5 3. Preventive maintenance: i) PM activities for Year 2 completed 259/259 branches, 100% completed ii) PM activities for Year 3 completed 247/185 branches, 75 % completed 4. CR and Integration: Total CR = 230, New= 1, In progress= 7, Done UAT = 33, Completed = 163, KIV = 7, Drop = 16 5. Peluasan & Perpindahan: Year 2 Completed Cameron Highland (9/10/2018) and Besut (7/12/2018); next branch (Jempol, Negeri Sembilan) in planning is for year 3, start 18/8/2019. 6. Training Year 2: Completed User Training = 28/28, Technical training = 4/4, CPR workshop= 4/5, Professional certification = 9/7, Technical workshop conference/seminar = 0/2 7. Training Year 3: Completed User Training = 8/24, Technical training = 0/4, CPR workshop= 1/5, Professional certification = 0/7, Technical workshop conference/seminar = 0/2 Transformation: 1. Overall completion: Plan = 100%; Actual = 90% 2. Progress: i. Passport & Selenggara – completed ii. Permit– completed iii. Kutipan Hasil – completed iv. Kawalan Stok: completed vi. Kawalan A: Pilot = 08/08/2019, Roll- out = 13/01/2020 viii. Kawalan B: Transactions Pilot = 1, UAT Done = 22, SIT2 Done = 3, SIT2 In Improvement = 29, UAT In Test = 1, SIT2 Ready = 43, SIT2 BTMR In Test = 11, In Progress (HeiTech) = 17 Target SIT2 final, Implementation = 21/01/2020 – 14/02/2020 Target UAT 16 Location - UAT1 (Model Darat/Udara): 10/02/2020 – 12/02/2020 - Target Pilot UAT1: 17/02/2020 – 19/02/2020 (Preparation); 20/02/2020 – 28/02/2020 (Pilot@KLIA2) - Target RollOut: 03/03/2020 – 16/03/2020 (15 Location Entrance Udara/Darat) - UAT2 (Kawalan Kapal/Laut): 09/03/2020 – 13/03/2020 - Target Pilot UAT2: 16/02/2020 – 18/03/2020 (Preparation); 19/02/2020 – 27/03/2020 (Pilot @ Pel Klang & RollOut) | myIMMS Maintenance Status as at 26/02/2020: 1. Overall completion: Plan = 83%; Actual = 83% 2. Technical Support Services: i) Problem Log: Total log for February 2020 = 757. Resolved = 566; In progress =151, Monitoring = 40 ii) Corrective Maintenance: Total log =273. Closed = 262, In progress = 10, New = 3, Cancel = 5 3. Preventive maintenance: i) PM activities for Year 2 completed 259/259 branches, 100% completed ii) PM activities for Year 3 completed 247/234 branches, 95 % completed 4. CR and Integration: Total CR = 232, New= 1, In progress= 8, Done UAT = 34, Completed = 167, KIV = 5, Drop = 17 5. Peluasan & Perpindahan: Year 2 Completed Cameron Highland (9/10/2018) and Besut (7/12/2018); 6. Training Year 2: Completed User Training = 28/28, Technical training = 4/4, CPR workshop= 4/5, Professional certification = 9/9, Technical workshop conference/seminar = 0/2 7. Training Year 3: Completed User Training = 12/24, Technical training 1/4, CPR workshop=2/5, Professional certification = 0/7, Technical workshop conference/seminar = 0/2 Transformation: 1. Overall completion: Plan = 100%; Actual = 90% 2. Progress: i. Passport & Selenggara – completed ii. Permit– completed iii. Kutipan Hasil – completed iv. Kawalan Stok: completed vi. Kawalan A: Pilot = 08/08/2019, Roll- out = 13/01/2020 viii. Kawalan B: Transactions Pilot = 1, UAT Done = 0, SIT2 Done = 2, SIT2 In Improvement = 0, UAT In Test = 0, SIT2 Ready = 48, SIT2 BTMR In Test = 11, In Progress (HeiTech) = 26 Target SIT2 final, Implementation = 21/01/2020 – 13/03/2020 Target UAT 15 Location - UAT1 (Model Darat/Udara): 2/03/2020 – 04/03/2020 - Target Pilot UAT1: 09/03/2020 – 11/03/2020 (Preparation); 12/03/2020 – 21/03/2020 (Pilot@KLIA2) - Target RollOut: 22/03/2020 – 30/04/2020 (15 Location Entrance Udara/Darat) - UAT2 (Kawalan Kapal/Laut): 22/03/2020 – 27/03/2020 - Target Pilot UAT2: 06/04/2020 – 08/04/2020 (Preparation); 09/04/2020 18/04/2020 (Pilot @ Pel Klang | myIMMS Maintenance Status as at 27/03/2020: 1. Overall completion: Plan = 86%; Actual = 86% 2. Technical Support Services: i) Problem Log: Total log for March 2020 = 600. Resolved = 485; In progress =35, Monitoring = 79 ii) Corrective Maintenance: Total log =286. Closed = 263, In progress = 15, New = 3, Cancel = 5 3. Preventive maintenance: i) PM activities for Year 2 completed 259/259 branches, 100% completed ii) PM activities for Year 3 completed 237/247 branches, 96 % completed 4. CR and Integration: Total CR = 243, New= 1, In progress= 15, Done UAT = 32, Completed = 173, KIV = 5, Drop = 17 5. Peluasan & Perpindahan: Year 2 Completed Cameron Highland (9/10/2018) and Besut (7/12/2018); 6. Training Year 2: Completed User Training = 28/28, Technical training = 4/4, CPR workshop= 4/5, Professional certification = 9/7, Technical workshop conference/seminar = 0/2 7. Training Year 3: Completed User Training = 16/24, Technical training 1/4, CPR workshop=2/5, Professional certification = 3/7, Technical workshop conference/seminar = 0/2 Transformation: 1. Overall completion: Plan = 100%; Actual = 90% 2. Progress: i. Passport & Selenggara – completed ii. Permit– completed iii. Kutipan Hasil – completed iv. Kawalan Stok: completed vi. Kawalan A: Pilot = 08/08/2019, Roll- out = Postpone viii. Kawalan B: Transactions Pilot = 1, UAT Done = 0, UAT Ready = 39, UAT In Test = 0,SIT2 Done = 2,SIT2 Ready = 51,SIT2 In Improvement = 0, SIT2 BTMR In Test = 11, In Progress (HeiTech) = 23 Target SIT2 final, Implementation = 21/01/2020 – 13/03/2020 Target UAT 15 Location - UAT1 (Model Darat/Udara): Postpone - Target Pilot UAT1: 16/03/2020 – 20/03/2020 (Preparation); 23/03/2020 – 31/03/2020 (Pilot@KLIA2) - Target RollOut:0 1/04/2020 – 15/05/2020 (15 Location Entrance Udara/Darat) - UAT2 (Kawalan Kapal/Laut):30/03/2020 – 03/04/2020 - Target Pilot UAT2: 13/04/2020 – 17/04/2020 (Preparation); 20/04/2020 - 30/04/2020 (Pilot @ Pel Klang | myIMMS Maintenance Status as at 23/04/2020: 1. Overall completion: Plan = 88%; Actual = 88% 2. Technical Support Services: i) Problem Log: Total log for April 2020 = 57. Resolved = 53; In progress =0, Monitoring = 4 ii) Corrective Maintenance: Total log =293. Closed = 267, In progress = 17, New = 4, Cancel = 5 3. Preventive maintenance: i) PM activities for Year 2 completed 259/259 branches, 100% completed ii) PM activities for Year 3 completed 238/248 branches, 96 % completed 4. CR and Integration: Total CR = 255, New= 3, In progress= 18, Done UAT = 35, Completed = 177, KIV = 5, Drop = 17 5. Peluasan & Perpindahan: Year 2 Completed Cameron Highland (9/10/2018) and Besut (7/12/2018); 6. Training Year 2: Completed User Training = 28/28, Technical training = 4/4, CPR workshop= 4/5, Professional certification = 9/7, Technical workshop conference/seminar = 0/2 7. Training Year 3: Completed User Training = 16/24, Technical training 1/4, CPR workshop=4/5, Professional certification = 3/7, Technical workshop conference/seminar = 0/2 8. Status Keseluruhan Training = Total = 135, Completed = 110 Transformation: 1. Overall completion:NA 2. Progress: i. Passport & Selenggara – completed ii. Permit– completed iii. Kutipan Hasil – completed iv. Kawalan Stok: completed vi. Kawalan A: Pilot = 08/08/2019, Roll- out = Postpone viii. Kawalan B: Transactions Pilot = 1, UAT Ready = 88, UAT Done & Ready for Pilot = 37, BTMR In Test for UAT = 0, In Progress (HeiTech) = 1 Target Pilot UAT = = Postpone Target UAT 15 Location - UAT1 (Model Darat/Udara): Postpone - Target Pilot UAT1: Postpone (Pilot@KLIA2 & LTA Kuching) - Target RollOut:0 1/04/2020 – 15/05/2020 (13 Location Entrance Udara/Darat) - UAT2 (Kawalan Kapal/Laut : 89 Transaction - Target UAT: 28/4/2020 – 14/5/2020 - Target Pilot UAT2: 15/05/2020 – 14/05/2020 (Preparation @ Staging Server); 01/06/2020 - 14/06/2020 (Pilot @ Pel Klang & BKH) | myIMMS Maintenance Status as at31/05/2020: Overall completion: Plan = 83%; Actual = 83% 1. Technical Support Services: i) Problem Log: Total log for May 2020 = 365. Resolved = 313; In progress =27, Monitoring = 25 ii) Corrective Maintenance: Total log = 301. Closed = 278, In progress = 15, New =3, Cancel = 5 2. Preventive maintenance: i) PM activities for Year 2 completed 259/259 branches, 100% completed ii) PM activities for Year 3 completed 239/248 branches, 96 % completed 3. CR and Integration: Total CR = 265, New=2, In progress= 18, Done UAT = 38, Completed = 182, KIV = 5, Drop = 20 4. Peluasan & Perpindahan: Year 2 Completed Cameron Highland (9/10/2018) and Besut (7/12/2018). 5. Peluasan & Perpindahan: Year 3 Completed Perpindahan MDEC Cyberjaya (29/2/2020). 6. Training Year 2: Completed User Training = 28/28, Technical training = 4/4, CPR workshop= 4/5, Professional certification = 9/9, Technical workshop conference/seminar = 0/2 7. Training Year 3: Completed User Training = 16/24, Technical training 1/4, CPR workshop=2/5, Professional certification = 3/7, Technical workshop conference/seminar = 0/2 8. Status Keseluruhan Training = Total = 135, Completed = 110 Transformation: Overall completion: Plan = 100%; Actual = 90% 1. Progress: i. Passport & Selenggara – completed ii. Permit– completed iii. Kutipan Hasil – completed iv. Kawalan Stok: completed vi. Kawalan A: Pilot = 08/08/2019, Roll- out = Postpone viii. Kawalan B: Transactions Pilot = 38, UAT Ready = 88, Transactions Pilot Done = 38, Transaction In Test by BTMR for UAT = 0, Transaction pending UAT = 1, Transaction Done UAT & Ready for Pilot = 0 2. Target Pilot UAT = = Postpone - UAT1 (Model Darat/Udara): Postpone - Target Pilot UAT1:5/5/2020 – 19/5/2020 (Pilot@KLIA2) - Target 2nd Pilot@KLIA – 4/6/2020 – 15/6/2020 - UAT2 (Kawalan Kapal/Laut : 89 Transaction - Target UAT: 11/5/2020 – 20/5/2020 – Completed 88 Transaction; 1 Transaction, target date 4/6/2020. - Target Pilot UAT2: Pending date from BTMR Preparation @ Staging Server Pilot @ Pel Klang & BKH | 1. Overall completion: Plan = 96%; Actual = 96% 2. Technical Support Services: i) Problem Log: Total log for July 2020 = 36,444, Closed = 36,232, In progress =131 ii) Corrective Maintenance: Total log = 306. Closed = 297, In progress = 9, New =0, Cancel = 6 3. Preventive maintenance: i) PM activities for Year 2 completed 259/259 branches, 100% completed. ii) PM activities for Year 3 completed 238/238 branches, 100 % completed. 4. CR and Integration: Total CR = 285, New=1, In progress= 12, Done, UAT = 33, Completed = 211, KIV = 8, Drop = 20 5. Peluasan & Perpindahan: Year 2 • Completed Cameron Highland (9/10/2018) and Besut (7/12/2018) 6. Peluasan & Perpindahan: Year 3 • Completed Perpindahan MDEC Cyberjaya (29/2/2020). • Completed Perpindahan Bahagian Pasport George Town dan Pembukaan UTC Pulau Pinang (3/7/2020). • Completed Perpindahan Bahagian Visa Pas Permit Jabatan Imigresen Negeri Perak (20/7/2020). • Completed PTS Beranang (28/7/2020). 7. Training Year 2: Completed User Training = 28/28, Technical training = 4/4, CPR workshop= 4/4, Professional certification = 9/8 8. Training Year 3: Completed User Training = 24/24, Technical training 4/4, CPR workshop=3/3, Professional certification = 7/7 9. Status Keseluruhan Training = Total = 126, Completed = 126 | 1. Overall completion: Plan = 96%; Actual = 96% 2. Technical Support Services: i) Problem Log: Total log for July 2020 = 36,444, Closed = 36,232, In progress =131 ii) Corrective Maintenance: Total log = 306. Closed = 297, In progress = 9, New =0, Cancel = 6 3. Preventive maintenance: i) PM activities for Year 2 completed 259/259 branches, 100% completed. ii) PM activities for Year 3 completed 238/238 branches, 100 % completed. 4. CR and Integration: Total CR = 285, New=1, In progress= 12, Done, UAT = 33, Completed = 211, KIV = 8, Drop = 20 5. Peluasan & Perpindahan: Year 2 • Completed Cameron Highland (9/10/2018) and Besut (7/12/2018) 6. Peluasan & Perpindahan: Year 3 • Completed Perpindahan MDEC Cyberjaya (29/2/2020). • Completed Perpindahan Bahagian Pasport George Town dan Pembukaan UTC Pulau Pinang (3/7/2020). • Completed Perpindahan Bahagian Visa Pas Permit Jabatan Imigresen Negeri Perak (20/7/2020). • Completed PTS Beranang (28/7/2020). 7. Training Year 2: Completed User Training = 28/28, Technical training = 4/4, CPR workshop= 4/4, Professional certification = 9/8 8. Training Year 3: Completed User Training = 24/24, Technical training 4/4, CPR workshop=3/3, Professional certification = 7/7 9. Status Keseluruhan Training = Total = 126, Completed = 126 | 1. Overall completion: Plan = 100%; Actual = 1000% 2. Technical Support Services: i) Problem Log: Total log for Aug 2020 (18/8/2020 to 9/9/2020) = 963 Closed = 695, In progress =175 ii) Corrective Maintenance: Total log = 1. Closed = 1 In progress = 0, New =0, Cancel =0 3. Preventive maintenance: i) PM activities for Year 2 completed 259/259 branches, 100% completed. ii) PM activities for Year 3 completed 238/238 branches, 100 % completed. 4. CR and Integration (18/8/2020 - 9/9/2020): Total CR = 5, New=0, In progress= 5, Done, UAT = 0, Completed = 0, KIV = 0, Drop = 0 5. Peluasan & Perpindahan: Year 2 • Completed Cameron Highland (9/10/2018) and Besut (7/12/2018) 6. Peluasan & Perpindahan: Year 3 • Completed Perpindahan MDEC Cyberjaya (29/2/2020). • Completed Perpindahan Bahagian Pasport George Town dan Pembukaan UTC Pulau Pinang (3/7/2020). • Completed Perpindahan Bahagian Visa Pas Permit Jabatan Imigresen Negeri Perak (20/7/2020). • Completed PTS Beranang (28/7/2020). 7. Training Year 2: Completed User Training = 28/28, Technical training = 4/4, CPR workshop= 4/4, Professional certification = 9/8 8. Training Year 3: Completed User Training = 24/24, Technical training 4/4, CPR workshop=3/3, Professional certification = 7/7 9. Status Keseluruhan Training = Total = 135, Completed = 125 % completed = 93% |  | 100% (August 2020 = 100%) (July 2020 = 100%) (June 2020 = 100%) (May 2020 = 100%) (April 2020 =100%) (March = 100%) (February 2020=100%) (January 2020=100%) (December 2019=100%) (November 2019=100% ) (October 2019 = 100%) (September 2019 = 100%)
1.1 |  | MyIMMs Application Maintenance (2017-2020) | 42430740 | 2020-08-18 | 2020-08-17 | 1. Applications Corrective Maintenance 2. Change Request and Integration | Rohani Mat Shariff | Azlan Abd Hamid | Azmin Adnan Faheussyakirin | Maintenance | No new or open issues | [11 empty] | NA | NA | 1. Overall completion: Plan = 96%; Actual = 96% 2. Technical Support Services: i) Problem Log: Total log (18/8/2020 - 30/10/2020 ) = 2,422, Closed = 2,343, Monitoring = 51, In progress =26 ii) Corrective Maintenance: Total log = 5 Closed = 4, In progress = 1, Cancel = 0 3. CR and Integration: Total CR = 25, New=14, In progress= 5, Done, UAT = 0, Completed = 6, KIV = 0, Drop = 0
2 | BESTINET | BESTINET: Integration Service Between Foreign Worker Centralized Mgmt System (FWCMS) and myIMMs System (2018 - 2021) | 2289600 | 2018-11-01 | 2021-10-31 | 1. Furnish Data from myIMMs to FWCMS 2. One Time and Incremental Data Update 3. Batch Jobs | Wan Suhaimi Wan Abd Hamid | Hatta Mohd Ali/ Azlan Abd Hamid | Muhammad Fahrussyakirin, Azmin | Maintenance | 1. (PSC 1/2019) - Pending payment for GST for May 2015 & June 2015. Bestinet claimed payment has been paid. To get proof of payment. (PSC 4/2019) - Bestinet claimed they had paid with cheque. Finance to follow up with Bestinet on the outstanding GST payment. (PSC 9/2019) - Finance to discuss with Bestinet on payment plan for outstanding payment. (PSC 12/2019) - Bestinet did not make payment to HTP as agreed. Finance to follow-up (open) 2. (PSC 4/2020) –Claim for Bestinet Jan 2020 RM508,800 is yet to be paid (open) | 1399200 | 890400 | 699600 |  | Application support on going. | Application support on going. | Application support on going. | Application support on going. | Application support on going. | Application support on going. | Application support on going. | Application support on going. | Application support on going. | Application support on going. | 100% (August 2020=100%) (July 2020=100%) (June 2020 =100%) (May 2020 =100%) (April 2020=100%) (March=100%) (February 2020=100%) (January 2020=100%) (December 2019=100%) (November 2019=100%) (October 2019 = 100%) (September 2019 = 100%)
3 | myEG | my EG Sevices Bhd: Integration services between myEG & myIMMs System on Working Permit Renewal of Foreign Workers | 2400000 | 2013-01-01 | TBA | 1. Application Dev & Maintenance | Wan Suhaimi Wan Abd Hamid | Hatta Mohd Ali/ Azlan Abd Hamid | Muhammad Fahrussyakirin, Azmin | Maintenance | No open or new issues | 3133627.93 | -733627.93 | 3051097.92 |  | 1. Services on going. Concession basis (50 cent per transaction) | 1. Services on going. Concession basis (50 cent per transaction) | 1. Services on going. Concession basis (50 cent per transaction) | 1. Services on going. Concession basis (50 cent per transaction) | 1. Services on going. Concession basis (50 cent per transaction) | 1. Services on going. Concession basis (50 cent per transaction) | 1. Services on going. Concession basis (50 cent per transaction) | 1. Services on going. Concession basis (50 cent per transaction) | 1. Services on going. Concession basis (50 cent per transaction) | 1. Services on going. Concession basis (50 cent per transaction) | NA
4 | MAHB | MALAYSIA AIRPORT HOLDINGS BERHAD (MAHB): Integration services for AQMS | 625292 | 29 Dec 2017 | 2021-04-18 | Integration services for AQMS . | Wan Suhaimi Wan Abd Hamid | Hatta Mohd Ali/ Azlan Abd Hamid | Muhammad Fahrussyakirin, Azmin | Development | No open or new issues | 3133627.93 | -2508335.93 | 3051097.92 |  | Maintenance on going | Maintenance on going | Maintenance support on going | Maintenance and support on going | Maintenance and support on going | Maintenance and support on going | Maintenance and support on going | Maintenance and support on going | Maintenance and support on going | Maintenance and support on going | NA
FOMEMA
1 | FOMEMA | FOMEMA MYIMM Biometric Integration | 48230000 | 2017-01-01 | 2026-12-31 | 1.Integration of FOMEMA application 2.Supply, delivery and deployment of 3.Biometric Fingerprint Scanner 4.Maintenance | Ahmad Suryadi bin Abd Aziz | Ibrahim Yusoff | Halimah Din | Implementation | No new or open issues | 22697850.76 | 25532149.24 | 22697850.76 | 26436474.73 | 1. Overall completion = 99% Pilot Production: Total Online Panels = 3,415 2. Stage 3 (761 panels) - Perak = 100% 3. Stage 4 (566 panels) - Go-Live for clinics/panels = 93%, started on 7/10/2019 and target to complete on 31/12/2019. - Kedah = 100%, Penang = 87%, Kelantan = 100%, Terengganu = 100% 4. Stage 5 (655 panels) - Go-Live for clinics/panels = 81%, started on 7/112019 and target to complete on 31/12/2019. - Johor = 78%, Perlis = 100%, Labuan = 100% 5. Maintenance activities: a) New Installation on 528 panel, start date 1/12/2019 and end 20/12/2019 - Total request + installed To Date = 96 - No response yet = 425 - Installation in December 2019 =10 b) Problem Log December 2019: - Total Received = 229 - Open = 11 - Closed = 193 6. Monthly report preparation for November 2019 completed on 20/12/2019. | 1. Overall completion = 99% Pilot Production: Total Online Panels = 3,415 Stage 3 (761 panels) = 100%, completed Stage 4 (566 panels) = completed on 28/12/2019 Stage 5 (655 panels) = completed on 10/01/2020 2. Lost Device Panels = 136 Fail Upgrade Panels = 132 Completed = 50%, start date 6/1/2020 and end 9/1/2020 3. Fomema successfully deployed performance tracking on biodata access to myIMMs, completed = 10%, start date 3/1/2020 and end 20/1/2020 4. a) New Installation on 528 Unreadiness Clinics, start date 1/12/2019 and end 20/12/2019 - Total request + installed To Date = 96 - No response yet = 425 - Installation in December 2019 =10 b) Problem Log January 2020: - Total Received = 269 - Open = 1 - Closed = 262 5. Monthly report preparation for December 2019 completed on 30/01/2020. | 1. Overall completion = 99% Pilot Production: Total Online Panels = 3,415 Stage 3 (761 panels) = 100%, completed Stage 4 (566 panels) = completed on 28/12/2019 Stage 5 (655 panels) = completed on 10/01/2020 2. Lost Device Panels = 136 Fail Upgrade Panels = 132 Completed = 50%, start date 12/3/2020 3. Fomema successfully deployed performance tracking on biodata access to myIMMs, completed = 10%, start date 3/1/2020 and end 20/1/2020 4. a) New Installation on 528 Unreadiness Clinics, start date 1/12/2019 and end 20/12/2019 - Total request + installed To Date = 106 - No response yet = 415 - Installation in January & February =10 b) Problem Log February 2020: - Total Received = 515 - Open = 1 - Closed = 481 5. Monthly report preparation for January 2020 completed on 12/02/2020. | Overall completion = 99% 1.Pilot Production: Total Online Panels = 3,415 Stage 3 (761 panels) = 100%, completed Stage 4 (566 panels) = completed on 28/12/2019 Stage 5 (655 panels) = completed on 10/01/2020 2. Lost Device Panels = 136 Fail Upgrade Panels = 132 Completed = 50%, start date 12/3/2020 3. Fomema agreed on BTMR request to enhance log files on gateway server with a statistical report, completed = 10%, start date 3/1/2020 and end 20/1/2020 4. a) New Installation on 528 Unreadiness Clinics, start date 1/12/2019 and end 20/12/2019 - Total request + installed To Date = 106 - No response yet = 415 - Installation in January & February =10 b) Problem Log March 2020: - Total Received = 321 - Open = 2 - Closed = 319 5. Monthly report preparation for February 2020 pending submission and printing due to MCO. | Overall completion = 99% 1. Pilot Production: Total Online Panels = 3,415 Stage 3 (761 panels) = 100%, completed Stage 4 (566 panels) = completed on 28/12/2019 Stage 5 (655 panels) = completed on 10/01/2020 2. Lost Device Panels = 136 Fail Upgrade Panels = 132 Completed = 50%, start date 12/3/2020 3. Fomema agreed on BTMR request to enhanced log files on gateway server with a statistical report, completed = 10%, start date 21/1/2020. 4. a) New Installation on 400 panel Clinics, start date 12/2/2020 and end 31/05/2020 – waiting official RFQ from Fomema. b) New Installation on 528 Unreadiness Clinics. - Total request + installed To Date = 106 - No response yet = 415 - Installation in January & February =10 c) Problem Log March 2020: - Total Received = 94 - Open = 0 - Closed = 90 - Cancelled /Duplicate = 4 5. Monthly report preparation for March & April 2020 pending printing and submission due to MCO. | Overall completion = 99% 1. Pilot Production: Total Online Panels = 3,415 Stage 3 (761 panels) = 100%, completed Stage 4 (566 panels) = completed on 28/12/2019 Stage 5 (655 panels) = completed on 10/01/2020 2. Lost Device Panels = 136 Fail Upgrade Panels = 132 Completed = 50%, start date 12/3/2020 3. Fomema agreed on BTMR request to enhanced log files on gateway server with a statistical report, completed = 10%, start date 21/1/2020. 4. a) New Installation on 400 panel Clinics, start date 12/2/2020 and end 31/05/2020 – waiting official RFQ from Fomema. b) New Installation on 528 Unreadiness Clinics. - Total request + installed To Date = 123 - No response yet = 405 - Installation in May 2020 =1 c) Problem Log May 2020; - Total Received = 270 - Open = 0 - Closed = 269 - Cancelled /Duplicate = 16 5. Monthly report preparation for March & April 2020 pending on printing and submission due to MCO. | 1. Overall completion = 99% 2.Pilot Production: Total Online Panels = 3,415 Stage 3 (761 panels) = 100%, completed Stage 4 (566 panels) = completed on 28/12/2019 Stage 5 (655 panels) = completed on 10/01/2020 3. Lost Device Panels = 136 Fail Upgrade Panels = 132 Completed = 50%, start date 12/3/2020 4. Fomema agreed on BTMR request to enhanced log files on gateway server with a statistical report, completed = 10%, start date 20/1/2020. 5. a) New Installation on 528 panel Clinics - Total request + installed To Date = 125 - No response yet = 403 - Installation in June 2020 =2, start date 1/6/2020 b) Problem Log June 2020: - Total Received = 295 - Open = 2 - Closed = 293 - Cancelled /Duplicate = 14 6. Monthly report preparation for March & April 2020 pending on printing and submission due to MCO. | 1. Overall completion = 99% 2. Pilot Production: Total Online Panels = 3,415 Stage 3 (761 panels) = 100%, completed Stage 4 (566 panels) = completed on 28/12/2019 Stage 5 (655 panels) = completed on 10/01/2020 2. Fomema agreed on BTMR request to enhanced log files on gateway server with a statistical report, completed = 10%, start date 20/1/2020. 3. a) New Installation on 528 panel Clinics - Total request + installed To Date = 130 - No response Panels = 398 - Installation in June 2020 =5, start date 1/7/2020 b) Problem Log July 2020: - Total Received = 515 - Open = 33 - Closed = 482 - Cancelled /Duplicate = 28 4. Monthly report for June 2020, completed by 27/7/2020 | 1. Overall completion = 99% 2. Pilot Production: Total Online Panels = 3,415 Stage 3 (761 panels) = 100%, completed Stage 4 (566 panels) = completed on 28/12/2019 Stage 5 (655 panels) = completed on 10/01/2020 2. Fomema agreed on BTMR request to enhanced log files on gateway server with a statistical report, completed = 10%, start date 20/1/2020. 3. a) New Installation on 528 panel Clinics - Total request + installed To Date = 131 - No response Panels = 397 - Installation in August 2020 =1, start date 1/8/2020 b) Problem Log August 2020: - Total Received = 1,032 - Open = 16 - Closed = 1,016 - Cancelled /Duplicate = 0 4. Monthly report for July 2020 and August 2020 yet to complete. | slide x dpt | 93% (August 2020=93%) (July 2020 =93%) (June 2020 =93%) (May 2020= 93%) (April 2020=93%) (March = 100%) (February 2020=93%) (January 2020 =93%) (December 2019=93%) (November 2019=93%) (October 2019 = 93%) (September 2019 = 93%)
HEALTH
1 | MOH | Critical Care Information System (CCIS) | 33179367.26 | 2019-02-01 | 2022-01-31 | 1. To supply, deliver, install, configure, testing and commission ICT Hardware and Software including network and integration 2. To supply, delivery, install, configure, testing and commission Critical Care Information System (CCIS) 3. To integrate CCIS with Sistem Pengurusan Pesakit (SPP) at 3 Hospitals i.e. Hospital Raja Permaisuri Bainun(HRPB), Hospital Raja Perempuan Zainab II (HRPZ II) and Hospital Tuanku Jaafar, Seremban. 4. To implement Critical Care Information System Project 5. To provide Service Support Operation, Helpdesk and Maintenance services during warranty period 6. To provide other related services with the implementation of CCIS i.e - Business Continuity Plan - Training and Transfer of Technology (ToT) - Change Management - Benefit Realization - Project Management Services | Mazwin Idris | Ahmad Zamin Mahadzir/Ibrahim Yusoff | Abu Yazid (Head PMO) Sanuza Zahari | Development | 1. ( PSC 2/2020) - Hardware as per tender BQ due to reduction of requirements in respective site ( open) (PSC 5/2020)- HTP propose to use the unallocated hardware for sites that requires the equipment ie HTJS (UPS Server and Rack) HPP (DB) (PSC 6/2020) -KKM agreed that only request related to CCIS Project are only will be approved KKM Project Working Committee (PWC) meeting agreed. Project Technical Committee (PTC) meeting endorsed and to bring to Project Steering Committee (PSC) Meeting Committee for approval PWC 2/2020 - KKM Project Working Committee (PWC) meeting agreed. Project Technical Committee (PTC) meeting endorsed and to bring to Project Steering Committee (PSC) Meeting Committee for approval PSC 2/2020 15/10/2020 To bring up to PSC meeting .(open) | 2709890 | 30469477.26 | 2709890 | 9476137 | 1. Overall completion: Plan = 35%, Actual = 25% (as at 26/12/2019). Delay due to: a. 3% delay due to MOH Postponement of Kick Off CCIS Project, planned 4/2/2019 actual 12/3/2019 b. 10% delay on Change of Hardware Model (EOF) • MOH Approval on Reduction of BQ for Hospital Melaka • MOH Approval on Usage of Hard Material Cable vs GI • Partner (LKL) delay in delivery of Trolley • Partner (Prestaring) delay on license key and requires MOH approval c. 1% MOH Finalization of CCIS Flow Sheet Template from 11 hospitals 2. Activity Status: i. Project Management: Plan= 32%, Completed = 25% ii. Site Evaluation & Solutions Planning, Completed = 100% iii. Infrastructure Implementation: Plan = 100%, Completed = 60% iv. CCIS Software Implementation = 22%, Completed = 18% v. Interfacing Medical Equipment: Plan = 5%, Completed = 5% vi. UAT: Plan = 1%, Completed = 1% vii. Integration with SPP: Plan = 9%, Completed = 3% viii. Training & ToT: Plan = 10%, Completed = 5% ix. Change Management: Plan = 48%, completed = 40% 3. Contract Management: i. Contract preparation with Government is still pending with KKM. ii. Sub-contract with Netlee, still in progress, discussion with Netlee on 16/1/2020, target completion by 31/01/2020 iii. Sub-contract preparation with KCSB is in progress, target completion by 15/01/2020 4. Infrastucture Implementation: i. Completed for all hospitals except for HSA Johor, HRPZII Kota Bharu and PDSA Putrajaya ii. Hospital Melaka, completed, target hardware delivery on 25/11/2019; confirmation on reduction of scope in PSC with MOH on 14/11/2019 due to power shortage iii. HSA, Johor, work in progress, delay due to confirmation on cabling material in MOH PSC on 14/11/2019; target hardware delivery 23/12/2019 – 29/12/2019. iv. HUS, Sarawak completed infrastructure work, hardware delivery target on 16/12/2019 – 20/12/2019. v. Other hospitals hardware delivery will be done in January and February 2020. 5. Project Deployment Activities in December 2019: i. HTAR, Klang – Pilot site; completed infrastructure work, hardware delivery and CCIS installation. Parallel run target from 29/11/2019 – 28/12/2019. ii. H Melaka – completed infrastructure work and hardware delivery. Change Awareness program done on 28/11/2019. iii. HTJS, NS – completed infrastructure work, hardware delivery target on 9/12/2019 – 13/12/2019, Change Awareness program done on 9/12/2019. iv. HTAA, Kuantan – completed infrastructure work, hardware delivery target on 2/12/2019 – 6/12/2019, PICIS installation 2/12/2019 – 13/12/2019. Change Awareness program done on 13/12/2019. | 1. Overall completion: Plan = 38%, Actual = 28% (as at 31/01/2020). Delay due to: a. 3% delay due to MOH Postponement of Kick Off CCIS Project, planned 4/2/2019 actual 12/3/2019 b. 7% delay on Change of Hardware Model (EOF) • MOH Approval on Printer Model 2. Activity Status: i. Project Management: Plan= 38%, Completed = 28% ii. Site Evaluation & Solutions Planning, Completed = 100% iii. Infrastructure Implementation: Plan = 100%, Completed = 85% iv. CCIS Software Implementation :30%, Completed = 28% v. Training & ToT: Plan = 10%, Completed = 10% vi. Change Management: Plan = 45%, completed = 45% vii. Business Continuity Plan (BCP): Plan = 11%, Completed =11% viii. Benefit Realization Plan (BRP): Plan =19%, Completed = 19% 3. Contract Management: i. Contract preparation with Government is still pending with KKM. ii. Sub-contract with Netlee, still in progress, discussion with Netlee on 16/1/2020, target completion by 06/02/2020 iii. Sub-contract preparation with KCSB is in progress, target completion by 3/02/2020 4. Infrastructure Implementation: i. HUS, Sarawak completed infrastructure work, delay due on the requirement of IP Address and Network segmentation is needed from all hospitals. Target to completed on 29/02/2020. ii. Additional electrical work for UPS installation in HQA and HUS, target to completed on 15/2/2020 iii. HRPZ Electrical Infrastructure, current electrical set up is based on single phase, thus additional DB is required to cater for CCSI, completed 14/12/2019. iv. Readiness of Hospital Infrastructure site for ICU ward 3 HTF is only 50% completed. v. Readiness of equipment for HPP is lacking of additional 10 trolley, confirmation on reduction of scope in PSC with KKM on April 2020. vi. Hospital people readiness and coordination in accepting CCIS system for HMelaka is to confirm if they are ready to accept the installation of CCIS due to internal hospital coordination after encounter Code Orange issue. vii. Other hospitals hardware delivery will be done in January and February 2020. 5. Project Deployment Activities in January 2020: i. HTAR, Klang, HTAA Kuantan, HQE 1, Kota Kinabalu, HUS Kuching, HAS Johor, HMelaka, HTF Kangar, HRPB, Ipoh, HTJS, Seremban – completed document infrastructure WIP for Electrical work and cabling done on 22/01/2020. ii. HTAR, Klang, HTAA Kuantan, HQE 1, Kota Kinabalu, HUS Kuching, HAS Johor, HMelaka, HTJS, Seremban – completed document for Hardware delivery, Installation and Configuration done on 29/01/2020. | 1. Overall completion: Plan = 59%, Actual = 49% (as at 29/02/2020). Delay due to: a. 3% delay due to MOH Postponement of Kick Off CCIS Project, planned 4/2/2019 actual 12/3/2019 b. 7% delay on Change of Hardware Model (EOF) • MOH Approval on Printer Model 2. Activity Status: i. Project Management: Plan= 68%, Completed = 71% ii. Site Evaluation & Solutions Planning, Completed = 100% iii. Infrastructure Implementation: Plan = 100%, Completed = 96% iv. CCIS Software Implementation :58%, Completed = 28% v. Training & ToT: Plan = 75%, Completed = 43% vi. Change Management: Plan = 91%, completed = 87% vii. Business Continuity Plan (BCP): Plan = 78%, Completed =11% viii. Benefit Realization Plan (BRP): Plan =40%, Completed = 19% 3. Contract Management: i. Sent reminder letter to MOH 0n 5/2/2020. Received contract from MOH for signing on 10/2/2020. En Halim signed the contract and return to MOH on 27/2/2020. ii. Netlee has returned the contract to HTP. HTP need to review the scheduled and SOW iii. HTP has received the KCSB sub contract completed contract on 20/2/2020 4. Infrastructure Implementation: i. Requirement of IP Address and Network segmentation is needed from all hospitals - HTP needs to review the existing network in HUS before configure CCIS network for not to interrupt with future Hospital Network configuration. Currently there is no Core Switches available in HUS. ii. Additional electrical work for UPS installation in HQA and HUS- HQEI – 27/2/20 completed reconfigure and reinstall HTP additional ELCB in the current DB HUS – Target in end Mac 2020 after complete hardware work in HPP an HRPB iii. HRPZ Electrical Infrastructure - HTP propose to use the unallocated DB (available 2 units from HMelaka and HTJS) Discussion with HRPZ on 11 Feb 2020 Submit proposal on 25 Feb 2020 (refer to slide) iv. Readiness of Hospital Infrastructure site for ICU ward 3 HTF is only 50% completed- HTP will delivery all required hardware but installation of respective hardware will be delayed until the completion of Ward ICU3. HTP is proposing payment based on delivering of hardware. . v. Readiness of equipment for HPP- HPP is lacking of additional 10 trolley- HTP will delivery all required hardware but install of respective trolley will be delayed until the trolley is ready. HTP is proposing payment based on delivering of hardware. vi. Readiness in Hospital antivirus and intrusion policy - HTP recommended that all hospital has to comply to MOH standard antivirus protection policy to safeguards the IT network vii. Hospital people readiness and coordination in accepting CCIS system - HTP propose to delay HMelaka CCIS installation after HTAA as to give coordination period within interdepartmental roles and responsibility viii. Unallocated Hardware as per tender BQ due to reduction of requirements in respective site - HTP propose to use the unallocated hardware for sites that requires the equipment ie HTJS (UPS Server and Rack) HPP (DB) ix. Mobility and ease of trolley movement due to limited working area in ICU - HTP propose to use project cost saving of RM896K 5. Project Activities in February 2020: i. UPS Servers - Pending due to electrical capacity by each hospital. HARDWARE DELIVERY ii. HPP - Delay due HSE (House Safety Environment) agreed to continue in week 9 or 16 March iii. HRPZ - pending on installation of the new DB after new electrical layout iv. PDSA – pending on documentation submission on end Mac Infra Documentation: HPP – pending on hospital feedback HRPZ – pending on installation of the new DB after new electrical layout PDSA – pending on documentation submission Change Management: HRPB – feedback on Pengarah availability HTF, HPP, HRPZ, HTJS – pending to obtain sign off Go Live Briefing and Final Questionaries' – upon go live activities Switch Configuration: HUS – obtain IP on 19 Feb and plan to reconfigure switches and servers on end Mac NetVault: Requires reconfiguration with upgrade of ODBC in MSSQL Report: Pending on documentation compilation- MS license etc | Overall completion: Plan = 59%, Actual = 49% (as at 31/03/2020). 1. Delay due to: a. 3% delay due to MOH Postponement of Kick Off CCIS Project, planned 4/2/2019 actual 12/3/2019 b. 7% delay on Change of Hardware Model (EOF) • MOH Approval on Printer Model 2. Activity Status: i. Project Management: Plan= 68%, Completed = 71% ii. Site Evaluation & Solutions Planning, Completed = 100% iii. Infrastructure Implementation: Plan = 100%, Completed = 96% iv. CCIS Software Implementation :58%, Completed = 28% v. Training & ToT: Plan = 75%, Completed = 43% vi. Change Management: Plan = 91%, completed = 87% vii. Business Continuity Plan (BCP): Plan = 78%, Completed =11% viii. Benefit Realization Plan (BRP): Plan =40%, Completed = 19% ix. PAT Go Live: Plan = 23%, Completed = 20% 3. Contract Management: i. Sent reminder letter to MOH 0n 5/2/2020. Received contract from MOH for signing on 10/2/2020. En Halim signed the contract and returned to MOH on 27/2/2020. ii. Netlee has returned the contract to HTP. HTP need to review the scheduled and SOW. Finalizing the contract, target by 6 March 2020. Contract pending on Netlee feedback on HTP comments. iii. HTP has received the KCSB sub contract completed contract on 20/2/2020 4. Infrastructure Implementation: i. Requirement of IP Address and Network segmentation is needed from all hospitals - HTP needs to review the existing network in HUS before configure CCIS network for not to interrupt with future Hospital Network configuration. Currently there is no Core Switches available in HUS. ii. Additional electrical work for UPS installation in HQA and HUS- HQEI – 27/2/20 completed reconfigure and reinstall HTP additional ELCB in the current DB. HUS – Target in end Mac 2020 after complete hardware work in HPP an HRPB iii. HRPZ Electrical Infrastructure - HTP propose to use the unallocated DB (available 2 units from HMelaka and HTJS) - Discussion with HRPZ on 11 Feb 2020 - Submit proposal on 25 Feb 2020 (refer to slide) iv. Readiness of Hospital Infrastructure site for ICU ward 3 HTF is only 50% completed- HTP will delivery all required hardware but installation of respective hardware will be delayed until the completion of Ward ICU3. HTP is proposing payment based on delivering of hardware. v. Readiness of equipment for HPP- HPP is lacking of additional 10 trolley- HTP will delivery all required hardware but install of respective trolley will be delayed until the trolley is ready. HTP is proposing payment based on delivering of hardware. vi. Readiness in Hospital antivirus and intrusion policy - HTP recommended that all hospital has to comply to MOH standard antivirus protection policy to safeguards the IT network. vii. Hospital people readiness and coordination in accepting CCIS system - HTP propose to delay HMelaka CCIS installation after HTAA as to give coordination period within interdepartmental roles and responsibility. viii. Unallocated Hardware as per tender BQ due to reduction of requirements in respective site - HTP propose to use the unallocated hardware for sites that requires the equipment ie HTJS (UPS Server and Rack) HPP (DB). KKM agreed that only request related to CCIS Project are only will be approval. ix. Mobility and ease of trolley movement due to limited working area in ICU - HTP propose to use project cost saving of RM896K. KKM agreed to present it in the next Technical Meeting. 5. Project Activities in March 2020: i. Infra Documentation: Delay due to MCO till 14 April 2020. ii. Change Management: Delay due to MCO till 14 April 2020. iii. Hardware Delivery: Delay due to MCO till 14 April 2020. iv. Software Delivery: Delay due to MCO till 14 April 2020. v. PICIS Installation: Delay due to MCO till 14 April 2020. vi. Training: Delay due to MCO till 14 April 2020. vii. Testing: Delay due to MCO till 14 April 2020. | Overall completion: Plan =68%, Actual = 49%2. 1. Activity Status: i. Project Management: Plan= 71%, Completed = 68% ii. Site Evaluation: Completed = 100% iii. Infrastructure Implementation: Plan = 100%, Completed = 96% iv. CCIS Software Implementation: Plan = 58%, Completed = 25% v. Interfacing Medical Equipment: Plan = 45%, Completed = 22% vi. UAT: Plan = 45%, Completed = 22% vii. Integration with SPP: Plan = 50%, Completed = 26% viii. Training & ToT: Plan = 35%, Completed = 20% ix. Change Management & Business Continuity Plan (BCP): Plan = 90%, completed = 89% x. PAT Go Live: Plan = 23%, Completed = 20% 2. Contract Management: i. Sent reminder letter to MOH 0n 5/2/2020. Received final contract copy from MOH for signing on 10/2/2020. En Halim signed the contract and & HTP signature, return to MOH on 27/2/2020. ii. Netlee has returned the contract to HTP. HTP need to review the scheduled and SOW. Finalizing the contract, target by 6 March 2020. Contract pending on Netlee feedback on HTP comments. iii. HTP has received the KCSB sub contract completed signed, stamped contract on 20/2/2020. 3. Infrastructure Implementation: i. Requirement of IP Address and Network segmentation is needed from all hospitals - HTP needs to review the existing network in HUS before configure CCIS network for not to interrupt with future Hospital Network configuration. Currently there is no Core Switches available in HUS. ii. Additional electrical work for UPS installation in HQA and HUS- HQEI – 27/2/20 completed reconfigure and reinstall HTP additional ELCB in the current DB. HUS – Target in end Mac 2020 after complete hardware work in HPP an HRPB. iii. HRPZ Electrical Infrastructure - HTP propose to use the unallocated DB (available 2 units from HMelaka and HTJS) - Discussion with HRPZ on 11 Feb 2020 - Submit proposal on 25 Feb 2020 (refer to slide) iv. Readiness of Hospital Infrastructure site for ICU ward 3 HTF is only 50% completed- HTP will delivery all required hardware but installation of respective hardware will be delayed until the completion of Ward ICU3. HTP is proposing payment based on delivering of hardware. v. Readiness of equipment for HPP- HPP is lacking of additional trolley- HTP will delivery all required hardware but install of respective trolley will be delayed until the trolley is ready. HTP is proposing payment based on delivering of hardware. vi.Readiness in Hospital antivirus and intrusion policy - HTP recommended that all hospital has to comply to MOH standard antivirus protection policy to safeguards the IT network. vii.Hospital people readiness and coordination in accepting CCIS system. - Delay in implementation due to ICU converted to COVID 19 center. - HTP propose to delay HMelaka CCIS installation after HTAA as to give coordination period within interdepartmental roles and responsibility. viii.Unallocated Hardware as per tender BQ due to reduction of requirements in respective site. - HTP propose to use the unallocated hardware for sites that requires the equipment ie HTJS (UPS Server and Rack) HPP (DB). KKM agreed that only request related to CCIS Project are will be approval. ix. Mobility and ease of trolley movement due to limited working area in ICU. - HTP propose to use project cost saving of RM896K. KKM agreed to present it in the next Technical Meeting. 4. Project Activities Till 6 March 2020: i. Infra Delivered and Pending Sign Off: Delay due to MCO and COVID19 ii. Hardware Delivery: Delay due to MCO and COVID19 iii. Rework and Reinstall required: All hospital site due to movement of hardware delivered iv. Change Management: Delay – waiting feedback on Pengarah availability, target CMA in end March or early April v. UPS Servers Status: Pending KKM discussion electrical capacity due to MCO & COVID19 vi. Hardware Delivery Status: Delay due to MCO and COVID19 vii. Switch Configuration: Delay due to MCO and COVID19 viii. NetVault Reconfiguration: Delay due to MCO and COVID19 ix. Report Submission & Review: Delay due to MCO and COVID19 x. CCIS Implementation: Delay due to MCO and COVID19 xi. CCIS Integration Development: Delay developing the interface COE module due to MOC and delay in hardware rework and CCIS final configuration xii. Delay in Training, Testing and Go Live: Delay due to MCO and COVID19 | Overall completion: Plan = 68%, Actual =49% (as at 31/05/2020). Delay due to: a. 3% delay due to MOH Postponement of Kick Off CCIS Project, planned 4/2/2019 actual 12/3/2019 b. 7% delay on Approval Printer Model, impact the Go Live data c. 10% MCO ruling due to COVID19 1. Activity Status: i. Project Management: Plan= 71%, Completed = 68% ii. Site Evaluation: Completed = 100% iii. Infrastructure Implementation: Plan = 100%, Completed = 96% iv. CCIS Software Implementation: Plan = 58%, Completed = 25% v. Interfacing Medical Equipment: Plan = 45%, Completed = 22% vi. UAT: Plan = 45%, Completed = 22% vii. Integration with SPP: Plan = 50%, Completed = 26% viii. Training & ToT: Plan = 35%, Completed = 20% ix. Change Management & Business Continuity Plan (BCP): Plan = 90%, completed = 89% x. PAT Go Live: Plan = 23%, Completed = 20% (Delay on Parallel Run/ Test due to COVID19 for HTAA, HQE1, HM, HTF) 2. Contract Management: i. Contract with Governement – Completed, signed, stamped and received on 6 Mac 2020. ii. Netlee has returned the contract to HTP. HTP need to review the scheduled and SOW. Finalizing the contract, target by 6 March 2020. Contract pending on Netlee feedback on HTP comments. Further discussion to be held on 3 June 2020. iii. KCSB sub contract completed signed, stamped and received contract on 20/2/2020. 3. Infrastructure Implementation: i. Requirement of IP Address and Network segmentation is needed from all hospitals - HTP needs to review the existing network in HUS before configure CCIS network for not to interrupt with future Hospital Network configuration. Currently there is no Core Switches available in HUS. ii. Additional electrical work for UPS installation in HQA and HUS- HQEI – 27/2/20 completed reconfigure and reinstall HTP additional ELCB in the current DB. HUS – Target in end Mac 2020 after complete hardware work in HPP an HRPB. iii. HRPZ Electrical Infrastructure - HTP propose to use the unallocated DB (available 2 units from HMelaka and HTJS) - Discussion with HRPZ on 11 Feb 2020 - Submit proposal on 25 Feb 2020 (refer to slide) iv. Readiness of Hospital Infrastructure site for ICU ward 3 HTF is only 50% completed- HTP will delivery all required hardware but installation of respective hardware will be delayed until the completion of Ward ICU3. HTP is proposing payment based on delivering of hardware. v. Readiness of equipment for HPP- HPP is lacking of additional 10 trolley- HTP will delivery all required hardware but install of respective trolley will be delayed until the trolley is ready. HTP is proposing payment based on delivering of hardware. vi. Readiness in Hospital antivirus and intrusion policy - HTP recommended that all hospital has to comply to MOH standard antivirus protection policy to safeguards the IT network. vii. Hospital people readiness and coordination in accepting CCIS system - Delay in implementation due to ICU converted to COVID 19 center - HTP propose to delay HMelaka CCIS installation after HTAA as to give coordination period within interdepartmental roles and responsibility. viii. Unallocated Hardware as per tender BQ due to reduction of requirements in respective site. - HTP propose to use the unallocated hardware for sites that requires the equipment ie HTJS (UPS Server and Rack) HPP (DB). KKM agreed that only request related to CCIS Project are only will be approval. ix. Mobility and ease of trolley movement due to limited working area in ICU. - HTP propose to use project cost saving of RM896K. KKM agreed to present it in the next Technical Meeting. 4. Project Activities Till 31 May 2020: i. Infra Delivered and Pending Sign Off: Delay due to MCO and COVID19 ii. Hardware Delivery: Delay due to MCO and COVID19 iii. Rework and Reinstall required: All hospital site due to reassess movement of hardware delivered iv. Change Management: Delay – waiting feedback on Pengarah availability, target CMA in end March or early April v. UPS Servers Status: Pending KKM discussion electrical capacity due to MCO & COVID19 vi. Hardware Delivery Status: Delay due to MCO and COVID19 vii. Switch Configuration: Delay due to MCO and COVID19 viii. NetVault Reconfiguration: Delay due to MCO and COVID19 ix. Report Submission & Review: Delay due to MCO and COVID19 x. CCIS Implementation: Delay due to MCO and COVID19 xi. CCIS Integration Development: Delay developing the interface COE module due to MOC and delay in hardware rework and CCIS final configuration xii. Delay in Training, Testing and Go Live: Delay due to MCO and COVID19 | 1. Overall completion: Plan = 69%, Actual = 49% 20% Delay due to: a. 3% delay due to MOH Postponement of Kick Off CCIS Project, planned 4/2/2019 actual 12/3/2019 b. 7% delay on Approval Printer Model, impact the Go Live data c. 10% MCO ruling due to Covid19 2. Activity Status: i. Project Management: Plan= 71%, Completed = 68% ii. Site Evaluation: Completed = 100% iii. Infrastructure Implementation: Plan = 100%, Completed = 90% iv. CCIS Software Implementation: Plan = 60%, Completed = 25% v. Integration with SPP: Plan = 50%, Completed = 26% vi. Training & ToT: Plan = 55%, Completed = 20% vii. Change Management & Business Continuity Plan (BCP): Plan = 80%, completed = 85% viii.Business Continuity Plan (BCP): = Plan = 10%, Completed = 10% ix. Benefit Realization Plan (BRP): = Plan = 10%, Completed = 10% x. PAT Go Live: Plan = 11%, Completed = 11% 3. Contract Management: i. Contract with Governement – Completed, signed, stamped and received on 6 Mac 2020. ii.Netlee – Finalized the contract however Netlee request to include RM250k stated in the contract for medical device additional cost. iii.KCSB sub contract completed signed, stamped and received contract on 20/2/2020. 4. Infrastructure & Hardware Delivery i. Infra Delivery and Pending Sign Off: • HPP – Issue on 100ma vs 300ma, propose similar to HRPB electrical layout for UPS installation. • HRPZ – New Jurutera and briefing will be done on 5 and 6 July • PDSA – Confirming on KKM Infra team to perform checking ii. Hardware Delivered and pending DO Sign Off: • HPP to continue delivery of hardware iii. Rework and reinstall required: • Completed for HMLK, HSA, HTAA, HRPZII • Confirmation from HUS and HQEI on entrance / travel policy 5. Hardware & Software Activities i. UPS Servers Status: • Pending at HPP, HRPB and HUS ii. Hardware Delivery Status: • HPP – delay to continue work on 20 July • HTF – to continue work in 13 July • HQE1 and HUS – to reconfirm on entrance / travel policy iii. NetVault Reconfiguration • HTAR – fail and testing is on going • TOT to implementation team to escalate and catch up work iv. License Report: • Delay documentation submission targeted between due to MCO & COVID19 6. Change Management i. HRPB – Delay – waiting feedback on Pengarah availability, target CMA on 15 July 2020 ii. HPP status on CMA: • Pending to obtain sign off due to MCO and COVID19 • Getting assistance from CE to collect the sign off | 1. Overall completion: Plan = 69%, Actual = 49% .: Delay due to a.3% delay due to MOH Postponement of Kick Off CCIS Project, planned 4/2/2019 actual 12/3/2019 b. 7% delay on Approval Printer Model, impact the Go Live data c. 10% MCO ruling due to Covid19 2. Activity Status: i. Project Management: Plan= 71%, Completed = 68% ii. Site Evaluation: Completed = 100% iii. Infrastructure Implementation: Plan = 100%, Completed = 60% iv. CCIS Software Implementation: Plan = 60%, Completed = 25% v. Interfacing Medical Equipment: Plan = 45%, Completed = 22% vi. UAT: Plan = 45%, Completed = 22% vii. Integration with SPP: Plan = 60%, Completed = 26% viii. Training & ToT: Plan = 55%, Completed = 20% 3. Infrastructure & Hardware Delivery i. Infra Delivery and Pending Sign Off: • HPP – Issue on 100ma vs 300ma, propose similar to HRPB electrical layout for UPS installation. • HRPZ – New Jurutera and briefing will be done on 5 and 6 July • PDSA – Confirming on KKM Infra team to perform checking ii. Hardware Delivered and pending DO Sign Off: • HPP to continue delivery of hardware iii. Rework and reinstall required: • Completed for HMLK, HSA, HTAA, HRPZII • Confirmation from HUS and HQEI on entrance / travel policy 4. Hardware & Software Activities i. UPS Servers Status: • Pending at HPP, HRPB and HUS ii. Hardware Delivery Status: • HPP – delay to continue work on 20 July • HTF – to continue work in 13 July • HQE1 and HUS – to reconfirm on entrance / travel policy iii. NetVault Reconfiguration • HTAR – fail and testing is on going • TOT to implementation team to escalate and catch up work iv. License Report: • Delay documentation submission targeted between due to MCO & COVID19 5. Change Management i. HRPB – Delay – waiting feedback on Pengarah availability, target CMA on 15 July 2020 ii. HPP status on CMA: • Pending to obtain sign off due to MCO and COVID19 • Getting assistance from CE to collect the sign off 6. CCIS Implementation i. Delay in CCIS Final Configuration due to MCO and COVID19 for All Hospital Site ii. Review technical configuration for CCIS Data synchronization from PDSA and respective hospitals iii. Delay in testing data synchronization activity iv. Delay in fine tuning CCIS and data configuration v. Delay in training due to non availability of uses 7. CCIS Integration Development i. Catching up on the development work ii. Resources from RIS/PAC and CD team are assigned iii. Weekly meeting updates and issues are discussed iv. Waiting for revised quotation from PhIS CMG team based on discussion on 16 June meeting v. To deploy stand alone CCIS to all 3 integration sites for escalation strategy | 1. Overall completion: Plan = 76%, Actual = 60% .: Delay (16%) due to a.3% delay due to MOH Postponement of Kick Off CCIS Project, planned 4/2/2019 actual 12/3/2019 b. 7% delay on Approval Printer Model, impact the Go Live data c. 10% MCO ruling due to Covid19 2. Activity Status: i. Project Management: Plan= 76%, Completed = 73% ii. Site Evaluation: Completed = 100% iii. Infrastructure Implementation: Plan = 100%, Completed = 94% iv. CCIS Software Implementation: Plan = 89%, Completed = 51% v. Interfacing Medical Equipment: Plan = 85%, Completed = 45% vi. UAT: Plan = 80%, Completed = 49% vii. Integration with SPP: Plan =870%, Completed = 40% viii. Training & ToT: Plan = 90%, Completed = 70% 3. Infrastructure & Hardware Delivery i. Infra Delivery and Pending Sign Off: • HPP – Issue on 100ma vs 300ma, propose similar to HRPB electrical layout for UPS installation. ii. Hardware Delivered and pending DO Sign Off: • HPP to continue delivery of hardware iii. Rework and reinstall required: • Completed for HMLK, HSA, HTAA, HRPZII • Confirmation from HUS and HQEI on entrance / travel policy 4. Hardware & Software Activities i. UPS Servers Status: • Pending at HPP, HRPB,HMLK and HUS due to COVID 19 and SST policy ii. Hardware Delivery Status: • HPP – delay to continue work on 20 July • HTF – to continue work in 13 July • HQE1 and HUS – to reconfirm on entrance / travel policy iii. NetVault Reconfiguration • HTAR – completed on testing environment and on going to other sites iv. License Report: • Delay documentation submission targeted between due to MCO & COVID19 5. Change Management i. HRPB – Delay – waiting feedback on Pengarah availability, target CMA in August 2020 ii. HPP status on CMA: • Pending to obtain sign off due to MCO and COVID19 • Getting assistance from CE to collect the sign off 6. CCIS Implementation i. Delay in CCIS Final Configuration due to MCO and COVID19 for All Hospital Site ii. Review technical configuration for CCIS Data synchronization from PDSA and respective hospitals iii. Delay in testing data synchronization activity iv. Delay in fine tuning CCIS and data configuration v. Delay in training due to non availability of uses 7. CCIS Integration Development i. Catching up on the development work ii. Resources from RIS/PAC and CD team are assigned iii. Weekly meeting updates and issues are discussed iv. To visit HTJS on 8/7/2020 to discuss on integration with current SPP v To propose deploy stand alone CCIS to all 3 integration sites for escalation strategy vi. To deploy stand alone CCIS to all 3 integration sites for escalation strategy | 1. Overall completion: Plan = 76%, Actual = 60% .: Delay (16%) due to a.3% delay due to MOH Postponement of Kick Off CCIS Project, planned 4/2/2019 actual 12/3/2019 b. 7% delay on Approval Printer Model, impact the Go Live data c. 10% MCO ruling due to Covid19 2. Activity Status: i. Project Management: Plan= 76%, Completed = 73% ii. Site Evaluation: Completed = 100% iii. Infrastructure Implementation: Plan = 100%, Completed = 94% iv. CCIS Software Implementation: Plan = 89%, Completed = 51% v. Interfacing Medical Equipment: Plan = 85%, Completed = 45% vi. UAT: Plan = 80%, Completed = 49% vii. Integration with SPP: Plan =870%, Completed = 40% viii. Training & ToT: Plan = 90%, Completed = 70% 3. Infrastructure & Hardware Delivery i. Infra Delivery and Pending Sign Off: • HPP – Issue on 100ma vs 300ma, propose similar to HRPB electrical layout for UPS installation. ii. Hardware Delivered and pending DO Sign Off: • HPP to continue delivery of hardware iii. Rework and reinstall required: • Completed for HMLK, HSA, HTAA, HRPZII • Confirmation from HUS and HQEI on entrance / travel policy 4. Hardware & Software Activities i. UPS Servers Status: • Pending at HPP, HRPB,HMLK and HUS due to COVID 19 and SST policy ii. Hardware Delivery Status: • HPP – delay to continue work on 20 July • HTF – to continue work in 13 July • HQE1 and HUS – to reconfirm on entrance / travel policy iii. NetVault Reconfiguration • HTAR – completed on testing environment and on going to other sites iv. License Report: • Delay documentation submission targeted between due to MCO & COVID19 5. Change Management i. HRPB – Delay – waiting feedback on Pengarah availability, target CMA in August 2020 ii. HPP status on CMA: • Pending to obtain sign off due to MCO and COVID19 • Getting assistance from CE to collect the sign off 6. CCIS Implementation i. Delay in CCIS Final Configuration due to MCO and COVID19 for All Hospital Site ii. Review technical configuration for CCIS Data synchronization from PDSA and respective hospitals iii. Delay in testing data synchronization activity iv. Delay in fine tuning CCIS and data configuration v. Delay in training due to non availability of uses 7. CCIS Integration Development i. Catching up on the development work ii. Resources from RIS/PAC and CD team are assigned iii. Weekly meeting updates and issues are discussed iv. To visit HTJS on 8/7/2020 to discuss on integration with current SPP v To propose deploy stand alone CCIS to all 3 integration sites for escalation strategy vi. To deploy stand alone CCIS to all 3 integration sites for escalation strategy | 87% (August 2020=87%) (July 2020 = 85%) (June 2020=92%) (May 2020=92%) (April 2020=92%) (March 2020 = 92%) (February 2020=92%) (January 2020 =91%) (December 2019 = 82%) (November 2019 = 91%) (October 2019 = 91%) (September 2019 = 91%)
2 | MOH | Clinical Documentation | 30101218.92 | 21/3/2016 | 20/3/2020 extension (21/3/2020 to 20/9/2021) | 1. 2 years Development of CD module with 11 Disciplines 2. Enrichment of SPP via identified CR 3. Develop Application Programming Interface 4. Develop Mobile Version of SPP & CD 5. Verification & Validation services by 3rd party entity 6. Data Migration of Existing SPP at HRPB 7. Integration to 9 identified systems 8. Integration to 16 types of medical equipment at 24 identified location with a total of 50 units 9. Delivery & Installation of Hardware & Software 10. 1 year Pilot implementation at HRPB 11. Benefit Realization 12. Change Management 13. Training & ToT 14. Helpdesk, Operation & Technical Support | Norli Masri | Ahmad Zamin Mahadzir/Sukiman Johari Abdul Manan | Noor Aini, Nur Syuhadah, Rozaimi | Development | 1. (PSC 3/2020)- Due to the delay in PAT Go-Live, additional resources are needed to expedite and complete all the deliverables as per contract.. Some of the extra resources requested have joined the team. To follow up status with HR of other resources required. As of 11/12/2019, the resource strength for CD Project is 113 (excluding part time & interns) -. EOT for the duration of 18 months approved during Mesyuarat JK Pemandu Bil 1/2020 dated 20/02/2020. However, resources still needed to complete the pending activities & deliverables SJAM will discuss with COO on the resource planning during the EOT(in progress) 2. (PSC 6/2020) - Extra resources to expedite and complete the delayed deliverables. Due to the delay in PAT Go-Live, additional resources are needed to expedite and complete all the deliverables as per contract. a. Some of the extra resources requested have joined the team. To follow up status with HR of other resources required. b. As of 11/12/2019, the resource strength for CD Project is 113 (excluding part time & interns) c. EOT for the duration of 18 months approved during Mesyuarat JK Pemandu Bil 1/2020 dated 20/02/2020. However, resources still needed to complete the pending activities & deliverables. SJAM will discuss with COO on the resource planning during the ( open) 3. (PSC 6/ 2020) - Extra cost required to complete the project. Due to the delay in PAT Go-Live, additional cost is needed to cover the expenses for the time and resources acquired a. EOT for the duration of 18 months approved during Mesyuarat JK Pemandu Bil 1/2020 dated 20/02/2020. However, resources still needed to complete the pending activities & deliverables, which will incur extra cost during the extension. PSC 2/2020 15/10/2020 SJAM will discuss with COO on the resource planning during the EOT (open) 4. (PSC 6/ 2020) Due to the delay of HIS@KKM EMR Basic, and not meeting the 25/10/2019 date, LAD is already imposed at RM3000+ per day. Extra cost is needed to cover LAD. a. EOT for the duration of 18 months approved during Mesyuarat JK Pemandu Bil 1/2020 dated 20/02/2020. However, resources still needed to complete the pending activities & deliverables, which will incur extra cost during the extension. b. EOT approved with LAD. (open) 5. (PSC 6/2020) - Isu functional yang direkodkan dalam log isu. a. Pihak HTP perlu menganalisa setiap isu functional yang direkodkan dan mencari root cause dan permanent solution perlu dikenalpasti dan dilaksanakan untuk mengelakkan isu daripada berulang. b. Isu yang berulang akan mengganggu kelancaran fungsi aplikasi dan kelancaran operasi hospital. (open) 6. (PSC 6/2020)- To request for extension of FAT date due to MCO Because of the MCO, PAT Go-Live planned to complete by 30 April 2020, has to be rescheduled as follows: Group #4 – 13/06/2020 Group #5 – 27/06/2020 Group #6 – 11/07/2020 For that reason, PAT Sign-off is expected to complete by 12 Aug 2020, hence leaving FAT ONLY approx. 1 month to complete from the earlier 4 months. PSC 2/2020 15/10/2020 The team had requested an EOT for 71 days until 30/11/2020(open) : | 26191691.74 | 3909527.18 | 26191691.74 | 30224942.1505 | No report submission for month of December 2019 | 1. Overall completion: Plan = 99%; Actual = 92% (Revised timeline # 2) 2. Application Development progress: - System Requirement & Design – 100% - Programming (coding) – 98% - Quality Assurance – 96%; Independent Verification Validation Testing – 88% - UAT – 77% 3. Pilot Implementation: - Hardware/Software/Infra Setup – 100% - Training – 76% - Data Migration – 100% - Change Management – 100%; Benefit Realisation – 100% 4.Proposal news date Implementation - User Acceptance Test: 18/9/2019-13/12/2019 - User Manual: 2/10/2019-20/12/2019 - System Go Live/PAT: i) EMR Basic: 23/11/2019 – 26/1/2020 ii) EMR Plus: 14/12/2019 – 26/12/2019 - FAT: 27/12/2019 – 26/22/2020 - Warranty Period: 26/2/2020 – 27/2/2021 PAT Go-Live Issues Log = Helpdesk 1,234, Close = 1180, Duplicate = 17, Verified HTP = 153, Closed (Users) = 1010, Progress =17 | 1. Overall completion: Plan = 99%; Actual = 92% (Revised timeline # 2) 2. Application Development progress: - System Requirement & Design – 100% - Programming (coding) – 100% - Quality Assurance – 100%; Independent Verification Validation Testing – 100% - UAT – 100% 3. Pilot Implementation: - Hardware/Software/Infra Setup – 100% - Training & Transfer of Technology – 99% - Data Migration (from SPPv3.5%)– 100% - Change Management – 100%; Benefit Realisation – 80% 4.Proposal news date Implementation - User Acceptance Test: 18/9/2019-31/3/2020 - User Manual: 2/10/2019-29/5/2020 - PAT & FAT: i) EMR Basic: 23/11/19 ii) EMR Plus: #1- 15/2/2020, #2-29/2/2020, #3-9/3/2020, #4-3/4/2020, #5-18/4/2020, #6- 30/4/2020 - FAT: 21/5/2020 – 20/9/2020 - Warranty Period: 21/9/2020 – 20/9/2021 5. PAT Go-Live Issues Log = Helpdesk 1,386, Close = 1414, Duplicate = 17, Verified HTP = 64, Closed (Users) = 10325, Progress =52 - All issues must be verified/ closed before FAT starts. 6. CD Project EOT Application; 21/3/2020 – 20/9/2021 for the duration of 18 month including 12 months warranty. | Overall completion: Plan = 87%; Actual = 87% (Revised timeline # 3) 1. Application Development progress: - System Requirement & Design – 100% - Programming (coding) – 94% - Quality Assurance – 93%; Independent Verification Validation Testing – 93% - UAT – 87% - Training - 68% - Provisional Acceptance Test - 69% 2.Proposal news date Implementation - User Acceptance Test: 18/9/2019-31/3/2020 - User Manual: 2/10/2019-29/5/2020 - PAT & FAT: i) EMR Basic: 23/11/19 ii) EMR Plus: #1- 15/2/2020, #2-29/2/2020, #3-9/3/2020, #4-3/4/2020, #5-18/4/2020, #6- 30/4/2020 - FAT: 21/5/2020 – 20/9/2020 - Warranty Period: 21/9/2020 – 20/9/2021 3. PAT Go-Live Issues Log by March = Total = 131, Closed = 94, Open = 24, Verified = 13 - All issues must be verified/ closed before FAT starts. 4. Received SST on 13 March 2020 for the extension; 21/3/2020 – 20/9/2021 for the duration of 18 month including 12 months warranty. | Overall completion: Plan = 88%; Actual = 88% (Revised timeline # 3) 1. Application Development progress: - System Requirement & Design – 100% - Programming (coding) – 95% - Quality Assurance – 96%; Independent Verification Validation Testing – 90% - UAT – 87% - Training - 72% - Provisional Acceptance Test - 69% 2.Proposal new date Implementation - User Acceptance Test: 18/9/2019-24/6/2020 - User Manual: 2/10/2019-29/5/2020 - PAT & FAT: i) EMR Basic: 23/11/19 ii) EMR Plus: #1- 15/2/2020, #2-29/2/2020, #3-9/3/2020, Remaining implementation phases will be in stages, - FAT: 1/7/2020 – 20/9/2020 - Warranty Period: 21/9/2020 – 24/8/2021 3. PAT Go-Live Issues Log by April = Total = 87, Closed = 75, Open = 6, Verified = 0 - All issues must be verified/ closed before FAT starts. 4. Received SST on 13 March 2020 for the extension; 21/3/2020 – 20/9/2021 for the duration of 18 month including 12 months warranty. | Overall completion: Plan = 90%; Actual = 90% (Revised timeline # 3) 1. Application Development progress; - Coding – 99% - Internal Quality Assurance – 97% - Independent Verification & Validation – 94% - User Acceptance Test – 90% - Training – 75% - Provisional Acceptance Test – 75% 2. Received SST on 13 March 2020 for the extension; 21/3/2020 – 20/9/2021 for the duration of 18 month including 12 months warranty. 3. The project team is in the process of implementing the following activities: i. Support & Monitoring Post PAT Go-Live for HIS@KKM EMR Basic & EMR Plus in HRPB • Helpdesk Support • On Call Technical Support • Problem Resolution • Close Issue Log PAT Go-Live HIS@KKM EMR Basic & EMR Plus ii. UAT for HIS @ KKM EMR Plus is being implemented online iii. Preparation of HIS @ KKM EMR Plus for implementation iv. Preparation of HIS @ KKM EMR Plus for training user setup 4. Provisional Acceptance Test (PAT) PAT Go Live HIS@KKM EMR Basic; 23/11/2019 PAT Go Live HIS@KKM EMR Plus have been implemented • Group 1; 15/2/2020 • Group 2; 29/2/2020 • Group 3; 9/3/2020 PAT Go Live HIS@KKM EMR Plus to be scheduled • Group 4; 12/6/2020 • Group 5; 26/6/2020 • Group 6; 10/7/2020 FAT: 21/5/2020 – 20/9/2020 Warranty Period: 21/9/2020 – 20/9/2021 5. PAT Go-Live Issues Log = Helpdesk 1,699, Close = 1631, Duplicate = 21, Verified HTP = 31, Closed (Users) = 1596, Progress = 4, Total New Request = 47 | Overall completion: Plan = 92%; Actual = 92% (Revised timeline # 3) 1. Application Development progress; - Coding – 99% - Internal Quality Assurance – 99% - Independent Verification & Validation – 98% - User Acceptance Test – 96% - Training – 89% - Provisional Acceptance Test – 85% 2. Received SST on 13 March 2020 for the extension; 21/3/2020 – 20/9/2021 for the duration of 18 month including 12 months warranty. 3. The project team is in the process of implementing the following+W20 activities: i. Support & Monitoring Post PAT Go-Live for HIS@KKM EMR Basic & EMR Plus in HRPB • Helpdesk Support • On Call Technical Support • Problem Resolution • Close Issue Log PAT Go-Live HIS@KKM EMR Basic & EMR Plus ii. UAT for HIS @ KKM EMR Plus is being implemented online iii. Preparation of HIS @ KKM EMR Plus for implementation iv. Preparation of HIS @ KKM EMR Plus for training user setup 4. Provisional Acceptance Test (PAT) PAT Go Live HIS@KKM EMR Basic; 23/11/2019 PAT Go Live HIS@KKM EMR Plus have been implemented • Group 1; 15/2/2020 • Group 2; 29/2/2020 • Group 3; 9/3/2020 • Group 4; 13/6/2020 • Group 5; 27/6/2020 PAT Go Live HIS@KKM EMR Plus to be scheduled • Group 6; 11/7/2020 5. PAT Go Live HIS@KKM EMR Plus to be scheduled due to MCO. FAT: 21/5/2020 – 20/9/2020 Warranty Period: 21/9/2020 – 20/9/2021 6. Basic Issues Log PAT Go-Live Issues Log = Helpdesk 1,826, Close = 1750, Duplicate = 21, Verified HTP = 66, Closed (Users) = 1657, Progress = 27, Total New Request = 55 7. Issues Log (Group #1,#2, #3,#4,#5) PAT Go-Live Issues Log = Helpdesk 193, Close = 165, Duplicate = 0, Verified HTP = 47, Closed (Users) = 165, Progress = 15, Total New Request = 28 8. Supplementary Agreement #4-EOT – As at 30 June 2020, the agreement is still with PUU, KKM. 9. The project team has requested budget during EOT (March 2020 until Sept 2021) estimated at RM5,830,180.00. Detail of the request has been shared with Finance (Jasina) since 19 March 2020. As of to date there is no feedback from Finance. | Overall completion: Plan = 93%; Actual = 92% (Revised timeline # 3) 1. Application Development progress; - Coding – 99% - Internal Quality Assurance – 99% - Independent Verification & Validation – 98% - User Acceptance Test – 99% - Training – 91% - Provisional Acceptance Test Go-Live – 98% - Provisional Acceptance Sign-0ff – 45% 2. Received SST on 13 March 2020 for the extension; 21/3/2020 – 20/9/2021 for the duration of 18 month including 12 months warranty. 3. The project team is in the process of implementing the following activities: i. Support & Monitoring Post PAT Go-Live for HIS@KKM EMR Basic & EMR Plus in HRPB • Helpdesk Support • On Call Technical Support • Problem Resolution • Close Issue Log PAT Go-Live HIS@KKM EMR Basic & EMR Plus ii. Preparation for training transfer of Technology and Train the Trainer HIS@KKM EMR iii. PAT & FAT Sign-off for HIS@KKM EMR 4. PAT Go Live HIS@KKM EMR Plus have been implemented • Group 1; 15/2/2020 • Group 2; 29/2/2020 • Group 3; 9/3/2020 • Group 4; 13/6/2020 • Group 5; 27/6/2020 • Group 6; 11/07/2020 5. Component / Module / Discipline that is still pending: • PAT Go-Live PMS API • PAT Go-Live Oral Health Dental Charting • PAT Go-Live System Integration MyHIX • PAT Go-Live System Integration eNotifikasi 6. PAT Go-Live Issues Log for Basic = Helpdesk 1,945, Close = 1860, Duplicate = 29, Verified HTP = 72, Closed (Users) = 1774, Progress = 14, Total New Request = 56 7. PAT Go-Live Issues Log for Plus = Helpdesk 263, Close = 222, Duplicate = 2, Verified HTP = 73, Closed (Users) = 113, Progress = 36, Total New Request = 39 | Overall completion: Plan = 94%; Actual = 93% (Revised timeline # 3) 1. Application Development progress; - Coding – 99% - Internal Quality Assurance – 99% - Independent Verification & Validation – 98% - User Acceptance Test – 98% - Training – 98% - Provisional Acceptance Test Go-Live – 98% - Provisional Acceptance Sign-0ff – 93% 2. Received SST on 13 March 2020 for the extension; 21/3/2020 – 20/9/2021 for the duration of 18 month including 12 months warranty. 3. The project team is in the process of implementing the following activities: i. Support & Monitoring Post PAT Go-Live for HIS@KKM EMR Basic & EMR Plus in HRPB • Helpdesk Support • On Call Technical Support • Problem Resolution • Close Issue Log PAT Go-Live HIS@KKM EMR Basic & EMR Plus ii. Preparation for training transfer of Technology and Train the Trainer HIS@KKM EMR iii. PAT & FAT Sign-off for HIS@KKM EMR 4. PAT Go Live HIS@KKM EMR Plus have been implemented • Group 1; 15/2/2020 • Group 2; 29/2/2020 • Group 3; 9/3/2020 • Group 4; 13/6/2020 • Group 5; 27/6/2020 -pending System Integration E-SMRP • Group 6; 11/07/2020 pending System Integration myHIX and API Online 5. Component / Module / Discipline that is still pending: • PAT Go-Live PMS API • PAT Go-Live System Integration MyHIX • PAT Go-Live System IntegrationE-SMRP 6. PAT Go-Live Issues Log for Basic = Helpdesk 2,112 Close = 1,996, Duplicate = 33, Verified HTP = 85, Closed (Users) = 1900, Progress = 11, Total New Request = 83 7. PAT Go-Live Issues Log for Plus = Helpdesk 397, Close = 345, Duplicate = 0, Verified HTP = 166, Closed (Users) = 163, Progress = 16, Total New Request = 52 | Overall completion: Plan = 94%; Actual = 93% (Revised timeline # 3) 1. Application Development progress; - Coding – 99% - Internal Quality Assurance – 99% - Independent Verification & Validation – 99% - User Acceptance Test – 98% - Training – 98% - Provisional Acceptance Test Go-Live – 99% - Provisional Acceptance Sign-0ff – 90% 2. Received SST on 13 March 2020 for the extension; 21/3/2020 – 20/9/2021 for the duration of 18 month including 12 months warranty. 3. The project team is in the process of implementing the following activities: i. Support & Monitoring Post PAT Go-Live for HIS@KKM EMR Basic & EMR Plus in HRPB • Helpdesk Support • On Call Technical Support • Problem Resolution • Close Issue Log PAT Go-Live HIS@KKM EMR Basic & EMR Plus ii. Preparation for training transfer of Technology and Train the Trainer HIS@KKM EMR iii. PAT & FAT Sign-off for HIS@KKM EMR 4. PAT Go Live HIS@KKM EMR Plus have been implemented • Group 1; 15/2/2020 • Group 2; 29/2/2020 • Group 3; 9/3/2020 • Group 4; 13/6/2020 • Group 5; 27/6/2020 -pending System Integration E-SMRP • Group 6; 11/07/2020 pending System Integration myHIX and API Online 5. Component / Module / Discipline that is still pending: • PAT Go-Live PMS API • PAT Go-Live System Integration MyHIX • PAT Go-Live System IntegrationE-SMRP 6. PAT Go-Live Issues Log for Basic = Helpdesk 2,112 Close = 1,996, Duplicate = 33, Verified HTP = 85, Closed (Users) = 1900, Progress = 11, Total New Request = 83 7. PAT Go-Live Issues Log for Plus = Helpdesk 397, Close = 345, Duplicate = 0, Verified HTP = 166, Closed (Users) = 163, Progress = 16, Total New Request = 52 | 87% (August 2020=87%) (July 2020 =86%) (June 2029= 93%) (May 2020= 93%) (April 2020 =93% (March 2020 = 93%) (February 2020=93%) (January 2020 =93%) (December 2019 =93%) (November 2019 = 93%) (October 2019 = 93%) (September 2019 = 85%) (August 2019 = 92%)
3 | MOH | RIS PACS HIS@KKM Fasa I | 10090979.26 | 2017-07-17 | 2020-01-16 | 1. Enhance& Implement RIS Module 2. Delivery & Installation of Picture Archiving Communication System (PACS) 3. Integration of Modalities, PACS and SPP RIS 4. Migration of Data & Mini PACS 5. Delivery & Installation of Hardware & Software 6. Installation of LAN/Fiber Optice cabling and upgrade Network Infrastructure 7. Installation of Electrical switch socket outlet and distribution board 8.Testing, UAT, PAT and FAT 9. Change Management and Benefit Realisation 10. Training & Transfer of Technology 11. Helpdesk ( i-DESK) 12. Implementation and Warranty Support at HRPZII will commence after 19/8/2019 (FAT date). | Suradi Abdul Rahman (Norashikin Bt Baharudin) | Ahmad Zamin Mahadzir/ Sukiman Johari Abdul Manan | Hamid Baharudin | Development | 1. (PSC 8/2019) Cabling at HRPZ was not properly arrange and the cable rack door couldn't be closed. HRPZ requested for the cable to be arranged properly. Project Team need to get new contractor to execute the exercise since the previous contractor is no longer available. (PSC 3/2020)- Re arrangement work will be carried out once obtaining endorsement from HMS infrastructure team (open) (PSC 5/2020)- (open) (PSC 6/2020)- (closed) 2. PSC 1/2020) KKM requested HTP to complete all development work during warranty period to be completed before Ju. Fyafiq HTP wil evaluate and realign all development work (PSC 3/20-20)- HTP have presented the reproposed schedule to KKM however it will slightly delay to early July to complete all deliverables (open) | 7455217.95 | 2635761.31 | 7455217.95 | 9498364.4757 | 1. Overall status completion: Plan = 100%. Actual = 91% 2. Application Development status: overall status 100% - SDD 100% - Database design completed 100% - Coding & Unit test completed 100% - UAT completed 100% - Change Management completed 80% - Benefits Realisation 90% - Training completed 100% - PAT completed 100% - FAT completed 100% - Warranty & Support completed 8% 3. Activities in warranty & support period: - Auto Login completed 100%, completed on 21/12/2019 - SMRP completed 29%, target completion 24/1/2020 - RFR completed 6%, target completion 7/5/2020 - Forensic completed 22%, target completion 9/7/2020 - Stand Alone not started 0%; target completion 21/8/2020 | 1. Overall status completion: Plan = 100%. Actual = 93% 2. Application Development status: overall status 100% - SDD 100% - Database design completed 100% - Coding & Unit test completed 100% - UAT completed 100% - Change Management completed 80% - Training completed 100% - PAT completed 100% - FAT completed 100% 3. Warranty Support status: Plan = 17%, Actual = 17% - Warranty Support 21% - Change Management 100% - Benefit Realization (Post Go Live Study) 0% - Reinforcement Training & TOT 37% 4. Warranty & Support Services - Auto Login = 100% - SMRP = 50% - TOT = 75% - Reinforcement = 0% - RFR = 50% - Forensic = 22% - Stand Alone = 0% 5. Summary Issue logs: Open 1, Resolution = 17, Closed = 113, Total 131 Total logs by category: Hardware = 9, Application = 122 Log Issue by Month: November 2019 = 48, December 2019 = 59, January 2020 = 24 | 1. Overall status completion: Plan = 100%. Actual = 97% 2. Application Development status: overall status 100% - SDD 100% - Database design completed 100% - Coding & Unit test completed 100% - UAT completed 100% - Change Management completed 80% - Training completed 100% - PAT completed 100% - FAT completed 100% 3. Warranty Support status: Plan = 33%, Actual = 33% - Warranty Support 33% - Change Management 100% - Benefit Realization (Post Go Live Study) 0% - Reinforcement Training & TOT 100% 4. Warranty & Support Services - Auto Login = 100% - SMRP = 100% - TOT = 100% - Reinforcement = 100% - RFR = 80% - Forensic = 36% - Stand Alone = 0% 5. Summary Issue logs: Open 1, Resolution = 17, Closed = 113, Total 131 Total logs by category: Hardware = 9, Application = 122 Log Issue by Month: November 2019 = 48, December 2019 = 59, January 2020 = 24 | Overall status completion: Plan = 100%. Actual = 97% 1. Warranty & Support : Plan 42 % Actual 42 % Change Management:Plan 100 % Actual 100 % Benefit Realization (Post Go Live Study):Plan 0 % Actual 0 % Reinforcement Training & TOT:Plan 100 % Actual 100 % 2. Application Development status: overall status 100% - SDD 100% - Database design completed 100% - Coding & Unit test completed 100% - UAT completed 100% - Change Management completed 80% - Training completed 100% - PAT completed 100% - FAT completed 100% Warranty & Support Services Overall completion: Plan = 42%; Actual = 42% Status Activities in the warranty - Training (Reinforcement Session) = 100% - Training (TOT Session) = 100% - Auto Login = 100% - SMRP= 100% - RFR= 75% - Forensic= Actual 35% - Stand Alone= 0% Summary Issue logs: Open 1, Resolution = 17, Closed = 113, Total 131 Total logs by category: Hardware = 9, Application = 122 Log Issue by Month: November 2019 = 48, December 2019 = 59, January 2020 = 24 | Overall status completion: Plan = 100%. Actual = 97% 1. Warranty & Support: Plan 42 % Actual 42 % Change Management: Plan 100 % Actual 100 % Benefit Realization (Post Go Live Study):Plan 0 % Actual 0 % Reinforcement Training & TOT:Plan 100 % Actual 100 % 2. Application Development status: overall status 100% - SDD 100% - Database design completed 100% - Coding & Unit test completed 100% - UAT completed 100% - Change Management completed 80% - Training completed 100% - PAT completed 100% - FAT completed 100% Warranty & Support Services Overall completion: Plan = 42%; Actual = 42% Status Activities in the warranty - Training (Reinforcement Session) = 100% - Training (TOT Session) = 100% - Auto Login = 100% - SMRP= 100% - RFR= 75% - Forensic= Actual 35% - Stand Alone= 0% Summary Logs Issue for April: Total = 4, Open 0, Resolution 0, Closed 0 Total logs by category: Hardware = 1, Application = 3 Log Issue by Month: November 2019 = 48, December 2019 = 59, January 2020 = 24, February 2020 = 33, March 2020 = 15, April 2020 = 4 | Overall status completion: Plan = 100%. Actual = 97% 1. Warranty & Support: Plan 59 % Actual 59 % Change Management: Plan 100 % Actual 100 % Benefit Realization (Post Go Live Study):Plan 100 % Actual 0 % Reinforcement Training & TOT:Plan 100 % Actual 100 % 2. Application Development status: overall status 100% - SDD 100% - Database design completed 100% - Coding & Unit test completed 100% - UAT completed 100% - Change Management completed 100% - Training completed 100% - PAT completed 100% - FAT completed 100% Warrantty Nov 2019-Nov 2020 Overall completion: Plan = 100%; Actual = 100% RFR Plan 100%, Actual =100% FORENSIC Plan 60%, Actual =46% STAND ALONE Plan 0%, Actual =0% Status Activities in the warranty - Training (Reinforcement Session) = 100% - Training (TOT Session) = 100% - Auto Login = 100% - SMRP= 100% - RFR= 100% - Forensic= Actual 46% - Stand Alone= 0% (developed outside of the project). As per discussion with KKM on 2/6/2020 Summary Logs Issue for May: Total = 18, Open 0, Resolution 0, Closed 18. Total logs by category: Hardware = 5, Application = 12 Log Issue by Month: November 2019 = 48, December 2019 = 59, January 2020 = 24, February 2020 = 33, March 2020 = 15, April 2020 = 4, May = 18. | Overall status completion: Plan = 100%. Actual = 98% 1. Warranty & Support: Plan 67 % Actual 67 % Change Management: Plan 100 % Actual 100 % Benefit Realization (Post Go Live Study): Plan 0 % Actual 0 % Reinforcement Training & TOT: Plan 100 % Actual 100 % 2. Application Development status: overall status 100% - SDD 100% - Database design completed 100% - Coding & Unit test completed 100% - UAT completed 100% - Change Management completed 80% - Training completed 100% - PAT completed 100% - FAT completed 100% Warrantty Nov 2019-Nov 2020 Overall completion: Plan = 100%; Actual = 100% Status Activities in the warranty - Training (Reinforcement Session) = 100% - Training (TOT Session) = 100% - Auto Login = 100% - SMRP= 100% - RFR= 100% - Forensic= Actual 87% - Stand Alone= 0% (developed outside of the project). As per discussion with KKM on 2/6/2020. (Stand Alone will be developed during warranty period of CD project) Summary Logs Issue for May: Total = 18, Open 0, Resolution 0, Closed 18. Total logs by category: Hardware = 5, Application = 12, Other = 1 Log Issue by Month: November 2019 = 48, December 2019 = 59, January 2020 = 24, February 2020 = 33, March 2020 = 15, April 2020 = 4, May = 18. | Overall status completion: Plan = 100%. Actual = 99% 1. Warranty & Support: Plan 67 % Actual 67 % 2.Benefit Realization (Post Go Live Study): Plan 100 % Actual 33 % 2. Application Development status: overall status 100% - SRS completed 100% - SDD completed 100% - Database design completed 100% - Development completed 100% - PASC Installation completed 100% - UAT completed 100% - PAT completed 100% - FAT completed 100% - Change Management completed 80% Warrantty Nov 2019-Nov 2020 Overall completion: Plan = 67%; Actual = 67% Status Activities in the warranty i. Training (Reinforcement Session) = 100% ii. Training (TOT Session) = 100% iii. Auto Login = 100% iv. SMRP= 100% v. RFR= 100% vi. Forensic= 100% vii. Stand Alone= 0% (Testing will be done during CD project warranty period using Lab approach) | Overall status completion: Plan = 100%. Actual = 100% 1. Warranty & Support: Plan 92 % Actual 92 % 2.Benefit Realization (Post Go Live Study): Plan 100 % Actual 33 % 2. Application Development status: overall status 100% - SRS completed 100% - SDD completed 100% - Database design completed 100% - Development completed 100% - PASC Installation completed 100% - UAT completed 100% - PAT completed 100% - FAT completed 100% - Change Management completed 100% Warrantty Nov 2019-Nov 2020 Overall completion: Plan = 92%; Actual = 92% Status Activities in the warranty i. Training (Reinforcement Session) = 100% ii. Training (TOT Session) = 100% iii. Auto Login = 100% iv. SMRP= 100% v. RFR= 100% vi. Forensic= 100% vii. Stand Alone= 0% (Testing will be done during CD project warranty period using Lab approach) | Overall status completion: Plan = 100%. Actual = 99% 1.Benefit Realization (Post Go Live Study): Plan 100 % Actual 33 % 2. Application Development status: overall status 100% - SRS completed 100% - SDD completed 100% - Database design completed 100% - Development completed 100% - PACS Installation completed 100% - UAT completed 100% - PAT completed 100% - FAT completed 100% - Change Management completed 100% Warrantty Nov 2019-Nov 2020 Overall completion: Plan = 92%; Actual = 92% Status Activities in the warranty i. Training (Reinforcement Session) = 100% ii. Training (TOT Session) = 100% iii. Auto Login = 100% iv. SMRP= 100% v. RFR= 100% vi. Forensic= 100% vii. Stand Alone= 0% (Testing will be done during CD project warranty period using Lab approach) | 73% (August 2020=67%) (July 2020 =62%) (June 2020 = 62%) (May 2020 =62%) (April 2020=62%) (March 2020 = 62%) (February 2020=62%) (January 2020=55%) (December 2019 =55%) (November 2019 = 55%) (October 2019 = 60%) (September 2019 = 50%) (August 2019 = 64%)
4 | MOH | Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu 01 Oct 2019 - 31 Dec 2019 (3 mths) | 226639 | 2019-10-01 | 2019-12-31 | Perkhidmatan Penyelenggaran Dan Sokongan Operasi Bagi Perkakasan, Perisian, Aplikasi Dan Rangkaian Untuk Sistem Pengurusan Pesakit (SPP) di Hospital Raja Perempuan Zainab II Kota Bharu Bagi Tempoh 3 Bulan | Suradi Abdul Rahman | Ahmad Zamin Mahadzir/ Sukiman Johari Abdul Manan | Hamid Baharudin | Maintenance | No open or new issues | 204518.57 | 22120.43 | 204518.57 | 273545.9502 | - Project Team in process of compiling report for December 2019. - Project closing will be on 16/1/2020. | Overall completion: Plan = 100%; Actual = 100% Corrective maintenance done, CM Report for month three completed on 16/01/2020. Project closing will be on 16/1/2020. | NA | NA | NA | NA | NA closed | NA closed | NA closed |  | NA
5 | MOH | VO RIS PACS HIS@KKM Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu 01 Nov 2019 - 28 Feb 2020 (4 mths) | 496000 | 2019-11-01 | 2020-09-30 | Perolehan Peralatan, Aksesori Rangkaian, Perkhidmatan Integrasi Modaliti Tambahan Dan Deployment Laporan SS RA1019 bagi Projeck RISPACS di Hospital Raja Perempuan Zainab II Kota Bharu | Suradi Abdul Rahman | Ahmad Zamin Mahadzir/ Sukiman Johari Abdul Manan | Hamid Baharudin | Implementation | No open or new issues | 0 | 496000 | 0 | 348115.84 | - Hardware procurement and deployment is in progress. Target completion by 29/2/2020 - Infrastructure and LAN cabling work has completed on 25/12/2019 | Status i. Procurement - Additional Hardware (In progress) ii. Network Accessoties Installation( In progress ) iii. Perkhidmatan Integrasi 3 Modaliti Tambahan & Deployment Laporan SS RA 1019;( In progress) | Status i. Server and firewall hardware were delivered and istalled at HRPZ ON 15/1/2020 AND 13/2/2020 respectively. ii. Wireless - PO has not been issued yet iii. Other equipments - POs wre issued but delivery cannot been done. due to payment issue. PM to issue memo to finance | Status 1. Server and firewall hardware were delivered and istalled at HRPZ ON 15/1/2020 and 13/2/2020 respectively. 2. Wireless - PO has not been issued yet 3. Other equipments - POs wre issued but delivery cannot been done. due to payment issue. PM to issue memo to finance | 1. Server and firewall hardware were delivered and istalled at HRPZ ON 15/1/2020 and 13/2/2020 respectively. 2. Wireless - PO has not been issued yet 3. Other equipments - POs wre issued but delivery cannot been done. due to payment issue. PM to issue memo to finance | i. Server and firewall hardware were delivered and installed at HRPZ ON 15/1/2020 and 13/2/2020 respectively. ii. UPS 10 KVA - waiting for delivery to HTPZII iii. Firewall - has been installed on HRPZII on February 12, 2020 iv. Wireless Access Point - PO has not been issued yet v. Other equipments (Scanner, Firewall, 2MP Colour Medical Grade and Computer w/o monitor)- Procurement process in progress vi Fiber Patch Cord = installed at HRPZII on 20 Dec 2019 vii Transceiver - Procurement process in progress viii Fiber patcgh panel 6 core - installed at HRPZII on 20 Dec 2019 | i. Server and firewall hardware were delivered and installed at HRPZ ON 15/1/2020 and 13/2/2020 respectively. ii. UPS 10 KVA - awaiting delivery instruction to HRPZII iii. Computer w/o Monitor - awaiting delivery instruction to HRPZII iv. Wireless Access Point - awaiting delivery instruction to HRPZI v. 2MP Colour Medical Grade - sent to HRPZII on 23/6/2020 vi Scanner - awaiting delivery instruction to HRPZII vii. Fiber Patch Cord ( 5m & 10m) - has been installed at HRPZII on 20/12/2019 viii. Transceiver Multimode and Fiber Cable Multimode outdoor (250m) - awaiting delivery instruction to HRPZI ix. Fiber patch panel 6 core - awaiting delivery instruction to HRPZII STATUS INTEGRASI MODALITI I. Perkhidmatan Integrasi 3 Modaliti Tambahan - Toshiba C-Arm (II) Toshiba SXT-2000A - work completed 18/5/2020 - Philips C-Arm Philips BV Endura- work completed 21/6/2020 - Siemens C-Arm Arcadis Varic - work completed 28/5/2020 2. Deployment SS RA101 bagi Integrasi SPP & RIS dengan eSMRP - will present to KKM on 16/7/2020 | No status updated & slide | 1. Server – Lenovo Think System SR650 (4 unit) - Kerja-kerja aktiviti TnC sehingga 20 - 30 September 2020 2. UPS 10 KVA (1 unit) - Pendawaian tambahan pada 24 September dan jangkaan pemasangan pada 25 September 2020 . 3. omputer Tanpa Monitor (5 unit) 4. 2MP Colour Medical Grade (5 unit) 5. Scanner (1) - Kerja-kerja aktiviti TnC sehingga 20 - 30 September 2020 6. Firewall (1) 7.Wireless Access Point (1) 8. Fiber Patch Cord LC-LC (5m) 9. Fiber Patch Cord SC-LC (10m) 10. Transceiver Multimode (MM) 1G 11. Transceiver Multimode (MM) 10G - Kerja-kerja aktiviti TnC sehingga 20 - 30 September 2020. 12. Fiber Cable Multimode outdoor (250 meter) 13. Fiber patch panel 6 core 14. Supply and lay cable optic 15. Splicing and termination 12 core 16. Perkhidmatan Integrasi 3 Modaliti Tambah Toshiba C-Arm (II) Toshiba SXT-2000A- Kerja sudah dilakukan dan selesai pada 18hb Mei 2020 Philips C-Arm Philips BV Endura - Kerja sudah dilakukan dan selesai pada 21hb Jun 2020 Siemens C-Arm Arcadis Varic - Kerja sudah dilakukan dan selesai pada 28hb Mei 2020 17. Deployment Laporan SS RA RA101 - enunggu pengesahan pihak PIK KKM sebelum di buat deployment - - 12. | 1. Server – Lenovo Think System SR650 (4 unit) - Kerja-kerja aktiviti TnC sehingga 20 - 30 September 2020 2. UPS 10 KVA (1 unit) - Pendawaian tambahan pada 24 September dan jangkaan pemasangan pada 25 September 2020 . 3. Komputer Tanpa Monitor (5 unit) 4. 2MP Colour Medical Grade (5 unit) 5. Scanner (1) - Kerja-kerja aktiviti TnC sehingga 20 - 30 September 2020 6. Firewall (1) 7.Wireless Access Point (1) 8. Fiber Patch Cord LC-LC (5m) 9. Fiber Patch Cord SC-LC (10m) 10. Transceiver Multimode (MM) 1G 11. Transceiver Multimode (MM) 10G - Kerja-kerja aktiviti TnC sehingga 20 - 30 September 2020. 12. Fiber Cable Multimode outdoor (250 meter) 13. Fiber patch panel 6 core 14. Supply and lay cable optic 15. Splicing and termination 12 core 16. Perkhidmatan Integrasi 3 Modaliti Tambah Toshiba C-Arm (II) Toshiba SXT-2000A- Kerja sudah dilakukan dan selesai pada 18hb Mei 2020 Philips C-Arm Philips BV Endura - Kerja sudah dilakukan dan selesai pada 21hb Jun 2020 Siemens C-Arm Arcadis Varic - Kerja sudah dilakukan dan selesai pada 28hb Mei 2020 17. Deployment Laporan SS RA RA101 - enunggu pengesahan pihak PIK KKM sebelum di buat deployment - - 12. | NA
6 | MOH | Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu - Perkhidmatan Penyelenggaraan 01 Jan 2020 - 31 Dec 2022 (3 years) | 2399802 | 2020-01-01 | 2022-12-31 | Perkhidmatan Penyelenggaran Dan Sokongan Operasi Bagi Perkakasan, Perisian, Aplikasi Dan Rangkaian Untuk Sistem Pengurusan Pesakit (SPP) di Hospital Raja Perempuan Zainab II Kota Bharu Bagi Tempoh 36 Bulan | Suradi Abdul Rahman | Ahmad Zamin Mahadzir/Sukiman Johari Abdul Manan | Hamid Baharudin | Maintenance | 1. (PSC 3/2020) - No loaner available due to high rate of hardware breakdown (open) - For hardware faulty, project team will source out to local vendor for repair otherwise need to arrange to send the hardware to KL - Temporary to procure small number of hardware for immediate replacement 2. PSC 3/2020) - Equipment tagging has not started yet due to unable to prepare sticker on time (open) - To speed up sticker preparation after MCO ended. 3. (PSC 3/2020)- Replacement and transition of iDesk to iFics. Projectis still using iDesk at the moment (open) - To brief CCC team with SPP and RISPACS workflow after MOC - To train HTP staff and IT HRPZII staff on iFics | 0 | 2399802 | 0 | 233754.3661 |  | NA | 1. PM activity will start on 9/3/2020 utilising 2 CE 2. To arrange for project's internal kickoff | Overall completion: Plan = 8%; Actual = 7% '1.Project kick off with customer was done on 16/12/2019 2.Monthly Corrective Maintenance report completed for January 2020, February 2020 and March 2020. 3. Network Utilization/ Antivirus/ Statistics of Usage & Disk Space Report completed for January 2020, February 2020 and March 2020. 3. PM activity has started on 9/3/2020 however due to MCO, the activity has stopped on 18/3/2020. It will continue after MCO. 4. Internal kick-off will be arranged after MCO | Overall completion: Plan = 8%; Actual = 7% '1. Project kick off with customer was done on 16/12/2019 2. Monthly Corrective Maintenance report completed for January 2020, February 2020 and March 2020. 3. Planned Preventive Maintenance (PPM) Activity, start 8/3/2020 4. Network Utilization/ Antivirus/ Statistics of Usage & Disk Space Report completed for January 2020, February 2020 and March 2020. 5. PM activity has started on 9/3/2020 however due to MCO, the activity has stopped on 18/3/2020. It will continue after MCO. 6. Internal kick-off will be arranged after MCO Hardware Install Status i. Personal Computer; 47% ii. Laser Printer; 45% iii. Barcode Printer; 43% iv. Barcode Scanner; 25% v. MyKad Reader; 0% | Overall completion: Plan = 8%; Actual = 7% 1. Project kick off with customer was done on 16/12/2019 2. Monthly Corrective Maintenance report completed for January 2020, February 2020 and March 2020. 3. Equipment Tagging & Inventory Update Activity status is 0%, yet to start 4. PM activity has started on 9/3/2020. However due to MCO, the activity has ceased temporarily on 18/3/2020. It will continue after MCO. 5. Internal kick-off will be arranged after MCO, likely in the middle of June 2020 Overall Hardware Installation Status is 45%. The breakdown as below: i. Personal Computer; 47% ii. Laser Printer; 45% iii. Barcode Printer; 43% iv. Barcode Scanner; 25% v. MyKad Reader; 0% | Overall completion: Plan = 8%; Actual = 7% 1. Project kick off with customer - 16/12/2019 2. Monthly Corrective Maintenance report completed for January 2020, February 2020 and March 2020. 3. Planned Preventive Maintenance (PPM) Activity, start 8/3/2020 4. PM activity has started on 9/3/2020 however due to MCO, the activity has stopped on 18/3/2020. It will continue after MCO. 5. Internal kick-off - 22/6/2020 Hardware Install Status i. Personal Computer; 47% ii. Laser Printer; 45% iii. Barcode Printer; 43% iv. Barcode Scanner; 25% v. MyKad Reader; 0% | 'No status updated & slide | Overall completion: Plan = 25%; Actual = 25% 1. Project kick off with customer - 16/1/2020 2. Monthly Corrective Maintenance report completed for January 2020, February 2020 and March 2020. 3. Planned Preventive Maintenance (PPM) Activity dor January, February 2020 has completed 4. PM activity has started on 9/3/2020 however due to MCO, the activity has stopped on 18/3/2020. It will continue after MCO. | Overall completion: Plan = 25%; Actual = 25% 1. Project kick off with customer - 16/1/2020 2. Monthly Corrective Maintenance report completed for January 2020, February 2020 and March 2020. 3. Planned Preventive Maintenance (PPM) Activity for January, February 2020 have completed 4. PM activity has started on 9/3/2020 however due to MCO, the activity has stopped on 18/3/2020. It will continue after MCO. | NA
7 | LPPKN | Sistem Reproductive Health Information System (RHIS) Membekal, Menghantar, Mengkaji, Merekabentuk, Membangun, Menginstalasi, Menguji, Mentauliah Dan Menyelenggara Bagi Naik Taraf Sistem Reproductive Health Information System (RHIS) di LPPKN | 1901901.21 | 2016-11-01 | 2020-02-06 | 1. Pertukaran persekitaran Client Server kepada Web Based 2. Migrasi pangkalan data dari server RHIS Client Based kepada Web Based 3. Pembangunan Modul Offline 4. Integrasi data di antara RHIS & LIS 5. Integrasi di antara RHIS & SAGA 6. Pembangunan Modul Pelaporan 7. Pemasangan dan konfigurasi pekakasan dan perisian 8. Latihan (Teknikal, Pentadbir Sistem & Pengguna) 9. Helpdesk, sokongan operasi dan teknikal | Redzuan Amiruddin | Ahmad Zamin Mahadzir/TBA | Halimah Din | Development | 1. Sharing resources ( System Analyst) with other project (open) | 1901901.21 | 0 | 1901901.21 | 1232780.5783 | 1. Overall completion, Plan = 98.8%, Actual = 98.8% 2. Corrective maintenance in progress 3. Monitoring & Stabilisation (Corrective Maintenance Activity), rescheduled to finish from 31/10/2019 to 6/2/2020 (end of contract) | 1. Overall completion, Plan = 100%, Actual = 100% 2. Monitoring & Stabilisation (Corrective Maintenance Activity), rescheduled to finish from 31/10/2019 to 6/2/2020 (end of contract). | 1. Overall completion, Plan = 100%, Actual = 100% 2. Monitoring & Stabilisation (Corrective Maintenance Activity = completed 6/2/2020 | Maintenance support is on going start on 7/2/2020. | NA | NA | NA | NA | NA | Overall completion status Plan = 63%, Actual =63% CM report (Feb 2020 - August 2020 )= done CM Report (sept 2020) = ongoing Problems Log for September, received and closed 5 (application) Issue Contract pending at LPPKN for sign off | NA
8 | MOH | SPP Maintenance HRPB, Ipoh (1 June 2019 - 31 May 2020) | 493499.17 | 2019-06-01 | 2020-05-31 | Perkhidmatan Penyelenggaraan dan Sokongan Operasi Bagi Perkakasan, Perisian, Aplikasi Dan Peralatan Rangkian untuk Sistem Pengurusan Pesakit (SPP) di Hospital Raja Permaisuri Bainun (HRPB), Ipoh | Redzuan Amiruddin | Ahmad Zamin Mahadzir/Sukiman Johari Abdul Manan | Halimah Din | Maintenance | 1. Contract renewal still not ready. (open) | 488259.38 | 5239.79 | 488259.38 | 134989 | 1. Overall completion: Plan = 27%; Actual = 27% 2. Corrective Maintenance in progress. 3. CM Report for December 2019, January & February 2020 target completed by 29/02/2020 4. Problems reported December 2019 - Total Received = 3 - Open = 0 - Closed = 3 | 1. Overall completion: Plan = 41%; Actual = 41% 2. Corrective Maintenance in progress. 3. CM Report for December 2019, January and February 2020 target completed by 29/02/2020 4. Problems reported January 2020; Total Received = 7, Open = 0, Closed = 7 | 1. Overall completion: Plan = 55%; Actual = 55% 2. Corrective Maintenance in progress. 3. CM Report for December 2019, January and February 2020 target completed by 29/02/2020 4. Problems reported February 2020; Total Received = 2, Open = 0, Closed = 2 | Overall completion: Plan = 68%; Actual = 68% 1. Corrective Maintenance in progress. 2. CM Report for December 2019, January and February 2020 done 29/02/2020 3. Problems reported March 2020; Total Received = 3, Open = 0, Closed = 3 | Overall completion: Plan = 78%; Actual = 78% 1. Corrective Maintenance in progress. 2. CM Report for March, April & April 2020 target completed by 31/05/2020 3. Total Nine (9) Hardware Failure Problems reported and closed | Overall completion: Plan = 98%; Actual = 98% 1. Corrective Maintenance in progress. 2. CM Report for March, April & April 2020, completed by 31/05/2020 3. Total four (4) Hardware Failure reported and closed. | Overall completion: Plan = 98%; Actual = 98% 1. Corrective Maintenance in progress. 2. CM Report for March, April & May 2020, completed by 31/05/2020 3. Total Four (4) Hardware Problems reported and closed. 4. PM#1 is on going | SPP Maintenance-Hospital Raja Permaisuri Bainun Ipoh, Perak (VO June 2020 – July 2020) Overall completion: Plan = 80%; Actual = 80% 1. V.O for Corrective Maintenance in progress. 2. V.O for CM Report for June & July 2020, target completed by 31/07/2020 3. Total Fourteent (14) Hardware Failure Problems reported and closed. | SPP Maintenance-Hospital Raja Permaisuri Bainun Ipoh, Perak (VO June 2020 – July 2020) Overall completion: Plan = 100%; Actual = 100% 1. PM31 and PM#2 has completed. 2. V.O for CM Report for June & July 2020, has completed 3. Total twelve (12) Hardware Failure Problems reported and closed. | SPP Maintenance-Hospital Raja Permaisuri Bainun Ipoh, Perak Overall completion: Plan = 100%; Actual = 100% 1. PM#1 and PM#2 has completed on 30/4/2020 and 30/05/2020 respectively. 2. CM Report for Jan until May 2020 has completed 3. V.O for CM Report for June and July 2020 on 31/07/2020 3. Total twelve (12) Hardware Failure Problems reported and closed. | NA
9 | MOH | SPP V2.6 Implementation Project - Hospital Taiping Perak (2018 - 2020) | 123275.4 | 2018-09-14 | 2020-09-13 | Membekal, Menghantar, Memasang, Menguji, Mengkonfigurasi, Mentauliah Guna dan Sewaan Peralatan ICT untk Pelaksanaan Aplikasi Sistem Pengurusan Pesakit (SPP) Versi 2.6 | Redzuan Amiruddin | Ahmad Zamin Mahadzir/ Sukiman Johari Abdul Manan | Halimah Din | Maintenance | No open or new issues | 92456.55 | 30818.85 | 92456.55 | 1725.34 | 1. Overall completion: Plan = 49%; Actual = 49% 2. Corrective Maintenance in progress. 3.CM Report for December 2019 , January - February 2020 target completed by 28/2/2020 4. Total one (2) Hardware Failure problems reported and closed. | 1. Overall completion: Plan = 65%; Actual = 65% 2. Corrective Maintenance in progress. 3.CM Report for December 2019, January – February target completed by28/02/2020 4. Total one (2) Hardware Failure problems reported and closed. | 1. Overall completion: Plan = 69%; Actual = 69% 2. Corrective Maintenance in progress. 3.CM Report for December 2019, January – February target completed by28/02/2020 4. No problems reported in February 2020. | Overall completion: Plan =74%; Actual = 74% 1. Corrective Maintenance in progress. 2.CM Report for December 2019, January – February done 28/02/2020 3. No problems reported in March 2020. | Overall completion: Plan = 83%; Actual = 83% 1.Corrective Maintenance in progress. 2.CM Report for March, April & May 2020, target completed by 31/05/2020 3. No problems reported and closed in May 2020. | Overall completion: Plan = 83%; Actual = 83% 1.Corrective Maintenance in progress. 2.CM Report for March, April & May 2020, completed by 31/05/2020 3. One (1) Hardware Failure problems reported and closed in April 2020.. | Overall completion: Plan = 87%; Actual = 87% 1. Corrective Maintenance in progress. 2.CM Report for December 2019, January 2020 and February 2020 completed by 28/2/2020 3. No problems reported for the month. | Overall completion: Plan =91%; Actual = 91% 1. Corrective Maintenance in progress. 2.CM Report for June, July & August 2020, target completed by 31/08/2020 3.Total one (1) Hardware Failure problems reported and closed. | Overall completion: Plan =100%; Actual = 100% 1. Corrective Maintenance in progress. 2.CM Report for September 2020 has completed 3.No problems reported | Overall completion: Plan =100%; Actual = 100% 1. Corrective Maintenance (Jan 2020 to August 2020) were completed. 2.CM Report for September 2020 is in progress 3.No problems reported in Sept 2020 4. Contract renewal not ready. | NA
10 |  | Perkhidmatan Sewaan Perkakasan ICT Untuk Sistem Pengurusan Pesakit (SPP) Versi 2.6 Selama 3 Tahun Di Hospital Taiping Perak Darul Ridzuan |  | 2020-10-26 | 2023-10-25 |  | Mas Maliny | Sukiman | Halimah DIn | Maintenance
10 | MOH | SPP Application Maintenance-Hospital Taiping, Perak (2018 - 2020) | 180200.42 | 18/9/2018 18 Sept 2020 | 2020-09-17 | 1. Melaksanakan perkhidmatan penyelenggaraan pencegahan bagi perisian SPP sebanyak empat (4) kali sepanjang tempoh kontrak. 2. Melaksanakan penyelenggaraan pembaikan terhadap perisian mengikut SLA yang telah ditetapkan. 3. Menyediakan dokumen prosedur pelan kontigensi bagi aplikasi SPP. 4. Menyediakan kakitangan sokongan secara offsite secara sepenuh masa sepanjang tempoh kontrak. 5. Menyediakan laporan dan dokumentasi berkaitan aplikasi. | Redzuan Amiruddin | Ahmad Zamin Mahadzir/ Sukiman Johari Abdul Manan | Halimah Din | Maintenance | No open or new issues | 135150.33 | 45050.09 | 135150.33 | 101949.57 | 1. Overall completion: Plan = 49%; Actual = 49% 2. Corrective Maintenance in progress. 3.CM Report for December 2019 , January - February 2020 target completed by 28/2/2020 | 1. Overall completion: Plan = 65%; Actual = 65% 2. Corrective Maintenance in progress. 3.CM Report for December 2019, January – February target completed by 28/02/2020 4. Total three (3) Application problems reported and closed. | 1. Overall completion: Plan = 69%; Actual = 69% 2. Corrective Maintenance in progress. 3.CM Report for December 2019, January – February target completed by 28/02/2020 4. Total seven (7) Application problems reported and closed. | Overall completion: Plan = 74%; Actual = 74% 1. Corrective Maintenance in progress. 2.CM Report for December 2019, January – February done 28/02/2020. 3. No problems repoted in March 2020. | Overall completion: Plan = 83%; Actual = 83% 1. Corrective Maintenance in progress. 2. CM Report for March, April & May 2020, target completed by 31/05/2020 3. Total three (3) application failure problems reported and closed in May 2020 | Overall completion: Plan = 83%; Actual = 83% 1.Corrective Maintenance in progress. 2.CM Report for March, April & May 2020, completed by 31/05/2020 3.Total Three (3) Application problems reported and closed. | Overall completion: Plan = 87%; Actual = 87% 1. Corrective Maintenance in progress. 2.CM Report for December 2019, January 2020 and February 2020 completed by 28/2/2020 3. Total six (6) Application problems reported and closed. | Overall completion: Plan = 91%; Actual = 91% 1. Corrective Maintenance in progress. 2.CM Report for June, July & August 2020, target completed by 31/08/2020 3. Total three (3) Application problems reported and closed. | Overall completion: Plan = 100%; Actual = 100% 1. Corrective Maintenance in progress. 2.CM Report for September 2020 has completed 3. Total five (5) Application problems reported and closed. | Overall completion: Plan =100%; Actual = 100% 1. Corrective Maintenance (Jan 2020 to Sept 2020) were completed. 2. Corrective Maintenance Oct 2020 to Nov 2020) is in progress 3.2 application problems were reported and closed in Sept 2020 | NA
11 | MOH | SPP CAS PHIS Integration-Hospital Raja Permaisuri Bainun Ipoh | 396556.6 | 2017-06-01 | 2020-08-31 | 1. Reconfigure Glassfish SPP application server 2. SPP Database - Alter related database - Check and update mapping reference table 3. Perform Data migration for encounter active 4. Application SPP v3.5 - Integration with existing SPP sources code at Hospital - Configure contact patch 5. Install and configure Mirth Component 6. Install and configure CAS Component 7. Install CAS icon, url, ie setting and certificate at 1,100 workstation 8. On going support and maintenance services for 3 years upon go live | Suradi Abd Rahman | Ahmad Zamin Mahadzir/Sukiman Johari Abdul Manan | Halimah Din | Maintenance | No open or new issues | 396556.6 | 0 | 293658.16 | 12237.06 | 1. Maintenance support is on going. | 1. Maintenance support is on going. | 1. Maintenance support is on going. | 1. Maintenance and support is on going. | 1. Maintenance andsupport is on going. | 1. Maintenance and support is on going. | 1. Maintenance and support is on going. | 1. Maintenance and support is on going. | 1. Maintenance and support is on going. |  | NA
12 | MOH | Proof od Concept (POC) HIS@KKM EMR Basic At Hospital Port Dickson | 500000 | 2019-05-01 | 2020-04-01 | Proof od Concept (POC) HIS@KKM EMR Basic 1. HIS@KKM Lite 2. Integration 3. Migration 4. Training 5. Infrastructure | Roslind Abdul Rahman | Ahmad Zamin Mahadzir/ Sukiman Johari Abdul Manan |  | Investment | 1. (PSC 2/2020)-EMR @ HPD go live timeline is postponed (currently mid August 2019) to a later date pending the acceptance of EMR @ HPRB. (PSC 3/2020)- New timeline has not been discuss with HPD yet (open) 2. (PSC 2/2020)-Letter from BPP states that the asset can be registered as a gift and becomes an asset upon submission of the HTP and approval application from HPD. (psc 3/2020)- HTP will submit an MOU that clarifies that hardware provided by HTP will remain in HPD during POC period. HPD will in turn carried out the leasing process for these hardware For servers, data relocate from Awan HeiTech to PDSA after warranty. open) (PSC 4/2020)- ( open) (PSC5/2020) - (open) (PSC6/2020) - (open) 4 (PSC 2/2020)-Downgrading existing network bandwidth from 100mbps to 20mbps could impact the performance of HISKKM EMR at AwanH (PSC 3/2020) - As per stress test HTP proposed minimum bandwidth requirement is 40Mbps. Also we informed (as a disclaimer) that it also depend on actual HISKKM usage and required to be monitored reqgularly (in progress) (PSC 4/2020)- Do network test on 200 load user using MyGovnet existing line 20mbps and 100mbps. Suggest best bandwidth to connect to AwanH for EMR Basic @ HPD. As per stress test HTP proposed minimum bandwidth requirement is 40Mbps. Also we informed (as a disclaimer) that it also depend on actual HISKKM usage and required to be monitored regularly (open) (PSC 5/2020- (open) (PSC6/2020) - (open) 4. There is a risk that existing bugs in EMR Basic (if any) will impact rollout at HPD which could result in unacceptable users experience. Bugs are mainly from data migration. There are support team onsite and at central. As of 13 /10/2020 there are 7 problem logs. PSC2/2020 15/10/2020 The risk has become an issue. Bugs happen but manageable. Some need further investigation (open) |  |  |  | 826803.3857 |  | Overall completion: 31% i. Project Initation; 100% ii. Site Assessment; 100% iii. Electrical Switch Socket Outlet Installation; 100% iv. Lan Cabling & Installation; 100% v. Network Access Switch/ Access Point Installation; 50% vi. Procurement of Hardware; 70% vii. TC & Peripheral Installation; 70% viii. Walkthrough EMR Basic;100% ix. Clound VM Server Components Configuration & Setting (Clound@Awan HeiTech); 45% x. Application Configuration & Setup; 0% xi. Data Migration (from SPPv.2.6); 0% xii. System Intergration (eGL, eSMRP, MyHix); 0% xiii. Training Plan; 0% xiv. End User Training; 0% xv. System Go-Live Approach; 0% xvi. System Go-Live & Monitoring; 0% xvii. Warranty Support; 0% | Overall completion: 49% i. EMR HIS@KKM EMR Basic Walkthru (Awareness program); 100% ii. Infra deployment @ HPD; 56% iii. HIS@KKM EMR Basic deployment @ AwanH; 100% iv. Rollout activities - First cut Db migration; 100% - Data verification; 50% - Users Training; 50% | Overall completion: 49% 1. EMR HIS@KKM EMR Basic Walkthru (Awareness program); 100% 2. Infra deployment @ HPD; 56% 3. HIS@KKM EMR Basic deployment @ AwanH; 100% 4. Rollout activities - First cut Db migration; 100% - Data verification; 50% - Users Training; 50% | Overall completion: 49% 1. EMR HIS@KKM EMR Basic Walkthru (Awareness program); 100% 2. Infra deployment @ HPD; 56% 3. HIS@KKM EMR Basic deployment @ AwanH; 100% 4. Rollout activities - First cut Db migration; 100% - Data verification; 50% - Users Training; 50% | Overall completion: 49% 1. EMR HIS@KKM EMR Basic Walkthru (Awareness program); 100% 2. Infra deployment @ HPD; 56% 3. HIS@KKM EMR Basic deployment @ AwanH; 100% 4. Rollout activities; 40% - First cut Db migration; 100% - Data verification; 50% - Users Training; 50% | Overall completion: 73% 1. EMR HIS@KKM EMR Basic Walkthru (Awareness program); 100% 2. Infra deployment @ HPD; 100% 3. HIS@KKM EMR Basic deployment @ AwanH; 100% 4. Rollout activities; 100% - First cut Db migration; 100% - Data verification; 100% - Users Training; 100% - Pre Go Live Simulation; 100% - Go Live; 100% 5. 1 Month Babysit – After Go Live; 38% | Overall completion: 83.9% 1. EMR HIS@KKM EMR Basic Walkthru (Awareness program); 100% 2. Infra deployment @ HPD; 100% 3. HIS@KKM EMR Basic deployment @ AwanH; 100% 4. Rollout activities; 100% - First cut Db migration; 100% - Data verification; 100% - Users Training; 100% - Pre Go Live Simulation; 100% - Go Live; 100% 5. 1 Month Post Go Live Support; 100% | Overall completion: 94% KKM requested HTP to extend another 3 months from 20/10/2020 until 19/1/2021 1. EMR HIS@KKM EMR Basic Walkthru (Awareness program); 100% 2. Infra deployment @ HPD; 100% 3. HIS@KKM EMR Basic deployment @ AwanH; 100% 4. Rollout activities; 100% - First cut Db migration; 100% - Data verification; 100% - Users Training; 100% - Pre Go Live Simulation; 100% - Go Live; 100% 5. 1 Month Post Go Live Support; 100% 6. 3 months warranty 66% | Overall completion: 94% KKM requested HTP to extend another 3 months from 20/10/2020 until 19/1/2021 1. EMR HIS@KKM EMR Basic Walkthru (Awareness program); 100% 2. Infra deployment @ HPD; 100% 3. HIS@KKM EMR Basic deployment @ AwanH; 100% 4. Rollout activities; 100% - First cut Db migration; 100% - Data verification; 100% - Users Training; 100% - Pre Go Live Simulation; 100% - Go Live; 100% 5. 1 Month Post Go Live Support; 100% 6. 3 months warranty 66% | NA
13 | LPPKN | Penyelenggaran Reproductive Health Information System (RHIS) 2.0 di LPPKN Bagi Tempoh Setahun | 289100 | 2020-02-07 | 2021-02-06 | 1.Hardware and Software Maintenance | Redzuan Amiruddin | Ahmad Zamin Mahadzir/Sukiman Johari Abdul Manan | Halimah Din | Maintenance | NA |  |  |  | 134691 |  | NA | NA | 1.Overall completion, Plan = 13%, Actual = 13% 2.Corrective Maintenance in progress. 3.CM Report for March Done 31/3/2020. 4. No problems reported in March 2020. | .Overall completion, Plan =22%, Actual = 22% 1.Corrective Maintenance in progress. 2.CM Report for April Done 31/4/2020. 3. No problems reported in March 2020. | Overall completion, Plan =32%, Actual = 32% 1.Corrective Maintenance in progress. 2.CM Report for May completed by 31/05/2020 3. Four (4) hardware failures reported and closed in May 2020. | Overall completion, Plan =40%, Actual = 40% 1.Corrective Maintenance in progress. 2.CM Report for June 2020 completed by 30/06/2020 3. No problems reported Billing 1. To bill RM72,275.00 in June 2020 | Overall completion, Plan =48%, Actual = 48% 1.Corrective Maintenance in progress. 2.CM Report for June 2020 completed by 30/06/2020 3. No problems reported | Overall completion, Plan =63%, Actual = 63% 1.Corrective Maintenance in progress. 2.CM Report for August 2020 completed by 31/8/2020 3. For August 2020, 15 application relation problems were reported and all were closed | Overall completion, Plan =63%, Actual = 63% 1.CM Report for Feb 2020 to August 2020 completed 2. For September 2020, 5 application relation problems were reported and all were closed 3. The contract is pending LPPKN sign off | NA
14 | SPP - HKL, HTAR, Hosp Kajang | Tender Perkhidmatan Penyelenggaran Dan Sokongan Operasi Perkakasan, Perisian, Rangkaian Dan Aplikasi Untuk Sistem Pengurusan Pesakit (SPP) di Hospital Kuala Lumpur, Hospital Tengku Ampuan Rahimah Dan Hospital Kajang, Kementerian Kesihatan Malaysia | 2102177.16 | 2020-04-20 | 2023-04-19 | 1.Hardware and Software Maintenance | Mohd Yushan Abdul Wahab | Ahmad Zamin Mahadzir/Sukiman Johari Abdul Manan | Halimah Din | Maintenance | 1. Hardware(backup server tape drive) damage before contract a.HKL - Backup failed b.HTAR - Tape drive damage (PSC 6/2020) - a.Shedule backup done at Netvault b.replicate database backup to apps server and external hard drive (open) 2. HKL all mycard device not function (PSC 6/2020) - Done deploy patches (open) 3. Onsite resource are central CE's (PSC 6/2020) - Discussion to absorb part-time staff and also to maintain some CE's(open) 4. mmediate replacement in case of server damage. (PSC 6/2020) - Propose for loaner unit as 1 to 1 replacement (open ) 5. HTAR request to dispose all Lexmark e360 printer and replace to Lexmark ms312 - agreed by En Nawawi KKM (PSC 6/2020) - HTP to prepare BER letter. ( open) |  |  |  | 125841.9923 | [5 empty] | Overall completion: Plan = 0%; Actual = 0% 1. Status Activities - Kick Meeting = 100% - Equipment Tagging & Inventory Update Activity = 10% - Monthly Correction Maintenance Report (submission to KKM on 10th each month – 36 times) = 8% - Monthly Correction Maintenance Report #1-3 = 10% 2. Total Five (5) Application and Four (4) Hardware Failure problems reported and closed for HKL. 3. Total One (1) Application, Five (5) Hardware Failure and Two (2) Customer Equipment problems reported and closed for HTAR. 4. Total Six (6) Hardware Failure and Two (2) Customer Equipment problems reported and closed for HKJ. | Overall completion: Plan = 100%; Actual = 7% 1. Status Activities - Kick Off Meeting = 100% - Equipment Tagging & Inventory Update Activity = 100% - Monthly Correction Maintenance Report (submission to KKM on 10th each month – 36 times) = 8% - Monthly Correction Maintenance Report #1= 100% - Monthly Correction Maintenance Report #2= 30% - Business Continuity Services & Disaster Recovery Plan Documentation = 100% 2. Total Five (5) Application, Six (6) Hardware Failure, One(1) Infra problems reported and closed for HKL. 3. Total One (1) Application and Five (5) Hardware Failure problem reported and closed for HTAR. 4. Total Six (6) Hardware Failure and Two (2) Customer Equipment problems reported and closed for HKJ. | Overall completion: Plan = 100%; Actual =16% 1. Status Activities - Kick Meeting = 100% - Equipment Tagging & Inventory Update Activity = 10% - Monthly Correction Maintenance Report (submission to KKM on 10th each month – 36 times) = 8% - Monthly Correction Maintenance Report #1-3= 100% - Business Continuity Services & Disaster Recovery Plan Documentation = 80% 2. Total one (1) Application, eight (8) Hardware Failure and three (3) User Request problems reported and closed for HKL. 3. Total one (1) Application, seventeen (17) Hardware and three (3) Software Failure problem reported and closed for HTAR. 4. Total Ten (10) Application, six (6) Hardware Failure and three (3) User Request problems reported and closed for HKJ. | Overall completion: Plan = 100%; Actual = 45% 1. Status Activities - Kick Off Meeting = 100% - Equipment Tagging & Inventory Update Activity = 10% - Monthly Correction Maintenance Report (submission to KKM on 10th each month – 36 times) = 16% - Monthly Correction Maintenance Report #1-#5 100% - Business Continuity Services & Disaster Recovery Plan Documentation = 100% 2. Total four (4) Application, eleven (11)Hardware Failure and two (2) User Request problems reported and closed for HKL. 3. Total five (5) Application, eighteen (18) Hardware and two (2) User Request problem reported and closed for HTAR. 4. Total Four (4) Application, eleven (11) Hardware Failure, two(2) Software, two (2) Customer Equipment, three( 3) Others and two(2) User Request problems reported and closed | Overall completion: Plan = 100%; Actual = 45% 1. Status Activities - Kick Off Meeting = 100% (30/4/2020) - Equipment Tagging & Inventory Update Activity = 100% (30/6/2020) - Monthly Correction Maintenance Report (submission to KKM (on 10th each month – 36 times) = 16% - Monthly Correction Maintenance Report #1-#5 100% - Business Continuity Services & Disaster Recovery Plan Documentation = 100% 2. Total four (4) Application, eleven (11)Hardware Failure and two (2) User Request, two (2) software and two (2) customer equipment and three (3) others problems reported and closed for HKL. 3. Total five (5) Application, eighteen (18) Hardware, two (2) software and two (2) User Request problem reported and closed for HTAR. 4. Total one (1) Application, seventeen (17) Hardware, three (3) Software and one( 1) Others problems were reported and closed for HKJ. | NA
15 | Cyberjaya Hospital | Proposed Development of Cyberjaya Hospital (288 Beds) on Lot 47686 And H.S.(D) 28779 PT41461 At Persiaran Multimedia Cyber 11, Cyberjaya, Mukim Dengkil, Daerah Sepang, Selangor Darul Ehsan(“Design & Build”) | 14,776,087.39 (Inclusive GST) | 2020-07-01 | 2023-08-31 | Implementation of HIS@KKM and BBIS inclusive Off Shelf Application ( PACS, CCIS, PhIS & BI ) | Redzuan Amiruddin | Ahmad Zamin Mahadzir/Sukiman Johari Abdul Manan | Nur Syuhadah, Rozaimi |  | No new or open issues |  |  |  | 8179 | [6 empty] | NONE | Overall completion: Plan = 3%, Actual = 3%, 1. Project Initiation; completed 47% 2. Contract Preparation; completed 47% 3. Procurement Process; completed 45% 4. Project Mobilisation & Project Planning; completed 47% | Overall completion: Plan = 7%, 1. Project Initiation; completed 100% 2. Contract Preparation; completed100% 3. Procurement Process; completed 47% 4. Project Mobilisation & Project Planning; completed 100% | Overall completion: Plan = 7%, 1. Project Initiation; completed 77% 2. Procurement Process; 47% 3. Business Realignment/ BPR 17% 4. Integration and technical Discussion 89% Issues 1. Commitment Core team to participate in deliverables activities - notify 2 weeks in advance | NA
16 | SPP - HRPB | Perkhidmatan Penyelenggaraan Dan Sokongan Operasi Bagi Perisian, Perkakasan Dan Peralatan Rangkaian Sistem Pengurusan Pesakit (SPP) (Luar Skop HIS@KKM) di Hospital Raja Permaisuri Bainun (HRPB), Ipoh (17 July 2020 - 16 October 2021) | 467623 | 2020-07-17 | 2021-10-16 | Hardware and Software Maintenance | Redzuan Amiruddin | Ahmad Zamin Mahadzir/Sukiman Johari Abdul Manan | Halimah Din | Maintenance | No new or open issues | [11 empty] | NA | NA | Overall completion status Plan = 2%, Actual =2% CM report ( August 2020 )= done CM Report (Sept 2020) = ongoing Problems Log for September, received and closed 12 (hardware) New Contract started 16/8/2020f | NA
Note on N9: Norhasina Hamzah: Based on collection made.
Note on P9: Norhasina Hamzah: Based on collection made.
Note on E14: Norhasina Hamzah: Ceiling value: RM2,400,000 (concession transaction base)
Note on E21: Aida Rashid: Original Contract value RM10,123,738.81

## Billing Status (August 2020)
BILLING STATUS AS AT 31 AUGUST 2020
No. | Main Project | Status | Project Name | Project Value (RM) | Total Billed as at 31/08/2020 | Paid/ Revenue (RM) | Balance to Pay (RM) | Balance to Bill (RM) | Total Billing as at 31/12/2019 | 2020 BILLING PLAN/PROJECTION | [23 empty] | TOTAL PLAN Y2020 | TOTAL PLAN Y2021 | TOTAL PLAN Y2022 | Remaining | Remarks | 2020 Billing Up-To-Date Summary (As at 31/08/2020)
[10 empty] | JAN |  | FEB |  | MAR |  | APR |  | MAY |  | JUN |  | JUL |  | AUG |  | SEPT |  | OCT |  | NOV |  | DEC
[10 empty] | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | [5 empty] | Planned | Actual | Variance
TRANSPORT
1 | JPJ | Ongoing | New Generation FireWall - NGFW 01 Oct 2018 - 31 Dec 2020 (2 Years 3 Mths) | 2979157.4222 | 2888682.11 | 2888682.11 | 0 | 90475.3122 | 1647031.88 | 0 |  | 0 |  | 0 | 0 | 1241650.24 | 1241650.23 | 0 |  | 0 |  | 30158.43 |  | 0 |  | 0 |  | 30158.43 |  | 0 |  | 30158.44 |  | 1332125.54 | 0 | 0 | 0 | JPJ project is no longer under Core 1 | 1271808.67 | 1241650.23 | -30158.44
2 | JPJ | Ongoing | mySIKAP Maintenance Extension Jul 2019 - Oct 2019 (4 mths) - 2nd extension - Carry forward for On Request | 7016592.27 | 6107574.63 | 6107574.63 | 0 | 909017.64 | 4833869.24 | 1273705.39 | 1273705.39 | 0 |  | 0 |  | 0 |  | 0 |  | 909017.64 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2182723.03 | 0 | 0 | 0 | JPJ project is no longer under Core 1 | 2182723.03 | 1273705.39 | -909017.64
3 | JPJ | Ongoing | mySIKAP Maintenance Extension Nov 2019 - Dec 2019 (2 mths) - 3rd extension | 3508296.13 | 3508296.13 | 3508296.13 | 0 | 0 | 1764232.2 | 1744063.93 | 1744063.93 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1744063.93 | 0 | 0 | 0 | JPJ project is no longer under Core 1 | 1744063.93 | 1744063.93 | 0
4 | JPJ | Ongoing | mySIKAP Maintenance Extension Jan 2020 - June 2020 (6 mths) - 4th extension | 10524888.4 | 7727962.23 | 7727962.23 | 0 | 2796926.17 | 0 |  |  |  |  | 1286924.59 | 1286924.59 | 1286924.59 | 1286924.59 | 5154113.05 | 5154113.05 | 1286924.59 |  | 1510001.58 | [11 empty] | 10524888.4 | 0 | 0 | 0 | JPJ project is no longer under Core 1 | 10524888.4 | 7727962.23 | -2796926.17
5 | PSP | Ongoing | Penang Smart Parking (PSP) - Majlis Bandaraya Pulau Pinang (MBPP) - Majlis Perbandaran Seberang Prai (MPSP) 01 May 2019 - 30 April 2026 (7 years) | 259686000 | 4760314.44 | 4760314.44 | 0 | 254925685.56 | 357814.21 | 0 | 533035.88 |  | 686428.02 |  | 492781.25 |  | 68925.87 |  | 203660.99 |  | 494293.15 |  | 1108685.8 |  | 814689.27 | [8 empty] | 0 |  |  |  | Billing based on collection /transaction. | 0 | 4402500.23 | 4402500.23
|  |  |  | 283714934.2222 | 24992829.54 | 24992829.54 | 0 | 258722104.6822 | 8602947.53 | 3017769.32 | 3550805.2 | 0 | 686428.02 | 1286924.59 | 1779705.84 | 2528574.83 | 2597500.69 | 5154113.05 | 5357774.04 | 2195942.23 | 494293.15 | 1540160.01 | 1108685.8 | 0 | 814689.27 | 0 | 0 | 30158.43 | 0 | 0 | 0 | 30158.44 | 0 | 15783800.9 | 0 | 0 | 0 |  | 15723484.03 | 16389882.01 | 666397.98
INTERNAL SECURITY
1 | JIM | Ongoing | myIMMS Maintenance 18 Aug 2017 - 17 Aug 2020 (3 Years) | 42430740 | 40146056.71 | 35615862.26 | 4530194.45 | 2284683.29 | 29230993.19 | 963554.65 | 963554.65 | 1008810.48 | 2614090.48 | 1008810.48 | 943090.48 | 1008810.48 | 1006690.48 | 1008810.48 | 855007.15 | 2598810.48 | 800390.48 | 1008810.48 | 879490.48 | 1008810.48 | 2852749.32 | 1805561.6 | [7 empty] | 11420789.61 |  | 0 | 0 | 1. Perluasan activity at Atase Kathmandu Nepal not able to execute/delay due to Covid 19/MCO. 2. Preventive Maintenance will not be implemented at 9 location in China, Hong Kong, Taiwan, USA, Cambodia and India due to Covid 19, worth RM129,500.00. 3. Local & Overseas training/CPR will not be executed since BTMR has canceled all the training due to Covid 19, worth RM810,000.00. | 9615228.01 | 10915063.52 | 1299835.51
2 | JIM - BESTINET | Ongoing | JIM-BESTINET/FWCMS 1 Nov 2018 - 31 Oct 2021 (3 Years) | 2289600 | 1399200 | 699600 | 699600 | 890400 | 890400 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 |  | 63600 |  | 63600 |  | 63600 |  | 763200 | 636000 | 0 | 0 |  | 508800 | 508800 | 0
3 | JIM - MYEG | Ongoing | JIM-myEG (Transaction Basis) Transaction base since Jan 2013 | 2400000 | 3133627.93 | 3051097.92 | 82530.01 | -733627.93 | 2766555.23 | 50000 | 54116.18 | 50000 | 56818.12 | 50000 | 53016.96 | 50000 | 37752.96 | 50000 |  | 50000 | 19938.6 | 50000 | 62899.87 | 50000 | 82530.01 | 50000 |  | 50000 |  | 50000 |  | 50000 |  | 600000 | 0 | 0 | 0 | Due to MCO, there is no any transaction in April 2020 and affect the transaction in May 2020 as well. *RM0.50 per transaction stipulated in consession agrement between HTP & myEG | 400000 | 367072.7 | -32927.3
4 | JIM - MAHB | Ongoing | JIM - MAHB QMS Integration 29 Dec 2017 - 18 Apr 2021 | 625292 | 657223.5 | 640285.76 | 16937.74 | -31931.5 | 657223.5 | [24 empty] | 0 |  |  |  |  | 0 | 0 | 0
5 | JIM - VKSB | Ongoing | JIM - VISTA KENCANA 01 Oct 2014 - 30 Sept 2017 (3 Years) | 180000 | 175211.36 | 175211.36 | 0 | 4788.64 | 166368.31 | 2122.12 | 2122.12 | 2000 | 2312.39 | 2000 | 2774.55 | 2000 | 1633.99 | 2000 |  | 2000 |  | 1509.57 | [11 empty] | 13631.69 |  |  |  | Due to MCO, there is no transaction from April onwards. *RM0.50 per successful mbike registration | 13631.69 | 8843.05 | -4788.64
6 | JIM | Ongoing | Autocropping for Online Passport System | 381123 | 381123 |  | 381123 | 0 | 0 |  |  |  | 381123 | [24 empty] | Positive variance due to amount billed is not in Billing Plan for Y2020. This is a CR raised by JIM/KDN. One Time billing. | 0 | 381123 | 381123
|  |  |  | 48306755 | 45892442.5 | 40182057.3 | 5710385.2 | 2414312.5 | 33711540.23 | 1079276.77 | 1083392.95 | 1124410.48 | 3117943.99 | 1124410.48 | 1062481.99 | 1124410.48 | 1109677.43 | 1124410.48 | 918607.15 | 2714410.48 | 883929.08 | 1123920.05 | 1005990.35 | 1122410.48 | 2998879.33 | 1919161.6 | 0 | 113600 | 0 | 113600 | 0 | 113600 | 0 | 12797621.3 | 636000 | 0 | 0 |  | 10537659.7 | 12180902.27 | 1643242.57
FOMEMA
1 | FOMEMA | Ongoing | FOMEMA MYIMM Biometric Integration 01 Jan 2017 - 31 Dec 2026 (10 Years) | 48230000 | 22697850.76 | 22697850.76 | 0 | 25532149.24 | 19817957.9 | 0 |  | 0 |  | 1439946.43 | 1439946.43 | 0 |  | 0 |  | 1439946.43 | 1439946.43 | 0 |  | 0 |  | 1439946.43 |  | 0 |  | 0 |  | 1439946.43 |  | 5759785.72 | 5759785.72 | 5759785.72 | 8252792.08 |  | 2879892.86 | 2879892.86 | 0
|  |  |  | 48230000 | 22697850.76 | 22697850.76 | 0 | 25532149.24 | 19817957.9 | 0 | 0 | 0 | 0 | 1439946.43 | 1439946.43 | 0 | 0 | 0 | 0 | 1439946.43 | 1439946.43 | 0 | 0 | 0 | 0 | 1439946.43 | 0 | 0 | 0 | 0 | 0 | 1439946.43 | 0 | 5759785.72 | 5759785.72 | 5759785.72 | 8252792.08 |  | 2879892.86 | 2879892.86 | 0
HEALTH/MOH
1 | CCIS | Ongoing | Critical Care Information System (CCIS) 1 Feb 2019 - 31 Jan 2022 (3 Years) | 33179367.26 | 2709890 | 2709890 | 0 | 30469477.26 | 0 | 0 |  | 0 |  | 2556500 |  | 15388505.53 | 2709890 | 0 |  | 0 |  | 0 |  | 8747789.34 |  | 0 |  | 0 |  | 0 |  | 5298350.13 |  | 31991145 | 634133.01 | -2155800.75 | 0 | KKM has accepted the submitted documents (final reviewed) and project team will propose the new amount to bill due to few relocated equipments among 11 sites. Target to obtain approval from Project Technical meeting on 06 October 2020. | 26692794.87 | 2709890 | -23982904.87
2 | CD | Ongoing | Clinical Documentation 21 Mar 2016 - 20 Mar 2020 (4 Years) | 30101218.92 | 26191691.74 | 26191691.74 | 0 | 3909527.18 | 26191691.74 | 0 |  | 0 |  | 0 |  | 0 |  | 3190968.37 |  | 251512.56 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3442480.93 | 0 | 0 | 0 | Due to MCO, most of activities have been delayed and resheduled to Oct 2020, hence this effects the deliverables submission and payment as well. | 3442480.93 | 0 | -3442480.93
3 | RISPACS | Ongoing | RIS PACS HIS@KKM Fasa I 17 Jul 2017 - 16 Jan 2020 (30 Months) | 10090979.26 | 7455217.95 | 7455217.95 | 0 | 2635761.31 | 7455217.95 | 0 |  | 0 |  | 0 |  | 2227057.827 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2227057.827 | 0 | 0 | 0 | Still in progress whereby currently KKM is reviewing the submitted documents. Once getting approval from KKM, we will proceed with the issuance of the Invoice. Target to submit the Invoice by October 2020. | 2227057.827 | 0 | -2227057.827
4 | HRPZII | Ongoing | Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu - Perkhidmatan Penyelenggaraan 01 Oct 2019 - 31 Dec 2019 (3 mths) | 226639 | 204518.57 | 204518.57 | 0 | 22120.43 | 187492.8 | 17025.77 | 17025.77 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 17025.77 |  |  |  |  | 17025.77 | 17025.77 | 0
5 | HRPZII | Ongoing | Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu - Perolehan Peralatan Tambahan 01 Nov 2019 - 28 Feb 2020 (4 mths) | 496000 | 0 | 0 | 0 | 496000 | 0 | [6 empty] | 496000 | [17 empty] | 496000 |  |  |  | Due to Movement Control Order (MCO)/ Covid 19, delivery of hardware and services have been delayed. Target to deliver by Sept 2020 and to bill by Oct 2020. | 496000 | 0 | -496000
6 | HRPZII | Ongoing | Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu - Perkhidmatan Penyelenggaraan 01 Jan 2020 - 31 Dec 2022 (3 years) | 2399802 | 0 | 0 | 0 | 2399802 | 0 | [6 empty] | 199983.5 | [5 empty] | 199983.5 | [5 empty] | 199983.5 | [5 empty] | 599950.5 | 799934 | 999917.5 | 0 | The contract issue has yet to resolve, currently still pending at Perolehan KKM. Target to bill in Oct 2020. | 399967 | 0 | -399967
7 | RHIS-LPPKN | Ongoing | Reproductive Health Information System (RHIS) - LPPKN 1 Nov 2016 - 6 Feb 2020 (3 Years++) | 1901901.21 | 1901901.21 | 1901901.21 | 0 | 0 | 1901901.21 | [24 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
8 | SPP-IPOH | Ongoing | Sistem Pengurusan Pesakit (SPP) Permaisuri Bainun, Ipoh 1 June 2019 - 31 May 2020 (1 Year) | 493499.17 | 488259.38 | 488259.38 | 0 | 5239.79 | 283848.22 |  |  | 41124.93 | 40779.33 | 41124.93 |  | 41124.93 | 82000.78 | 41124.93 | 6 | 41124.93 | 41000.39 |  |  |  | 40624.66 | [8 empty] | 205624.65 | 0 | 0 | 0 | 1. Negative variance due to CN issued : a. No software maintenance & support services and SPP Application after using the CD system. b. Reduction of 1 unit notebook due to BER (beyond Economic Repair) problem. c. No renewal license and support for Antivirus Software. 2. Some of hardware were not found during PM activities; UPS (1), PC (1), Barcode Reader (4) and printer laserjet (6). | 205624.65 | 204411.16 | -1213.49
9 | SPP-TAIPING | Ongoing | SPP V2.6 Implementation Project - Hospital Taiping Perak - HWSW Maint Renewal 14 Sept 2018 - 13 Sept 2020 (2 Years) | 123275.4 | 92456.55 | 92456.55 | 0 | 30818.85 | 61637.7 | 0 |  | 0 |  | 30818.85 | 30818.85 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 30818.85 |  | 0 |  | 0 |  | 0 |  | 61637.7 | 0 | 0 | 0 |  | 30818.85 | 30818.85 | 0
10 | SPP-TAIPING | Ongoing | SPP Application Maintenance-Hospital Taiping, Perak - Application Maint Renewal 18 Sept 2018 - 17 Sept 2020 (2 Years) | 180200.424 | 135150.33 | 135150.33 | 0 | 45050.094 | 90100.22 | 0 |  | 0 |  | 45050.11 | 45050.11 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 45050.11 |  | 0 |  | 0 |  | 0 |  | 90100.22 | 0 | 0 | 0 |  | 45050.11 | 45050.11 | 0
11 | SPP-CAS PHIS | Ongoing | Dataware - SPP CAS PHIS Integration 01 June 2017 - 31 Aug 2020 (3 Years++) | 396556.6 | 396556.6 | 293658.16 | 102898.44 | 0 | 396556.6 | [24 empty] | 0 |  |  |  |  | 0 | 0 | 0
12 | RHIS-LPPKN | Ongoing | Penyelenggaran Reproductive Health Information System (RHIS) 2.0 di LPPKN Bagi Tempoh Setahun 7 Feb 2020 - 6 Feb 2021 (1 Year) | 289100 | 0 |  | 0 | 289100 | 0 | [29 empty] | 0 | 0 | 0
13 | SPP-eKL | Ongoing | Tender Perkhidmatan Penyelenggaran Dan Sokongan Operasi Perkakasan, Perisian, Rangkaian Dan Aplikasi Untuk Sistem Pengurusan Pesakit (SPP) di Hospital Kuala Lumpur, Hospital Tengku Ampuan Rahimah Dan Hospital Kajang, Kementerian Kesihatan Malaysia 20 April 2020 - 19 April 2023 (3 Years) | 2102177.16 | 0 |  | 0 | 2102177.16 | 0 | [29 empty] | 0 | 0 | 0
|  |  |  | 81980716.404 | 39575642.33 | 39472743.89 | 102898.44 | 42405074.074 | 36568446.44 | 17025.77 | 17025.77 | 41124.93 | 40779.33 | 2673493.89 | 75868.96 | 18352671.787 | 2791890.78 | 3232093.3 | 6 | 292637.49 | 41000.39 | 199983.5 | 0 | 8747789.34 | 40624.66 | 75868.96 | 0 | 199983.5 | 0 | 0 | 0 | 5298350.13 | 0 | 39131022.597 | 1434067.01 | -1155883.25 | 0 |  | 33556820.007 | 3007195.89 | -30549624.117
OTHERS
1 |  |  |  |  | 0 |  | 0 | 0 | 0 | [29 empty] | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
|  |  | GRAND TOTAL (RM) | 462232405.6262 | 133158765.13 | 127345481.49 | 5813283.64 | 329073640.4962 | 98700892.1 | 4114071.86 | 4651223.92 | 1165535.41 | 3845151.34 | 6524775.39 | 4358003.22 | 22005657.097 | 6499068.9 | 9510616.83 | 6276387.19 | 6642936.63 | 2859169.05 | 2864063.56 | 2114676.15 | 9870199.82 | 3854193.26 | 3434976.99 | 0 | 343741.93 | 0 | 113600 | 0 | 6882055 | 0 | 73472230.517 | 7829852.73 | 4603902.47 | 8252792.08 |  | 62697856.597 | 34457873.03 | -28239983.567
|  |  | checking | 459460005.4662 |  |  |  |  | 98700892.1 | 4114071.86 |  | 2556757.85 |  | 6629073.24 |  | 25678731.147 |  | 5747726.22 |  | 6747234.48 |  | 1354061.98 |  | 9870199.82 |  | 3434976.99 |  | 343741.93 |  | 113600 |  | 6882055 |  | 73472230.517 |  |  |  | checking | 62697856.597 | 34457873.03 | -28239983.567
|  |  |  | 2772400.16 | New/ Unbudgeted |  |  |  | 0 | 0 |  | -1391222.44 |  | -104297.85 |  | -3673074.05 |  | 3762890.61 |  | -104297.85 |  | 1510001.58 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0 | 0
Note on P9: Aida Rashid: CN issued in April 2020
Note on R9: Aida Rashid: Reissue the Inv (to replace the Inv issued in March 2020)
Note on I10: Aida Rashid: Opportunity loss to project
Note on L10: Aida Rashid: RM184,035.43 (On Request-budget 3rd extension)
Note on L11: Aida Rashid: RM184,035.43 - On Request
Note on P12: Aida Rashid: Feb 2020
Note on R12: Aida Rashid: March 2020
Note on T12: Aida Rashid: April 2020
Note on N13: Aida Rashid: 1. MBPP - RM535,696.98 2. MBSP - RM150,731.04
Note on P13: Aida Rashid: 1. MBPP - RM373,124.44 2. MBSP - RM119,656.81
Note on R13: Aida Rashid: 1. MBPP - RM61,910.16 2. MBSP - RM7,015.71
Note on T13: Aida Rashid: MBPP - RM167,043.50 MBSP - RM36,617.49
Note on V13: Aida Rashid: MBPP - RM414,517.74 MBSP - RM79,775.41
Note on X13: Aida Rashid: MBPP - RM854,569.20 MBSP - RM254,116.60
Note on Z13: Aida Rashid: MBPP - RM612,253.01 MBSP - RM202,436.26
Note on N19: Aida Rashid: Jan 2020 1. RM658,657.50 - Bantuan sokongan teknikal 2. RM220,832.98 - Change Request 3. RM227,900.00 - Latihan 4. RM1,590,000.00 - Khidmat Audit Sistem myIMMS 5. RM83,300.00 - CN for Penalty Aug & Sept
Note on P19: Aida Rashid: Feb 2020 1. RM220,832.98 - Change Request 2. RM63,600 - Latihan 3. RM658,657.50 - Bantuan Sokongan Teknikal
Note on R19: Aida Rashid: March 2020
Note on T19: Aida Rashid: April 2020 1. RM658,657.50 - Technical Support 2. RM220,832.98 - CR 3. RM5,300 - Perluasan 4. (RM29,783.33) - CN for Aug - Sep 2019
Note on V19: Aida Rashid: May 2020 1. RM658,657.50 - Technical Support 2. RM220,832.98 - CR 3. (RM79,00.00) - CN for Nov-Dec 2019, Jan-Feb 2020 (4 mths)
Note on L20: Aida Rashid: JAN 2020
Note on N20: Aida Rashid: FEB 2020
Note on P20: Aida Rashid: MARCH 2020
Note on R20: Aida Rashid: APRIL 2020
Note on T20: Aida Rashid: MAY 2020
Note on V20: Aida Rashid: JUNE 2020
Note on X20: Aida Rashid: JULY 2020
Note on Z20: Aida Rashid: AUGUST 2020
Note on L21: Aida Rashid: DEC 2019
Note on N21: Aida Rashid: JAN 2020
Note on P21: Aida Rashid: FEB 2020
Note on R21: Aida Rashid: MARCH 2020
Note on V21: Aida Rashid: MAY 2020
Note on X21: Aida Rashid: JUNE 2020
Note on Z21: Aida Rashid: JULY 2020
Note on L23: Aida Rashid: DEC 2019
Note on N23: Aida Rashid: JAN 2020
Note on P23: Aida Rashid: FEB 2020
Note on R23: Aida Rashid: MARCH 2020
Note on R34: Aida Rashid: Revise amount (to include sst)
Note on E36: Aida Rashid: Original Contract value RM10,123,738.81
Note on I37: Aida Rashid: CN issued in Y2019/Y2020
Note on N41: Aida Rashid RM345.60 - CN
Note on R41: Aida Rashid: FEB 2020 & MARCH 2020
Note on T41: Aida Rashid: 1. Credit Note for Invoice No. IV-20000313 Dated 28/02/2020 2. Debit Note for Credit No. CN-20000013 Dated 28/02/2020
Note on V41: Aida Rashid: APRIL 2020
Note on Z41: Aida Rashid: MAY 2020
Note on E58: Aida Rashid: 1. JIM - Autocropping 2. LPPKN 3. SPP - eKL *highlighted in yellow row
Note on M58: Aida Rashid: The variance due to adjustment made at JPJ mySIKAP Maint-4th ext (based on latest payment schedule in SST).
Note on O58: Aida Rashid: The variance due to adjustment made at JPJ mySIKAP Maint-4th ext (based on latest payment schedule in SST).
Note on Q58: Aida Rashid: The variance due to adjustment made at JPJ mySIKAP Maint-4th ext (based on latest payment schedule in SST).
Note on S58: Aida Rashid: The variance due to adjustment made at JPJ mySIKAP Maint-4th ext (based on latest payment schedule in SST).
Note on U58: Aida Rashid: The variance due to adjustment made at JPJ mySIKAP Maint-4th ext (based on latest payment schedule in SST).
Note on W58: Aida Rashid: The variance due to adjustment made at JPJ mySIKAP Maint-4th ext (based on latest payment schedule in SST).

## Billing Status (hidden)
BILLING STATUS AS AT 31/12/2019
e | Main Project | Status | Project Name | Project Value (RM) | Total Billed (RM) as at 31/12/2019 | Paid (RM) | Balance to Pay (RM) | Balance to Bill (RM) | Total Billing as at 31/12/2018 | 2019 BILLING PLAN/PROJECTION | [24 empty] | 2020 | 2021 | Remaining | Remarks | 2019 Billing Up-To-Date Summary (As at 31/12/2019)
[10 empty] | JAN |  | FEB |  | MAR |  | APR |  | MAY |  | JUN |  | JUL |  | AUG |  | SEPT |  | OCT |  | NOV |  | DEC |  | TOTAL
[9 empty] | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | [5 empty] | Planned | Actual | Variance
1 | JPJ | Closed | JPJ Maintenance | 6569161 | 6569155.92 | 6569155.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 0 | 0
2 | JPJ | Closed | JPJ Revamp | 282000000 | 282000000 | 281851000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. RM149,000 credit note imposed due to LAD. | 0 | 0 | 0
3 | JPJ | Closed | eAuto | 194643 | 194643 | 194643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 0 | 0
4 | JPJ | Closed | PUSPAKOM | 824860.5 | 837386.72 | 795180.07 | 42206.65 | -12526.22 | 837386.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
5 | JPJ | Closed 2019 | PRISM | 177000000 | 176999773 | 176999773 | 0 | 227 | 171719473 | 0 | 0 | 0 | 0 | 0 | 0 | 1095395 | 0 | 0 | 1095395 | 0 | 0 | 3089607 | 0 | 0 | 3089607 | 0 | 0 | 1095395 | 1095298 | 0 | 0 | 0 | 0 | 5280397 | 0 | 0 | 0 | Billing completed with RM97 discount requested by JPJ | 5280397 | 5280300 | -97
6 | JPN | Closed | JPN Maintenance | 120628000 | 119392168.73 | 119392168.73 | 0 | 1235831.27 | 119392168.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51184.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. (Balance of RM1,232,386.28 will not be billed due to unutilize budget of RM301,764.47 for Training Services and RM930,621.81 for CR Services) | 0 | 51184.75 | 51184.75
7 | JPN | Closed | JPN Boomgate | 169260.08 | 162687.5 | 162687.5 | 0 | 6572.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. Unutilized amount of RM6,572.58 due to customer request (training services and CR not required) | 0 | 0 | 0
8 | JIM | Closed | JIM Maintenance (2014-2016) | 27480000 | 27480000 | 27480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. Credit note of RM196,000 was imposed due to 2 undelivered scopes (CPR and PM). | 0 | 0 | 0
9 | JIM | Closed | JIM Maintenance (2016-2017) | 21475600 | 17398423.81 | 17398423.81 | 0 | 4077176.19 | 17398423.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total of RM3,692,170.80 cannot be billed due to incomplete Transformation Development (RM2,660,600), unutilized budget of RM106,000 for Branch Extension Services, RM422,600 for Training Services, RM407,570 for Integration Services and RM95,400 for CR services. Credit Note issued for invoice No 1813001420 dated 13/7/2017 (Audit Sistem Aplikasi myIMMs Bagi Tahun Kedua) | 0 | 0 | 0
10 | JIM | Closed 2018 | JIM-BESTINET/FWCMS | 3600000 | 3957454.26 | 3676800 | 280654.26 | -357454.26 | 3744000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213454.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Surplus billing from project value due to GST since 2015 | 0 | 213454.26 | 213454.26
11 | JIM | Closed | JIM-STAR EMGS | 560000 | 560000 | 560000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 0 | 0
12 | JIM | Closed | JIM-NZ Gemilang/PDRM | 124087 | 124087 | 124087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 0 | 0
13 | JIM | Closed | JIM-TALENT CORP | 151800 | 151800 | 151800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 0 | 0
14 | JIM | Closed | JIM-Innovexion | 203384.32 | 203384.32 | 203384.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 0 | 0
15 | JIM | Closed | JIM-Vista Kencana | 40280 | 40280 | 40280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980190.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 980190.48 | 980190.48
16 | JIM | Closed | JIM-MARDI | 50880 | 0 | 0 | 0 | 50880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project close. Mardi to reissue new PO once they are ready with integration scope/work. | 0 | 0 | 0
17 | JIM | Ongoing | JIM-myEG (Transaction Basis) | 2400000 | 2711883.08 | 2606857.22 | 105025.86 | -311883.08 | 2039521.9 | 0 | 0 | 0 | 133455.59 | 0 | 53473.82 | 0 | 68179.2 | 0 | 62990.5 | 0 | 85147.68 | 0 | 46652.72 | 0 | 66251.06 | 0 | 51184.75 | 0 | 50408.3 | 0 | 0 | 0 | 54617.56 | 0 | 0 | 0 | 0 | Billing based on Transaction | 0 | 672361.18 | 672361.18
18 | MOH | Closed | SPP V3.0 Rollout Project-HRPZ II (EOT) | 184299.97 | 19229488.22 | 184299.97 | 19045188.25 | -19045188.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 0 | 0
19 | MOH | Closed | SPP V2.6 Maintenance-HTJ & HPD | 1050402.25 | 23542.5 | 982324.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. RM118,858 credit note was imposed due to reduction of preventive maintenance price for hardware. Few hardware has been decided by Hospital to dropped from PM scope. | 0 | 0 | 0
20 | MOH | Closed | SPP V2.6 Maintenance-eKL | 1245514 | 73394 | 1244625 | 0 | 1172120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. RM889 credit note imposed due to reduction of preventive maintenance price for switches. Switches was not found due to movement during building renovation work. | 0 | 0 | 0
21 | MOH | Closed 2018 | SPP V2.6 Implementation-Hospital Taiping, Perak | 449611.91 | 491098 | 449611.91 | 41486.09 | -41486.09 | 449611.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30818.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Closure in progress. Billing completed. | 0 | 30818.85 | 30818.85
22 | MOH | Closed | SPP-PHIS Integration Project | 107073 | 657223.5 | 107073 | 550150.5 | -550150.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45050.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 45050.11 | 45050.11
23 | MOH | Closed | HRPB - Server Upgrade | 442881 | 80000 | 442881 | -362881 | 362881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 0 | 0
24 | OTH | Closed | Data Center- HQE, KK | 859882 | 0 | 859882 | -859882 | 859882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 0 | 0
25 | MOH | Closed | DC Upgrade - HSNI, Batu Pahat | 934409 | 934409 | 934409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 63600 | 63600
26 | MOH | Closed | DC Upgrade - HTAR Klang | 943381 | 943381 | 943381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 0 | 0
27 | MOH | Closed 2019 | SPP V2.6 Maintenance-HBTNG | 952654.86 | 895550.58 | 895550.58 | 0 | 57104.28 | 818794.59 | 0 | 0 | 0 | 0 | 79387.91 | 0 | 0 | 0 | 0 | 76755.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79387.91 | 0 | 0 | 0 | Billing completed. Variance due to service not delivered (i.e Antivirus Sotware & attendance issue) | 79387.91 | 76755.99 | -2631.92
28 | MOH | Closed 2019 | SPP V2.6 Maintenance-eKL (Renewal) | 2332000 | 2307221.18 | 2307221.18 | 0 | 24778.82 | 2113649.31 | 0 | 0 | 0 | 0 | 194333.33 | 193571.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194333.33 | 0 | 0 | 0 | Billing completed. Variance due to services not delivered (i.e lost of hardware). | 194333.33 | 193571.87 | -761.46
29 | MOH | Ongoing | Clinical Documentation | 30101218.92 | 26191691.74 | 26191691.74 | 0 | 3909527.18 | 24152080.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3749940.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1823673.04 | 2039610.76 | 0 | 0 | 5573613.07 | 0 | 0 | 0 | Next billing to carry forward in Y2020. | 5573613.07 | 2039610.76 | -3534002.31
30 | DEF | Closed | Enhanced Training Aid System (ETAS) | 31000000 | 31000000 | 31000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 0 | 0
31 | DEF | Closed | IGLA Weapon System | 2925240 | 2925240 | 2925240 | 0 | 0 | 2925240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closure in progress. Billing completed based on LO only. | 0 | 0 | 0
32 | DEF | Transferred to PMC | Arthur Radar Weapon Locating System (WLS) | 6890000 | 5015484.55 | 3976324.55 | 1039160 | 1874515.45 | 3387098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - Submitted 4 Invoices under June-2018 Billing for RM 1,484,367.47. However Invoice for LO0027 RM 1,098,456.80 was rejected. - Variance of billing: lower amt of invoice in October 2018 (RM1,039,160) for same item in but diff version in June (RM1,098,456.80) - Monitored until Oct 2018 | 0 | 0 | 0
33 | DEF | Transferred to PMC | Action Speed Tactical Trainer (ASTT) | 4500000 | 140093.84 | 129532 | 10561.84 | 4359906.16 | 120240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Monitored until October 2018 | 0 | 0 | 0
34 | DEF | Closed | JHEV Maintenance | 196091 | 196091 | 196091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 0 | 0
35 | DEF | Transferred to PMC | Asean Customs Transit System (ACTS) | 1425000 | 914008.74 | 914008.74 | 0 | 510991.26 | 791965.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Variance due to exhange rate difference between planned (xchg rate=4.75) and actual (xchg rate=4.87) - Monitored until Oct 2018 | 0 | 0 | 0
36 | MOH | Closed 2019 | SPP V3.1 Rollout Project - Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu | 2591208.16 | 2534333.69 | 2534333.69 | 0 | 56874.47 | 1914663.77 | 0 | 0 | 0 | 0 | 215934.02 | 194980.21 | 0 | 0 | 0 | 0 | 215934.02 | 0 | 0 | 0 | 0 | 211235.45 | 215934.02 | 213454.26 | 0 | 0 | 0 | 0 | 0 | 0 | 647802.06 | 0 | 0 | 0 | Billing completed. Variance due to services not delivered (i.e lost of hardware, obsolete of hardware and attendance issue). | 647802.06 | 619669.92 | -28132.14
37 | JPJ | Closed | mySIKAP Maintenance(Software License Renewal) 2015 | 3399877 | 3399877 | 3399877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 0 | 0
38 | JPJ | Closed | mySIKAP Maintenance(Software License Renewal) JAN-OCT 2016 | 11391672.66 | 11391672.66 | 11391672.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 0 | 0
39 | JPJ | Closed 2018 | mySIKAP Maintenance (2016 - 2018) | 79768327.34 | 77594184.07 | 77594184.07 | 0 | 2174143.27 | 77594184.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - Additional budget for extension Jan - Jun 2019 = RM18,724,343.50 - Unclaimable OR (2017 + 2018) = RM1,756,227.18, - Unclaimable GST (Jun, Jul & Aug 2018) = RM408,253.13; - Credit Note for scanner not done in PM activity = RM9,662.96 | 0 | 0 | 0
40 | MOH | Closed | HKL-Bekalan Perkhidmatan Penggantian Server | 438043 | 438043 | 438043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project closed. | 0 | 0 | 0
41 | LPPKN | Closed 2019 | Reproductive Health Information System (RHIS) - LPPKN | 1901901.21 | 1901901.21 | 1901901.21 | 0 | 0 | 1901901.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
42 | MOH | Closed 2018 | SPP V2.6 Apps Maintenance Project-HTPG | 182320 | 179740 | 136740 | 43000 | 2580 | 91160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Variance due to GST | 0 | 0 | 0
43 | FOM | Ongoing | FOMEMA MYIMM Biometric Integration | 48230000 | 19817957.9 | 18378011.47 | 1439946.43 | 28412042.1 | 14058172.18 | 0 | 0 | 0 | 0 | 0 |  | 1439946.43 | 1439946.43 | 0 | 0 | 0 | 1439946.43 | 1439946.43 | 0 | 0 | 0 | 1439946.43 | 0 | 0 | 1439946.43 | 0 | 0 | 1439946.43 | 1439946.43 | 5759785.72 | 5759785.72 | 5759785.72 | 16892470.66 |  | 5759785.72 | 5759785.72 | 0
44 | DEF | Transferred to PMC | SUKHOI-30MKM - TOFT, CBT & Infra Maintenance | 258000000 | 216548000 | 207948000 | 8600000 | 41452000 | 199348000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Monitored until October 2018 | 0 | 0 | 0
45 | JPJ | Closed 2018 | Next Generation Firewall | 2752960 | 2752960 | 2752960 | 0 | 0 | 2752960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Warranty support | 0 | 0 | 0
46 | MOH | Ongoing | RIS PACS HIS@KKM Fasa I | 10123738.81 | 7455217.95 | 7455217.95 | 0 | 2668520.86 | 4775348.5 | 0 | 0 | 0 | 0 | 2024747.764 | 0 | 0 | 0 | 979614.322 | 0 | 0 | 0 | 2024747.764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2679869.45 | 0 | 0 | 5029109.85 | 0 | 0 | 0 | Next billing to carry forward in Y2020 (Training, CM, BR and services). | 5029109.85 | 2679869.45 | -2349240.4
47 | MOH | Ongoing | SPP CAS PHIS Integration | 396556.6 | 396556.6 | 293658.16 | 102898.44 | 0 | 190759.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205796.88 | 95173.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95173.58 | 110623.3 | 0 | 0 | Planned billing 2020 has been done during billing for June 2019. | 95173.58 | 205796.88 | 110623.3
48 | JIM | Ongoing | myIMMS Maintenance (2017-2020) | 42430740 | 29230993.19 | 29161603.19 | 69390 | 13199746.81 | 17147307.26 | 0 | 0 | 1076473.46 | 1043690.48 | 1076473.46 | 1038490.48 | 1689418.46 | 966690.48 | 1076473.46 | 1099090.48 | 1076473.46 | 911290.48 | 1076473.46 | 943090.48 | 1076473.46 | 1054891.13 | 1076473.46 | 980190.48 | 1689418.46 | 912990.48 | 1076473.46 | 2131880.48 | 2152946.92 | 1001390.48 | 14143571.52 | 11139861.22 | 0 | 0 | Variance due to :- 1. Billing for System Audit not done yet. Target Jan 2020. 2. Not able to execute activities for Peluasan since it depends on IMMs request. 3. Not able to execute overseas training - pending approval from KDN. 4. Billing for Dec 2019 wil be submitted in Jan 2020. | 14143571.52 | 12083685.93 | -2059885.59
49 | JTK | Closed | JTKSM WNP | 287600 | 212610 | 0 | 212610 | 74990 | 212610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Warranty support | 0 | 0 | 0
50 | JTK | Closed | JTKN Hardware Supply | 45468 | 45468 | 45468 | 0 | 0 | 45468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Warranty support | 0 | 0 | 0
51 | JPJ | Closed 2018 | JPJ Mobile Handheld Enforcement | 931350 | 931350 | 931350 | 0 | 0 | 931350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
52 | JIM | Closed | JIM - CIDB | 25864 |  |  |  |  | 25864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
53 | JIM | Closed | JIM - Borderpass Travel Sdn Bhd | 55000 | 55000 | 55000 | 0 | 0 | 11681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work done and billed. Payment received 3/7/2018. Project closure | 0 | 0 | 0
54 | JIM | closed | JIM - INTIPADU TECHNOLOGY | 83184 | 23542.5 | 0 | 23542.5 | 59641.5 | 23542.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
55 | JIM | Closed 2018 | JIM - MDEC eXpat System | 137588 | 73394 | 137588 | -64194 | 64194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work done and billed. Payment received 3/7/2018. Project closure done | 0 | 0 | 0
56 | JIM | Closed 2018 | JIM - TALENTCORP | 79500 | 491098 | 79500 | 411598 | -411598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work done and billed. Payment received. Project closure done | 0 | 0 | 0
57 | JIM | Closed 2019 | JIM - MDEC MTEP System | 73394 | 73394 | 73394 | 0 | 0 | 73394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
58 | JIM | closed 2018 | JIM - DATASONIC | 491098 | 491098 | 0 | 491098 | 0 | 491098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
59 | JIM | Ongoing | JIM - MAHB QMS Integration | 625292 | 657223.5 | 640285.76 | 16937.74 | -31931.5 | 657223.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
60 | JIM | Closed 2019 | JIM - EMGS (Maintenance) | 164800 | 164800 | 164800 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84800 | 89600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89600 | 0 | 0 | 0 | Amount billed is for Year 2 Maintenance and Support. Variance due to over plan for SST. | 89600 | 84800 | -4800
61 | JIM | Closed | JIM - EMGS (CR) | 15359 | 14490 | 14490 | 0 | 869 | 14490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Variance due to not in billing plan | 0 | 0 | 0
62 | JIM | Closed | JIM - UKSB VLN Integration | 20988 | 19800 | 19800 | 0 | 1188 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Variance due to not in billing plan | 0 | 0 | 0
63 | MOH | Ongoing | SPP V2.6 Implementation Project - Hospital Taiping Perak (HTPG) Extension | 123275.4 | 61637.7 | 61637.7 | 0 | 61637.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30818.85 | 0 | 0 | 30818.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30818.85 | 30818.85 | 0 | 0 | 0 | 0 | 0 | 61637.7 | 61637.7 | 0 | 0 |  | 61637.7 | 61637.7 | 0
64 | MOH | Ongoing | SPP Application Maintenance-Hospital Taiping, Perak (2018 - 2020) | 180200.424 | 90100.22 | 90100.22 | 0 | 90100.204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45050.11 | 0 | 0 | 45050.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45050.11 | 45050.11 | 0 | 0 | 0 | 0 | 0 | 90100.22 | 90100.204 | 0 | 0 |  | 90100.22 | 90100.22 | 0
65 | JPJ | Ongoing | New Generation FireWall - NGFW (2018 - 2020) | 2810525.87 | 1647031.88 | 1647031.88 | 0 | 1163493.99 | 313667 | 0 | 0 | 0 | 0 | 0 | 0 | 1242889.59 | 0 | 0 | 1242889.59 | 0 | 0 | 30158.43 | 0 | 0 | 30158.43 | 0 | 0 | 30158.43 | 0 | 0 | 60316.86 | 0 | 0 | 1303206.45 | 30158.43 | 0 | 0 | Planned billing 2020 has been done during billing for June 2019. | 1303206.45 | 1333364.88 | 30158.43
66 | myIPO | Closed 2019 | myIPO IV&V | 252500 | 252500 | 252500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101000 | 101000 | 151500 | 151500 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 252500 | 0 | 0 | 0 |  | 252500 | 252500 | 0
67 | JIM | Ongoing | JIM-BESTINET/FWCMS (2018 - 2020) | 2289600 | 890400 | 318000 | 572400 | 1399200 | 0 | 63600 | 0 | 63600 | 0 | 63600 | 0 | 63600 | 381600 | 63600 | 0 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 127200 | 63600 | 63600 | 63600 | 63600 | 763200 | 1399200 | 0 | 0 | Positive Variance due to amount billed for Nov & Dec 2018 which is not in Billing Plan for Y2019. | 763200 | 890400 | 127200
68 | JPJ | Closed 2019 | mySIKAP Maintenance Extension (Jan-Jun 2019) | 18724343.5 | 17904486.5 | 17904486.5 | 0 | 819857 | 0 | 0 | 0 | 1520738.54 | 0 | 1520738.54 | 0 | 1645532.34 | 1609619.54 | 9315094.5 | 3166270.88 | 1520738.54 | 57430.8 | 3201501.04 | 10017343.44 | 0 | 1520738.54 | 0 | 0 | 0 | 1533083.3 | 0 | 0 | 0 | 0 | 18724343.5 | 0 | 0 | 0 | Variance amount will not be billed due to no requirement for some software license renewal. These softwares' functions have been replaced by other softwares. | 18724343.5 | 17904486.5 | -819857
69 | MOH | Ongoing | Critical Care Information System (CCIS) | 33179367.26 | 0 | 0 | 0 | 33179367.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000000 | 0 | 0 | 0 | 0 | 0 | 8000000 | 25179367.26 | 0 | 0 | Variance due to delay in HW/Equipment deployment which requires decision from KKM for the changes of HW/Equipment specifications. Next billing to carry forward to 2020. (Infra, HW/SW, Training, CM, CCIS App and deployment services) | 8000000 | 0 | -8000000
70 | MOH | Ongoing | Sistem Pengurusan Pesakit (SPP) Permaisuri Bainun, Ipoh (16 JUNE 2019-15 JUNE 2020) | 480755.16 | 283848.22 | 283848.22 | 0 | 196906.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80125.86 | 0 | 40062.93 | 116162.5 | 40062.93 | 80125.86 | 80125.86 | 87559.86 | 240377.58 | 240377.58 | 0 | 0 | Underbudgeted | 240377.58 | 283848.22 | 43470.64
71 | PSP | Ongoing | Penang Smart Parking (PSP) - Majlis Bandaraya Pulau Pinang (MBPP) - Majlis Perbandaran Seberang Prai (MPSP) | 259686000 | 85518.42 | 85518.42 | 0 | 259600481.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5407.06 | 0 | 16616.6 | 10000 | 27406.92 | 10000 | 36087.84 | 20000 | 37085783.0829 | 37085783.0829 | 185428915.4143 | Billing based on collection /transaction. | 20000 | 85518.42 | 65518.42
72 | JPJ | Closed 2019 | mySIKAP Maintenance Extension (July-Oct 2019) - 2nd extension | 7016592 | 4833869.24 | 4833869.24 | 0 | 2182722.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950554.04 | 4833869.24 | 2066037.96 |  | 7016592 | 2182722.76 | 0 | 0 | Allocation for On Request could not be fully utilized within the contract period since LOA was only received in September 2019. The amount to be carried forward to 3rd extension (Nov -Dec 2019) | 7016592 | 4833869.24 | -2182722.76
73 | JPJ | Ongoing | mySIKAP Maintenance Extension (Nov-Dec 2019) - 3rd extension | 3508296.13 | 1764232.2 | 1764232.2 | 0 | 1744063.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727084.5 | 3508296.13 | 37147.7 | 3508296.13 | 1744063.93 | 0 | 0 | Billing for Dec 2019 will be submitted in Jan 2020. | 3508296.13 | 1764232.2 | -1744063.93
74 | MOH | Ongoing | Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu - Perolehan Peralatan Tambahan 01 Nov 2019 - 28 Feb 2020 (4 mths) | 496000 | 0 | 0 | 0 | 496000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 496000 | 0 | 0 | The billing to carry forward to Y2020. | 0 | 0 | 0
75 | MOH | Ongoing | Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu - Perkhidmatan Penyelenggaraan 01 Oct 2019 - 31 Dec 2019 (3 mths) | 226639 | 187492.8 | 187492.8 | 0 | 39146.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187492.8 | 0 | 13800 | 0 | 0 | Next billing to carry forward to Y2020. | 0 | 187492.8 | 187492.8
|  |  |  | 648297599.304 | 299339614.8 | 297033016.33 | 2306598.47 | 348957984.504 | 241955956.92 | 63600 | 0 | 2660812 | 1177146.07 | 5276215.024 | 1581516.38 | 7404150.78 | 4617535.65 | 11434782.282 | 6819261.4 | 6626686.05 | 2848012.27 | 11110807.704 | 11070686.64 | 1140073.46 | 6036481.61 | 2876079.77 | 1389705.51 | 10994503.78 | 5291705.61 | 7964363.47 | 13643764.07 | 9320953.3 | 2907842.67 | 76873027.62 | 85533481.1869 | 42845568.8029 | 202321386.0743 |  | 76873027.62 | 57383657.88 | -19489369.74
Note:
Note on N22: Aida Rashid: charges for Dec 2018 & Jan 2019
Note on P22: Aida Rashid: charges for Feb
Note on R22: Aida Rashid: charges for Mar
Note on T22: Aida Rashid: charges for April
Note on V22: Aida Rashid: Charges for May 2019
Note on X22: Aida Rashid: Charges for June 2019
Note on Z22: Aida Rashid: Charges for July 2019
Note on AB22: Aida Rashid: Charges for August 2019
Note on AD22: Aida Rashid: Charges for Sept 2019
Note on AH22: Aida Rashid: Charges for Oct 2019
Note on F37: Norhasina Hamzah: Variance from last report due to CN and lower amt of invoice in October 2018 (RM1,039,160) for same item in but diff version in June (RM1,098,456.80)
Note on AB44: Aida Rashid: '- Additional budget for extension Jan - Jun 2019 = RM18,724,343.50 - Unclaimable OR (2017 + 2018) = RM1,756,227.18, - Unclaimable GST (Jun, Jul & Aug 2018) = RM408,253.13; - Credit Note for scanner not done in PM activity = RM9,662.96
Note on F49: Norhasina Hamzah: Until Oct 2018
Note on AJ52: Norhasina Hamzah: Billing done in June 2019
Note on R53: Aida Rashid: Less: Credit Note Penalty for August 2018 : RM4,100.00 Credit Note Penalty from Sept 2018 - Nov 2018 : RM9,400.00
Note on T53: Aida Rashid: Less Credit Note Penalty for December 2018 : RM3,000
Note on AD53: Aida Rashid: CN Jan to March
Note on AF53: Aida Rashid: 1. RM658,657.50 - Bantuan Sokongan Teknikal Oct '19 2. RM220, 832.98 - CR Oct '19 3. RM26,500 - Training Oct '19 4. RM612,945 - PM Thn ke 2 (1/2) 5. RM612,945 - PM Thn ke 2 (2/2)
Note on AH53: Aida Rashid: 1. RM658,657.50 - Bantuan Sokongan Teknikal Nov '19 2. RM220, 832.98 - CR Nov '19 3. RM121,900 - Training Nov '19
Note on E64: Norhasina Hamzah: Change value without GST
Note on Q69: Norhasina Hamzah: Change in value to include SST
Note on T69: Aida Rashid: include SST
Note on AC69: Norhasina Hamzah: Change in value to include SST
Note on AF70: Aida Rashid: Q3 & Q4
Note on AJ70: Aida Rashid: Billing done in Nov 2019
Note on R72: Aida Rashid: Billing for Nov 2018 - April 2019
Note on V72: Aida Rashid: May 2019
Note on X72: Aida Rashid: June 2019
Note on Z72: Aida Rashid: July 2019
Note on AB72: Aida Rashid: August 2019
Note on AD72: Aida Rashid: Sept 2019 & Oct 2019
Note on AF72: Aida Rashid: Nov 2019
Note on AH72: Aida Rashid: Dec 2019
Note on R73: Aida Rashid: Feb 2019 1) RM1,520,738.54 - CM 2) RM88,881.00 - OR
Note on T73: Aida Rashid: Jan 2019 1) RM1,520,738.54 - CM March 2019 1) RM1,645,532.34 - CM
Note on V73: Aida Rashid: March 1. RM57,430.80 - OR
Note on X73: Aida Rashid: April 2019 1) RM9,315,094.50 - CM 2) RM818,489.60 - Credit Note May 2019 1) RM1,520,738.54 - CM
Note on Z73: Aida Rashid: June 2019 1) RM1,520,738.54 - CM
Note on AD75: Aida Rashid: Billing for June, July & Aug CN for June 2019
Note on AF75: Aida Rashid: 1. Billing for Sept & Oct 2. CN for Oct
Note on AH75: Aida Rashid: Billing for Nov & Dec
Note on F76: Norhasina Hamzah: Amount received
Note on G76: Norhasina Hamzah: Amount Received
Note on AD76: Aida Rashid: collection in Oct
Note on AF76: Aida Rashid: Collection in Nov
Note on AH76: Aida Rashid: Collection in Dec 2019
Note on AE77: Aida Rashid: Sept : 1.Maint & Support - RM1,614,440.42 2.On Request - RM316,487.38 Oct : 1. Maint & Support - RM1,553,833.86 2. On Request - RM1,465,792.38
Note on AF77: Aida Rashid: Sept : 1.Maint & Support - RM1,614,440.42 2.On Request - RM316,487.38 Oct : 1. Maint & Support - RM1,553,833.86 2. On Request - RM1,349,107.58
Note on AG77: Aida Rashid: On Request
Note on AF78: Aida Rashid: 1. Maintenance for Nov 2019
Note on AH78: Aida Rashid: 1. On Request for Nov 2019

## Outstanding Payment
Outstanding Payment to Vendor as of 31/08/2020
NO | PROJECT | VENDOR | DESCRIPTION | AMOUNT (RM) | INVOICE NO.
1 | Internal Security | I World Technology Sdn Bhd | Latihan Teknikal – Microsoft Project 2016 (Beginner) | 10000 | INV20191118
2 |  | I World Technology Sdn Bhd | Latihan Teknikal – Android Application Development | 12000 | INV20200714
3 |  | Indah Putrajaya Sdn Bhd | Penginapan untuk peserta latihan Passport and Dokumen Perjalanan (Passport Online) - Day 1 | 1750 | BQT0720/042
4 |  | Indah Putrajaya Sdn Bhd | Penginapan untuk peserta latihan Passport and Dokumen Perjalanan (Passport Online) - Day 2 | 3500 | BQT0720/052
5 |  | Indah Putrajaya Sdn Bhd | Penginapan untuk peserta Latihan Modul Kawalan Sesi 1 2020 | 7700 | BQT0820/012
34950

## Risk List okt 2020
SUMMARY OF REPORTED RISKS FOR PROJECT DELIVERY (PSG).
Reported as at 30/6/2020.
No. | Project | TYPE (INT / EXT) | RISK DESCRIPTION | RISK IMPACT | Mitigation Action Plan | WHO | WHEN | Status of Mitigation | OLD STATUS | OLD STATUS | OLD STATUS | OLD STATUS | OLD STATUS | OLD STATUS | OLD STATUS | PREVIOUS STATUS | CURRENT STATUS
| TRANSPORT - JPJ | [7 empty] | As at 28/2/2020 | As at 31/3/2020 | As at 30/4/2020 | As at 30/5/2020 | As at 30/6/2020 | As at 31/7/2020 | As at 31/8/2020 | As at 15/10/2020 | As at 30/10/2020
1 | JPJ MySIKAP - EXT IV | Human resource - Internal | Due to MCO, mySIKAP developers travel to BTD IT building at Cyberjaya are limited. Access to mySIKAP system can only be done inside BTD IT building. Current CR development is put on hold since mySIKAP developers can’t access mySIKAP system outside BTD IT building. | ● Movement restriction may greatly impacted the SLA to JPJ, which may result in monetary penalty. | Mitigattion ●1. Get approval from BTD IT for VPN access so that mySIKAP developers can develop the CR/On Request from home. ● 2. Official letter from JPJ for the support staff to travel cross district to support JPJ Branches. 3. Inform BTD/IT that CR development to be put 'on-hold' due to MCO | PD, PM, ADM | Before 30/6/2020 | Mitigation in-Progress : 1. To send Letter / Notice of Force Majeure if MCO will be extended beyond 29/4/2020.(Pending) 2. Request official Letter from JPJ for essential service, so staff can go cross-district to continue support.(Done) 3. Email/ Inform BTD/IT that CR development is 'on Hold' due to MCO.(Done) | NONE | No PSC - MCO (18/3-14/4) - Mitigation action items are still in-progresss. | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items - Status Quo. | PSC #3/2020 - Project team started to work again on CRs from 1/5/2020 in order to complete all works before 30/6/2020. In Progress. | PSC #4/ 2020 - Was separately conducted by HTP-CORE03 management. In Progress. | Risk occurred. Minor bugs and manageable In Progress. | Was separately conducted by HTP-CORE03 management. Risk occurred. Minor bugs and manageable In Progress. | Was separately conducted by HTP-CORE03 management. Risk occurred. Minor bugs and manageable Closed.
2 | JPJ MySIKAP - EXT IV | Human resource - Internal | There is a risk that application resources cannot be released from their current assigned-project to execute application CR which could result in late CR delivery | • Non-dedicated developer resources could lead to potential risk of not being able to complete task on-time. (Note: currently some JPJ staff is shared with other proj like PSP) | Mitigation 1) Staff assigned to specific project based on % involvement. Certain staff is assigned to multi-projects. 2) SDC to strategize & prioritize on resource sharing with other project when multi-tasking. | SDC, PD, PM | Before 30/6/2020 | Mitigation in-Progress : 1. Staff can continue to develop on CR even after being co-located at other project.(ie doing multi-tasking) | NONE | No PSC - MCO (18/3-14/4) - Mitigation action items are still in-progresss. | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items - Status Quo. | PSC #3/2020 - As per above status, starting 1 May 2020, project team return to JPJ Cyberjaya. In Progress. | PSC #4/2020 - Due to MCO Govt/JPJ is late in making decision on re-hiring/ contract renewal on MySIKAP maintenance which should commence from 1/7/2020. Project Team will report duty to JPJ CyberJaya potentially from 1/8/2020. In Progress. | Was separately conducted by HTP-CORE03 management. | Was separately conducted by HTP-CORE03 management. | Was separately conducted by HTP-CORE03 management. Closed
3 | JPJ MySIKAP - EXT IV | Project Mgmt - Finance | There is a risk that project deliverables are behind schedules because vendors payment might be delayed due to finance processing SOP (which require more time) which could result in SLA penalty done july | •Risk not triggered yet but potential to be a threat | Mitigation •Follow up closely with Finance Team and requesting Finance to commit for faster payment To Vendor. - Prioritize the payments | Finance, PD, PM, PMO | On-going | Mitigation in-Progress : 1. Formally reporting to Finance manager on outstanding payments to Vendor. (Vendor List) (On going) | NONE | No PSC - MCO (18/3-14/4) - Escalate to Finance representative in PSC session regularly. | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items is Status Quo. - Payment by FIN based on priority. | PSC #3/2020 - Mitigation executed accordingly. All payments to Vendors still in progress. | PSC #4/2020 - Mitigation on ensuring payments to all vendors are in progress. | Was separately conducted by HTP-CORE03 management. | Was separately conducted by HTP-CORE03 management. | Was separately conducted by HTP-CORE03 management. Closed
| LOCAL COUNCIL - PENANG SMART PARKING (MBPP) | [9 empty] | As at 30/4/2020 | As at 30/5/2020 | As at 30/6/2020 | As at 31/7/2020 | As at 31/8/2020 | As at 31/8/2020
1 | Penang Smart Parking (PSP) | Financial - External | Revenue streams for the business depends on effective Council's Enforcement drive to ensure public pays for parking space. (for both MBPP and MBSP) | Medium - Enforcement Systems need a quick stabilization period, and have full enforcement functionalities upon successful Integration with all Sensors equipment. | Mitigation : 1. To expedite ENF System's full Integration with Sensor's functionalities.(In progress) Target on-ground deployment before End March 2020 (Has been 2-mth delayed due to longer MCO). 2. To develop an efficient 'targeted-enforcement' methods using auto lot-no detection (for unpaid parking).(In progress) 3. Ensure our PSP system able to Alert and monitor the Councils via Enforcement Dashboard.(In progress) | AD Team | Target by30/4/2020 | Mitigation in Progress. 1. Phase-1 Enforcement was deployed on 24/9/2019 but require improvement. 2. Phase-2 Enforcement application Upgrades completed on 30/6/2020. New version ENF live on 30/6/2020. Already being used with enhanced photo clarity. 3. Dashboard pengurusan (Enforcement) already completed since 30/4/2020. Already being used with Data-data penggunaan NTK. | (PSC 2/2020) - Dashboard Enhancement (50% completed) Target Pilot 24/3/2020. Warden Trafik (80 % Completed) Target Pilot - 16/3/2020. Pendakwaan TLK (80% Completed). Target Pilot - 18/3/2020. In Progress. | No PSC - MCO (18/3-14/4) - SIT testing target on 23/4/2020 - Target Pilot on 30/4/2020 | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items - Status Quo. | PSC #3/2020 - Due to MCO, UAT Testing was delayed. AD Team targets to perform Testing/ UAT with ENFORCEMENT Unit on 4/6/2020. In Progress. | PSC #4 - All mitigation actions in progress Target for final Signoff on 31/7/2020 In Progress | PWC #1/2020 - All mitigation actions still in progress. Expected to complete by end of 2020. In progress | PWC#2 for PSP not done. Unable to get latest update. | PWC#2 for PSP not done. Unable to get latest update. | PSC 2/2020 16/10/2020 All 3 mitigations expected to complete by 2021 in progress
2 | Penang Smart Parking (PSP) | Technical Solution - Internal | Choosing compatible, robust, and minimal-maintenance for the Smart Parking Apps would ensure our reduced in manpower requirement in operating the TLK systems and to lower down our overall project costs. | High - Failure of device integration (sensor working together with the Apps) which result in lacking navigation features for Find-park, and Parking Enforcement, would decrease the effectiveness of operations for both MBPP and MBSP. | Mitigation : 1. To engage a more reliable Supplier of Sensor with complete solution eg. HW, Solution, Network coverage and Maintanence suppport. (Note: For Phase-2, HTP engaged IoTMalta sensor supplied by X-Peranti instead of SCC's sensor) | PM, AD, Prod & Solution Achitect | Before Start of Phase-2. (Jan2020) | Mitigation in Progress. 1. Transfering Knowledge and Documentation as well TOT from GBSB (En. Maliki) to our PSP Team. 2. Improvement of features based on enhanced UI and UX by internal HTP staff. (Target by 31/7/2020) | PSC 2/2020 - HeiTech is engaging X-PERANTI for Radar/ Magnetic parking sensors for Phase-2 of Deployment to improve sensor Sensitivity and Ease of Maintenance. Both Majlises are yet to decide on the appointed X-peranti sensors. MBSP also in midst to give approval for Surface and Flush Type sensors to be installed at roads under Pewartaan JKR. In Progress. | No PSC - MCO (18/3-14/4) - MBPP and MBSP are seeking the recommendation from MIROS and JKR prior to deployment and installations. | No PSC due to Extended MCO until 29/4/2020. HeiTech is engaging X-PERANTI for Radar/ Magnetic parking sensors for Phase-2 of Deployment to improve sensor Sensitivity and Ease of Maintenance. However, both Majlises are yet to decide on adapting the IoTMalta Surface mounted sensors. MBSP also in midst of evaluating whether Surface mounted is suitable for JKR Roads ( Warta JKR). (In Progress.) | PSC #3/2020 - The new type of Sensors are underway from Malta. Once installed new Phase-2 sensors should work well with PSP Apps. Fine-tune for Public Apps, Dashboard & ENF application shall be done from now until 31/7/2020. In Progress. | PSC #4/2020 - HTP obtained MBPP's decision on the selection of Surface-mount Sensor on 20/5/2020 (TSC). Once arrived from Malta, HTP target to start install the first batch of sensors beginning 8/7/2020. In Progress | PWC 1/2020- sensor installed on 8/7/2020. As of to date MBPP has installed 2,629 /7,500 unit (35%) while MBSP has installed 2,466/ 7,500 unit (35%). Expected to complete by 28/2/2021. In Progress | PWC#2 for PSP not done. Unable to get latest update. | PWC#2 for PSP not done. Unable to get latest update. | PSC#2/2020 16/10/2020 MBPP Batch !A 6,270/7,500 unit (83.6%) , Batch 1B 1,756/ 4,500 (39%). MBSP 3,330 unit. In progress
3 | Penang Smart Parking (PSP) | Technical Solution - External | Unreadiiness of third party system to be integrated (For example - 7-Elevan and Happy-mart) . | Third-party Integration Timeline potentially affected. | Mitigation : 1. Pilot with Happy Mart done on 17/3/2020. Deployment to rest of Happy Mart branches is target after MCO. (In progress) 2. Integration development with 7-Eleven still on-going. (In progress) | BD, AD, PMO | Before 30/06/2020 | Mitigation In progress. 3. Development of Huawei Apps Gallery still in progress (Completed - Rollout on 30/6/2020) | None | No PSC - MCO (18/3-14/4) - Pilot soft launch e-Coupon with Happy-Mart on 17/3/2020. - Target Pilot with 7-Elevan on End April 2020. | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items - Status Quo. | PSC #3/2020 - As reported Soft launch of e-Coupon Agent -Happy Mart completed on17/3/2020. Deployment to rest of Happy Mart outlets are in progress. | PSC #4/2020 - MBPP plans to call Main & Sub-Agents for a meeting session with Objective to get Demographic Data & whereabouts of Agents for the whole of Penang. In Progress. | PWC1/2020 - MBPP has identified 207 agents and 39 agents in MBSP. By August there will be 24 live branches in MBPP and 3 live branches in MBSP. In progress | PWC#2 for PSP not done. Unable to get latest update. | PWC#2 for PSP not done. Unable to get latest update. | PSC 2/2020 - 16/10/2020 Meeting on MBSP integration on 23 Sept 2020, decided the duration for integration development and payment for non PSP MBSP at Public Apps for 6 weeks target date for Live is 8 Nov 2020). This will be brought to JKT PSP Bil 7/2020 meeting for approval in progress
| Penang Smart Parking (PSP) | Project Management - External | Late decision from Majlis on type of sensor to be installed for both MBPP and MBSP. | Timeline breaches due to late decision coupled with Covid-19 pandemic. | Mitigation : 1. To get MIROS endorsement and recommendation on the proposed specifications of Surface-mounted sensors. (Done) 2. To get JKR's endorsement and approval for testing for Surface-Type sensors. (In progress) | BD, PD, PM, PMO | 2020-03-31 | Mitigation Completed. 1. With MIROS (Completed) 2. With JKR (Pending) | None | No PSC - MCO (18/3-14/4) - Still awaiting MBPP's decision on implementation of Surface mounted Sensors. | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items - Status Quo. | PSC #3/2020 - Based on Internal MBPP/ MBSP meeting held on 14/5/2020 to finalize the Sensor-type, HTP was informed that Majlis had concluded on selection of Surface-typr sensors. Flush-type was abandoned. CLOSED. | CLOSED
4 | Penang Smart Parking (PSP) | Project Management - External | Legal injunction or restrictions towards HeiTech will caused interruption of project operations. This situation will caused project delay and LAD/penalty can be imposed. | Affected reputation, profit margin and contract with Majlis | Mitigation Legal to execute settlement negotiation with SCC (for scope of work completed in Phase 1) Project team to execute project based on legal advise | PM, PD, BD, Legal | 2020-03-31 | Mitigation In progress |  |  |  | None | None | None | None | PSC 1/2020 High level legal to legal discussion is in progress in progress | PSC 2/2020 16/10/2020 High level legal to legal discussion is in progress in progress
5 | Penang Smart Parking (PSP) | Project Management - External | Sensor storage facility or warehouse is vulnerable to vandalism, thieve threat and fire. | Risk of theft, extra cost to project to re purchase, time taken for device to arrive | Mitigation in progress: The following action has been initiated: Installation of security alarm system Established proper procedure for accessing the warehouse Recruitment of Security Guard Installation of Fire Distinguisher Obtain proposal for insurance protection/coverage | PM, PMO | ASAP. | Mitigation In progress | [7 empty] | PSC 2/2020 16/10/2020 HTP is updating the insurance company with the required information before deciding on the right insurance company
6 | Penang Smart Parking (PSP) | Project Management - External | Contract commitment : e.g Year 1 minimum revenue for MBPP is RM3,515,400 and MPSP is RM3,698,100 . If collection is lesser than this committed amount, HTP to top-up the different. | Prolong additional cost if the collection does not meet the minimum commitment | Mitigation in progress: To ensure/monitor Councils commitment in ensuring and enforce full usage of PSP facilities. Effective promotional programme in efforts to promote positive awareness and usage of the Public Apps. | PM, PD |  | More active promotional activity conducted | None | None | None | None | None | None | None | The collection showed some increment especially after MCO lifted in Penang (in progress) | PSC2/2020 16/10/2020 The collection showed some increment especially after MCO lifted in Penang (in progress)
INTERNAL SECURITY - JIM
1 | JIM MyIMMs - Integration | MYEG – PLKS Renewal | No proper contract for service rendered to myEG. Delayed in Signing service contract. | HTP at risk if there is no contract. | Mitigation 'To initiate with legal on contract preparation with myEG to ensure company interest was safeguarded | Account Manager | By 31/1/2020 | Mitigation In Progress MyEG is reviewing the final Terms and Condition of Contract to be finalized. Legal HTP has vetted thru the Contract.(In progress) | (PSC 2/2020) Final scope of work has been confirmed by Project Team. AM has sent to myEG for review and yet to receive any response. An official email was sent and still waiting for their feedback. AM following up. In Progress. | No PSC - MCO (18/3-14/4) | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items - Status Quo. | PSC #3/ 2020 - Updates : Agreement with MyEG is in final stage to be signed. In progress. | PSC #4/2020 - Final draft copy already sent to MyEG for execution AM also email reminder to MyEG. In Progress. | PWC 1/2020 - MyEG has returned the draft to HTP. AM will arrange an appointment to meet HTP legal together with Integration Project manager (En Wan Suhaimi) In progress | PWC 2/2020 - Need to discuss with HTP Legal, AM and Integration Leader Wan Suhaimi. AM will arrange for the meeting. In progress | PWC 2/2020 - AM to arrange a meeting with HTP Legal to discuss matters raised by myEG. In progress | PWC 3/2020 2/11/2020 HTP return the document to myEG after some comments. In progress
2 | JIM Transformation | Financial - External | Potential LAD being imposed by JIM due to the delays in Transformation project. The earlier agreed project Timeline has surpassed. | Any LAD being imposed to HeiTech will give a bad reputation, thus reflect a bad track record. | Mitigation: 1. Second revision of Timeline indicated that the JIM Transformation project can be completed by July 2019. | PM, ADM (Transformation) | By end May 2019. | Mitigation Completed. JIM/BTMR accepted and approved the revised timeline (Second revision). HTP negotiated to pay a total of RM30,000 only for the LAD.(Capped) | (PSC 2/2020) - Until transformation is completely finish, PB(D) would not give the decision as yet on the appeal of LAD. In Progress. | No PSC - MCO (18/3-14/4) | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items - Status Quo. | PSC #3/2020 - Updates : Final LAD figure due to delayed Transformation completeness is still pending decision KDN. | PSC #4/2020 - KDN might not make any decision as yet on the LAD finalization until HTP complete the Transformation. Mitigation Completed. JIM/BTMR accepted and approved the revised timeline (Second revision). HTP negotiated to pay a total of RM30,000 only for the LAD. In Progress. | PSC 1/2020 - no update from KDN so far in progress | PWC 2/2020 - HTP has submitted a letter for reduce amount of penalty to be imposed. As of to date BTMR has not responded to the letter. In progress | PSC 2/2020 - KDN has not responded to HTP appeal letter. In progress | PSC 3/2020 - 2/11/2020 KDN has not responded to HTP appeal letter. HTP was awarded with a 6 months contract extension closed
| MyIMMs Maintanence | Financial - External | Related to undelivered training activities (overseas seminar/workshop), KDN did not approve the proposal submitted by BTMR and was declared by Pengarah Bahagian IT (PBD) in Mesyuarat Pemantauan on 17/02/2020. This matter to be closed. | Unable to submit claim for certain contractual scope eg. Training Overseas. | Mitigation 1: 1. BTMR To write with justification and propose to KDN. | PM, BTMR | By 31/1/2020 | Mitigation CLOSED : KDN rejected BTMR's proposal on Training Overseas. | CLOSED | CLOSED | CLOSED | CLOSED
FOMEMA -
All risk registered have closed
KKM - CLINICAL DOCUMENTATION
| CD - Clinical Documentation (HRPB) | Project mgmt - AD development | Tarikh FAT dijangka akan melangkaui tarikh tamat kontrak iaitu selepas 20 Mac 2020 | Potential LAD and increase of cost. | Mitigation 1: Application request for EOT must be applied about three (3) month prior to Contract expiry on 20/03/2020. | PM, ADM | 2020-03-20 | Mitigation completed: HTP requested EOT and approved by KKM during CD J/KPemandu @ 20/02/2020 mtg on contract extension (EOT) since contract is expiring on 20/03/2020. Tender Board approved the EOT for a duration of 18 months from 21/03/2020 to 20/09/2021 (with LAD). | NONE | No PSC due to MCO> Tender Board approved the EOT for a duration of 18 months from 21/03/2020 to 20/09/2021 (with LAD). | CLOSED | PSC #3/2020 - Updates : Tender Board approved the EOT for a duration of 18 months from 21/03/2020 to 20/09/2021 (with LAD). CLOSED. | CLOSED
1 | CD - Clinical Documentation (HRPB) | External factor - Force Majeure | Movement Control Order from the Govt of Malaysia with regards to the Covid-19 pandemic from 18/03/2020 to 14/04/2020. | Potential FAT Sign-off is further delayed ! | Mitigation 1: - Developers to continue to work from home to complete the remaining modules. Access now enable by Cloud facility. | PD, PM, ADM, all developers | 2020-05-01 | Mitigation in progress. 1. Mitigation action item in-progress. To speed up and Target for PAT sign-off on 2/7/2020. | NONE | No PSC - MCO (18/3-14/4) | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items - Status Quo. | PSC #3/2020 - tender board already approved of EOT until Sept 2021. (but, with LAD Calculation) | PSC #4/2020 - tender board already approved of EOT until Sept 2021. (but, with LAD Calculation) Target for PAT Signoff is on 2/7/2020. In Progress. | PWC 1/2020 - PAT signoff new target date is 14/8/2020 in progress |  | PSC #2/2020 15/10/2020 SJAM will sit with NMM to discuss on the right wording so that the status reflect the risk itself and not the mitigation action. The project has had the 71 days EOT in progress | PWC #3/2020 2/11/2020 This risk has become an issue. It will be closed and transferred to issue list closed
2 | CD - Clinical Documentation (HRPB) | Project mgmt - Timeline/ Scheduling | Short duration to complete the project, compared to the huge scope - development of CD, SPP-CD, Integration & API, revamp of other functions in SPP | Unable to complete the requirement within the timeline and budget. | Mitigation 1: To monitor closely the deliverables against timeline and if needed, to add resources in certain phase in the project. | PM, APM, ADM, PMO | 2020-05-01 | Mitigation in progress. 1. Mitigation action item in-progress. | NONE | No PSC due to MCO> 1. The timeline is monitored closely and being reported monthly either internally and externally in meetings and project reports. 2. HTP have requested and approved by KKM during CD J/KPemandu @ 12/11/2018 mtg on to extent the UAT & go-live timeline for additional 3 more months. 3. HTP have requested and approved by KKM during CD J/KPemandu @25/03/2019 mtg on to extent the UAT & go-live timeline for additional 3 more months (without LAD). 4. HTP requested and approved by KKM during CD J/KPemandu @ 20/02/2020 mtg on contract extension (EOT) since contract is expiring on 20/03/2020. Tender Board approved the EOT for a duration of 18 months from 21/03/2020 to 20/09/2021 (with LAD). . | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items - Status Quo. | PSC #3/2020 - UPDATES : - Work-in progress for next PAT for Module 4 to be on 13/6/2020. - HTP requested and approved by KKM during CD J/KPemandu @ 20/02/2020 mtg on contract extension (EOT) since contract is expiring on 20/03/2020. Tender Board approved EOT for additional 18 months until 20/9/2021. (But, with LAD Calculation) | PSC #4/2020 - UPDATES : Status is still as per last month. - Work-in progress for next PAT for Module 4 to be on 02/07/2020. - HTP requested and approved by KKM during CD J/KPemandu @ 20/02/2020 mtg on contract extension (EOT) since contract is expiring on 20/03/2020. Tender Board approved EOT for additional 18 months until 20/9/2021. (But, with LAD Calculation) In Progress | PSC #1/2020 - UPDATES : Status is still as per last month. - Work-in progress for next PAT is expected to be sign off on 14/8/2020. - HTP requested and approved by KKM during CD J/KPemandu @ 20/02/2020 mtg on contract extension (EOT) since contract is expiring on 20/03/2020. Tender Board approved EOT for additional 18 months until 20/9/2021. (But, with LAD Calculation) In Progress | PWC #2/2020- PAT go live HIS@KKM EMR Plus Group#5 (27/06/2020) pending e-SMRP go live Group#6 (11/07/2020) pending myHIX & API Online go live in progress | PSC #2/2020 15/10/2020 SJAM will sit with NMM to discuss on the right wording so that the status reflect the risk itself and not the mitigation action. The project has had the 71 days EOT in progress | PWC #3/2020 2/11/2020 This risk has become an issue. It will be closed and transferred to issue list closed
3 | CD - Clinical Documentation (HRPB) | Human resource - Internal | Change of project team members due to resignation, re-assignment or end of contract. | Interrupt the working process and affect may deliverables. | Mitigation 1: To ensure the continuity and smooth transition on tasks to the new team member and handing over of tasks and TOT is done efficiently. | HR, SDC, PD, PM | 2020-05-01 | Mitigation in Progress. 1. HTP to ensure the new project team member will have to undergo proper handover and will join 4 weeks prior to last day of resigned staff. | NONE | No PSC - MCO (18/3-14/4) Mitigated with HR and SDC to ensure timely replacemnent of resigned staff. | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items - Status Quo. | PSC #3/2020 - Updates: Reported that 9 pax -3rd party Contract staff expiry by 30/6/2020. HR Requires that identified renewals to be expedited. In Progress. | PSC #4/2020 - Project Team agreed to renew few staff due to EOT and revised schedule on Go Live / FAT. In Progress. | PSC 1/2020 - Reported that 9 pax -3rd party Contract staff expired by 30/6/2020. Project Team agreed to renew the contract due to EOT and revised schedule on Go Live / FAT. In Progress. | PWC 2/2020 - Status as per previous month. In Progress. | PSC 2/2020 15/10/2020- There will be a discussion on resource planning between COO, SJAM, NMM on the 71 days EOT. Status as per previous month. In Progress. | PWC #3/2020 2/11/2020 This risk has become an issue. It will be closed and transferred to issue list closed
KKM - RISPACS
| RISPACS | Project/ Contract Management | Potential delay in completing the project due to late getting 'signoff' for the SDD documentations. Hence, actual application development can only start after the SDD Acceptance. KKM refuse to allow any EOT as yet since it's still early in development stage. | Project team already behind schedule. There's a potential of penalties being imposed to the project team. | Mitigation : 1. To closely monitor the progress of Bugs fixing and comprehensive re-Testing of all modules. 2. ADL to ensure sufficient manpower & right skills among the SDs. | ADL, SDC, HR. | From 28/1/19 Till 25/9/2019 (FAT Date) | Mitigation CLOSED : 1) presented Justification for 'Additional Time' (Anjakan Masa) request at TSC and Pemandu level. (Done) 2) Internally HR & SDC to ensure timely appointment of additional SA & Developers for RISPACS AD - forensic and RFR. (Done) | CLOSED | CLOSED | CLOSED | CLOSED
1 | HRPZ II Maintenance Contract | Preventive Maintenance | Ageing hardware will increase the probability of damage to the component – PC, Laser Printers, Barcode Printers, UPS etc | Could lead to high cost of maintenance and potential reduced of revenue. | Mitigation •PM & Technical team to source out parts and repair services from multiple vendors for a reasonable price. ● CE need to regularly check and keep proper history of maintenance records to ensure timely replacement of parts. | PM, Infra Leader | On-going. | Mitigation in progress. 1. Keep good record of history maintenance repair for all hardware components. | NONE | No PSC - MCO (18/3-14/4) - Scheduled PPM on-going. | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items - Status Quo. | PSC #3/2020 - MItigation Action Items - Status Quo. In Progress. | PSC #3/2020 - UPDATES: Status is as per the last updated. All new purchases under the Variation Order (VO) valued at RM 499,000 are yet to be completed. Due to some critical items yet to order and ready for Forensic Go-Live, some loaners equip eg Scanners to be deployed. In Progress. | PWC #1/2020 - PM and technical team to source out parts and repair services from various vendors for a reasonable price. - IA to regularly check the condition of the hardware to anticipate the replacement parts. In Progress. | PWC #2/2020 - IA and technical team will try to look for local contractor who can do the hardwrae maintenance and support. - IA will keep regularly do the condition checking of the hardware to anticipate the replacement parts. In Progress. | PWC #2/2020 - IA and technical team will try to look for local contractor who can do the hardwrae maintenance and support. - IA will keep regularly do the condition checking of the hardware to anticipate the replacement parts. In Progress. | PWC #3/2020 30/10/2020 same as previous month. In Progress.
KKM - C.C.I.S
1 | CCIS | Project Management | Project will incur additional cost on integration for CCIS and Medical Equipment as there is no cost allocation for integration (Medical devices) work during tender submission. Project Team to further study the requirement and identify the cost | Some critical Integration points between PICIS product with Medical Equipments may not be possible if SOW on integration is NOT clear, and cost not allocated. | Mitigation Project Team to further study the requirement and identify the cost that may incurred | PM, AD, Principal | Target by 31/10/2019. | Mitigation in Progress. 1. Integrated Medical devices - list confirmed by KKM. Medical Equipments may fall under any of these categoty. Cat 1,2,3,4,5,6. 2. Non-integrated (Type 4 & 5) Medical devices - list also confirmed by KKM. Cost be borne by KKM. | PSC 2/2020 - Finalization of Medical devices under Cat. 1,2,3,6, already approved @ Mesy. Pasukan Projek on 30/1/2019. Revised List for Cat. 4 and 5 to be tabled at TSC tentative Mid-March 2020 for Approval because will be allocated under Government Budget. In progress. | No PSC - MCO (18/3-14/4) | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items - Status Quo. | PSC #3/2020 - Updates: In principal, for identified Medical devices (Type 1,2,3) that are interfacing PICIS, it was agreed contractually that the additional costs to enable the Integration shall be borne on shared basis between HTP and NETLEE on a 50% - 50% basis. This agreement on cost sharing is deemed elaborated in the supplementary contract between both. In progress | PSC # 4/2020 - Updates: Status is as per last updates. In principal, for identified Medical devices (Type 1,2,3) that are interfacing PICIS, it was agreed contractually that the additional costs to enable the Integration shall be borne on shared basis between HTP and NETLEE on a 50% - 50% basis. However, Netlee insisted that a capping value of RM250,000 is stated in the Contract. This agreement on cost sharing is deemed elaborated in the supplementary contract between both. In progress | PWC # 1/2020 - Updates: Both HTP and Net Lee has agreed on terms and conditions in the contract including integration cost capped at RM250K. Contract agreement to be signed soon Closed | closed | closed | closed
2 | CCIS | Contract management | Product Provider - NETLEE - Have limited resources - Incomplete and delays in project deliverable - delay in plan and strategy on BI and Med. Devices Integration | High impact due to late / delayed deliverables of critical components of AD - Incomplete deliverables that do not comply cotract compliance - Quality issues as deliverables did not go through proper review & QA processes | Mitigation : 1. 16/01/2020 - Discussed on project Delay 2. 14/02/2020 - Sent Complaint Letter to NETLEE 3. ADL Azzad to monitor and Identify -all related medical devices findings 4. Detail out trailing tasks to execute once after COVID19 | PM, ADM, PMO | May 2019 - may2020 | Mitigation in Progress - Action items 1 & 2 completed Action item 3 and 4 - still on-going. | None | No PSC - MCO (18/3-14/4) | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items - Status Quo. | PSC #3/2020 - Updates : - action items in itigating 1 & 2 completed. - Need to find suitable Solution Architect to take up as AD LEAD. - Netlee to expedite delivery readiness of critical documents such as SRS, SDD Tech documentations etc. In progress. | PSC #4 /2020 - Updates: - delay in plan and strategy on BI : - Azzad and Nooraizah will work on the BI design and development. - Med. Devices Integration : - Interim, Noraizam will supervise the following resources on Integration :- Lokman (from RIS) Mahadir and Yana (from CD ) Net Lee to expedite the delivery of SRS and SDD documents In Progress. | PWC1/2020- Update Catching up on the development work 8 July 2020 - visit HTJS to discuss on integration wit current SPP To propose deploy stand alone CCIS to all 3 integration sites for escalation strategy 27-28 July - SRS Integration Workshop for 3 integrated hospital Net Lee has yet to submit SRS /SDD documents. In Progress |  | PWC2/2020 24/8/2020 NetLee has hired people who will focus on the management while technical matters will be handled bo another team. HTP to monitor the performance of this new structure in progress | PWC3/2020 21/9/2020 NetLee has hired people who will focus on the management while technical matters will be handled bo another team. HTP to monitor the performance of this new structure in progress
3 | CCIS | Technical Development | Development for PICIS Integration Modules were brought forward to 2020 (delayed). Target - 2019 - Deliver HW and Infra + PICIS Configuration (All 11 hospitals) Target - 2020 - PICIS dev'pmt, deploy and Integration modules. (at least for all 8 non-SPP integrated hospitals) | Resources Not fully available & knowledgable for development works. | Mitigation : 1. Resource only available: a) SA on Oct 2019 and JAN2020 b) SW Dev on Dec 2019 (Junior), Feb2020 (Senior) 2) To deliver a Stand-Alone (PICIS) Solution | PM, ADM, PMO | By Oct2019 | Mitigation in Progress Action item # 1 & #2 are closed. | None | No PSC - MCO (18/3-14/4) | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items - Status Quo. | PSC #3/ 2020 - Updates : - All critical resources on development already - On-board. - Except a full-time in-project Solution Architect need to be hired. In progress. | PSC # 4/ 2020 - Updates : Status as per last updates. - All critical resources on development already - On-board. -Agreed in the meeting En Aizam will overlook the CCIS integration while En Azzad will be responsible for internal CCIS matters. In progress. | PSC # 1/ 2020 - Updates : Status as per last updates. - All critical resources are on board. -Agreed in the meeting En Aizam will overlook the CCIS integration while En Azzad will be responsible for internal CCIS matters. Mitigation action items 1 and 2 are closed closed. | Closed | Closed | Closed
4 | CCIS | Project management | Unable to complete infrastructure and HW/SW activity before end of September 2019 will affect project billing to government for this year | Serious impact to Cash Flow and Collection on Billings for Project since spending exceeded the collection for revenues targeted for this year 2019. | Mitigation Project team to look for other payment item with less risk and focus on hospitals with no changes on Bill of Material (BOM). PM to identify and monitor the risk | PM,AM,PMO | Target by 31/10/2019. | Mitigation in progress. 1. List of highly potential deliveries and collection without issues have been discussed with PMO KKM. PMO working hard to expedite the documentation/ acceptance/ billing processes. 2. Project Team to maximize billing before end FY2020. | PSC 2/2020 -(a) Billing for 1st Payment Approved By Pemandu 14/10/2019 - Invoice RM 2,567,775.00 Submitted to KKM on 15/01/2020. (Done) b) Billing for 2nd Payment amounting RM 5,493,761.11 to be tabled at TSC to be scheduled in March 2020. (Not Done due to MCO) In Progress. | No PSC - MCO (18/3-14/4) | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items - Status Quo. KKM in progress of payment to HTP. | PSC #3/2020 - Updates : 1st payment - RM 2.556 million received from KKM in April 2020. Project Team is targeting to initiate billing for 2nd Payment of about RM 5.5 Million by July/ August 2020. In Progress. | PSC #4/2020 - Updates : 2nd payment for 2020 - Project team is working hard to finalize the handing over of all documentations for Second Payment. Target date for documents submission is in July, while TSC meeting to endorse the deliverables and payment will be in August-2020 session In Progress | PWC1/2020 - KKM requested HTP to amend some of the documents. Thus billing for documentations planned in July will be most likely to be delayed to September 2020. In progress
KKM - EKL
1 | EKL | NONE | 1. Servers Hardware - Specific skills on server maintaining, managing, problem solving and repairing not available in the project team. Do not have a stock of spare parts if required | Risk for not able replace problematic hardware within SLA period. Fully dependent on the contractor | 1. To find reliable and capable contractor | PM, Tech | ASAP. | open | NONE | NONE | No PSC - Extended MCO (15/4 - 29/4/2020) to look for the right contractor open | PSC # 3/ 2020 to look for the right contractor open | PSC # 4/ 2020 to look for the right contractor open | PWC1/2020 to replace tape drive open | PWC2/2020 Engaged Green Apps Sdn Bhd as a maintenance and support contractor for EKL project (server) for a 1year agreement. In progress | PWC2/2020 Engaged Green Apps Sdn Bhd as a maintenance and support contractor for EKL project (server) for a 1year agreement. In progress | PWC 3/2020 27/10/2020 Monitoring the Green Apps Sdn Bhd performance in progress
2 | EKL | NONE | Preventive maintenance Hardware - server’s/network switches/workstations | The potential for frequent damage of hardware is very high. - Can lead to high maintenance costs and potential of revenue reduction | CE need to check and take action based on hardware history of maintenance/usage records to reduce the probability of damage | IA | NONE | closed | NONE | NONE | No PSC - Extended MCO (15/4 - 29/4/2020) deploy patches closed | PSC # 3+M38/ 2020 deploy patches closed | PSC # 4/ 2020 deploy patches closed | PWC1/2020 deploy patches closed | PWC2/2020 Engaged Green Apps Sdn Bhd as a maintenance and support contractor for EKL project. In progress | PWC2/2020 Engaged Green Apps Sdn Bhd as a maintenance and support contractor for EKL project. In progress | PWC 3/2020 27/10/2020 As of to date the risk is manageable and within control In progress
3 | EKL | Resource- internal | Onsite resource still using central CE until HR get the proper IA. | Staff could be more focussed and concentrate on their job functions. | 1. Liase with HR constantly to get IA (either from internal or from outside) | PM, HR | ASAP. | Open | None | None | No PSC - Extended MCO (15/4 - 29/4/2020) Still using central CE open | PSC # 3/ 2020 Still using central CE open | PSC # 4/ 2020 Still using central CE open | PWC1/2020 Still using central CE open | PWC2/2020 - Received 1 IA from myIMMs project and was posted at HKL. Will fulfill the requirement once CD is delivered. In progress | PWC2/2020 - Received 1 IA from myIMMs project and was posted at HKL. Will fulfill the requirement once CD is delivered. In progress | PWC 3/2020 27/10/2020 Health Sector team is planning to use pool IA for future project. closed
4 | EKL | contract management - external | Outsourcing server maintenance and support to Green Apps for 1 year. After 1 year HTP to decide to do the maintenance on its own or continue Green Apps contract. | Unable to meet the SLA and could be penalised. | 1. Outsource to Green Apps for server maintenance. This will be only 1 year. 2. After 1 year, HTP to decide to do the maintenance itself or continue Green Apps services. | PM | 2021-04-01 | Open | None | None | No PSC - Extended MCO (15/4 - 29/4/2020) Engaged Green Apps for a 1 year server maintenance and support open | PSC # 3/ 2020 Engaged Green Apps for a 1 year server maintenance and support open | PSC # 4/ 2020 Engaged Green Apps for a 1 year server maintenance and support open | PWC 1/2020 Engaged Green Apps for a 1 year server maintenance and support open | PWC 2/2020 As per previous month status. In progress | PWC 2/2020 As per previous month status. In progress | PWC 3/2020 27/10/2020 The contractor able to solve problem within SLA period closed
HRPZII MAINTENANCE
1 | HRPPZII MAINTENANCE | Project Management - Internal | Lifespan of hardware will increase the probability of damage to the component – PC, Laser Printers, Barcode Printers, UPS etc. | Higher cost to HTP | PM & Technical team to source out parts and repair services from multiple vendors for a reasonable price. IA need to regularly check the condition of the hardware to anticipate the replacement parts | pm, pmo, Site Leader | ASAP. | In Progress | None | None | None | None | None | None | None | None | PWC 3/2020 30/10/2020 Mitigation in progress
2 | HRPPZII MAINTENANCE | Project Management - External | Unplanned of annual leave (emergency leave) and medical leave of dedicated onsite support staff | HTP could be penalised for having less support personnel than agreed. Problem log cannot be solved on time | In critical event e.g.: Preventive Maintenance, CR deployment, engaged part time staff with daily wages. In normal situation e.g: staff absent, daily salary will be deducted from project costing. Deduction from salary is more cost saving compared to get replacement from HQ | PM,IA | ASAP. | In Progress | None | None | None | None | None | None | None | None | PWC 3/2020 30/10/2020 Mitigation in progress
HRPB MAINTENANCE
1 | HRPB MAINTENANCE | Project Management - External | Item not found during asset tagging activities | HTP could be penalised later | Follow up with IT HRPB | PM,PD | ASAP. | In Progress | None | None | None | None | None | None | None | None | PWC 4/2020 2/12/2020 Mitigation in progress
KKM - HIS@KKM EMR HOSPITAL CYBERJAYA
|  |  | No risk presented during PWC | No risk presented during PWC | No risk presented during PWC |  |  |  | None | None | None | None | None | None | None | None
KKM - HIS@KKM EMR BASICS HPD
1 | HIS@KKM EMR BASIC HPD | Project Management - Internal | There is a risk that required resources are tight up on different projects which could result in delay to execute activities | Unable to complete the development on time | Mitigation : 'Plan resources time in advance and get confirmation Explore alternative resources ie: other resource from other projects | PM, ADM, | ASAP. | Mitigation in progress. (1) team work on more than one project at one time . | No PSC - Extended MCO (15/4 - 29/4) - Updates : - Risk not occurred but potential to be a threat In Progress. | No PSC - Extended MCO (15/4 - 29/4) - Updates : - Risk not occurred but potential to be a threat In Progress. | No PSC - Extended MCO (15/4 - 29/4) - Updates : - Risk not occurred but potential to be a threat In Progress. | PSC #3/2020 - Updates : - Risk not occurred but potential to be a threat In Progress. | PSC # 4/2020 - Updates : - Risk not occurred but potential to be a threat In Progress. | PWC # 1/2020 - Updates : - Risk not occurred but potential to be a threat In Progress. | PWC 2/2020 - Risk occurred but manageable Team work on more than 1 project at 1 time In progress | PWC 2/2020 - Risk occurred but manageable Team work on more than 1 project at 1 time In progress | PWC 3/2020 27/10/2020- Project is delivered eventhough with resource sharing with other project. closed
2 | HIS@KKM EMR BASIC HPD | Project Development - Internal | There is a risk that existing bugs in EMR Basic (if any) will impact rollout at HPD which could result in unacceptable users experience | Need resource and time to do bugs fixing | Mitigation : '1 Functional test need to be thorough and point out any bugs early 2. Work with application team to solve any bugs | PM, ADM, | ASAP. | Mitigation in progress. (1) Continous testing . | No PSC - Extended MCO (15/4 - 29/4) - Updates : - Risk not occurred but potential to be a threat In Progress. | No PSC - Extended MCO (15/4 - 29/4) - Updates : - Risk not occurred but potential to be a threat In Progress. | No PSC - Extended MCO (15/4 - 29/4) - Updates : - Risk not occurred but potential to be a threat In Progress. | PSC #3/2020 - Updates : - Risk not occurred but potential to be a threat In Progress. | PSC # 4/2020 - Updates : - Risk not occurred but potential to be a threat In Progress. | PWC # 1/2020 - Updates : - Risk occurred . - minor bugs and manageable - continue testing . In Progress. |  |  | PWC # 2/2020 -27/10/2020 - The risk occurred and has been transferred to issue list. Closed.
3 | HIS@KKM EMR BASIC HPD | Project Management - Internal | There is a risk that AwanH security could be compromised and as a result HTP could be liable to the “Letter of assurance” that HTP submitted | Unable to complete the development on time | Mitigation : Make sure all resources AwanH and PSG project team need to signoff Evetting Administrator password need to be controlled | PM, ADM, | ASAP. | Mitigation in progress. (1) Risk not occurred but potential to be a threat . | No PSC - Extended MCO (15/4 - 29/4) - Updates : - Risk not occurred but potential to be a threat In Progress. | No PSC - Extended MCO (15/4 - 29/4) - Updates : - Risk not occurred but potential to be a threat In Progress. | No PSC - Extended MCO (15/4 - 29/4) - Updates : - Risk not occurred but potential to be a threat In Progress. | PSC #3/2020 - Updates : - Risk not occurred but potential to be a threat In Progress. | PSC # 4/2020 - Updates : - Risk not occurred but potential to be a threat In Progress. | PWC # 1/2020 - Updates : - Risk not occurred but potential to be a threat In Progress. | PWC 2/2020 - Risk not occurred but potential to be a threat In Progress. | PWC 2/2020 - Risk not occurred but potential to be a threat In Progress. | PWC 2/2020 - 27/10/2020 Risk not occurred but potential to be a threat In Progress.
OTHERs.
1 | All related projects | Contract management - Internal | Late Signing of Main Contract / Agreements with Clients. (eg CCIS and PSP Projects ). Agreement with Subcontractors not comprehensively written. To be reviewed by Legal Advisors. | Weak and not thoroughly written/reviewed Agreements will expose HeiTech to litigation as project progress and/or fail in future. | Mitigation : '1. Quick but comprehensive drafting of the contract document using the standard Service Agreements template available at Legal dept. 2. Any dispute raised by vendor/ service providers to be discussed & reviewed with Legal. | PM, AM, PMO. | ASAP. | Mitigation in progress. (1) S5 already signed the Contract on 30/8/2018. HeiTech still KIV on signing (2) CCIS project being reviewed too long by KKM. (3) PSP Concession Agreement between HTP, MBPP, MPSP yet to be finalised/signed. . | PSC #02/2020 S5 (Fomema) AGREEMENT - Reprinting & Re-signing of the Contract. (In progress) KSCB ( CD) AGREEMENT - Completed myEG (myIMMs) AGREEMENT - MyEG Revision and Signing (In Progress at MyEG) CCIS/ NETLEE - Target to complete by End-MARCH 2020. CCIS/ KCSB - Completed In progress. | No PSC - MCO (18/3-14/4) - S5 Agreement (for Fomema Project) - Not signed yet - MyEG Agreement For (myIMMs) - Not signed yet - CCIS/ NETLEE Agreement - Finalizing the contract, target by 6/3/2020 - Pending Netlee's feedback on HTP comments. - In Progress. | No PSC - Extended MCO (15/4 - 29/4) - S5 Agreement (for Fomema Project) - Not signed yet - MyEG Agreement For (myIMMs) - Not signed yet - CCIS/ NETLEE Agreement - Pending Netlee's feedback on HTP comments. - In Progress. | PSC #3/2020 - Updates : - S5 contract ready to be signed after Revised payment schedule finalised. - CCIS - contract with KKM already signed. Contract with Netllee to be signed before 30/6/2020. - Contract PSP with MBPP - ready to be signed. - Contract PSP with MBSP - still finalizing few clauses in contract. - Contract with MyEG - still pending. In Progress. | PSC # 4/2020 - Updates : - S5 contract ready to be signed after Revised payment schedule finalised. - CCIS - contract with KKM already signed. Contract with Netllee already passed the deadline of 30/6/2020. Yet to signed due to changed clauses. - Contract PSP with MBPP - ready to be signed. - Contract PSP with MBSP - still finalizing few clauses in contract. - Contract with MyEG - still pending. In Progress. | PSC # 4/2020 - Updates : - S5 contract ready to be signed after Revised payment schedule finalised. - CCIS - contract with KKM completed, signed, stamped and received on 6/3/2020. Contract with Netllee has been finalized. Awaiting for signatures from both parties. Already passed the deadline of 30/6/2020. - Contract PSP with MBPP - agreed on 3 July 2020. Contract given to MBPP Legal for signing. - Contract PSP with MBSP - MBSP raised some comments to HTP on 13 July 2020. HTP replied on 23 July 2020. Signing is expected in August 2020. - Contract with MyEG - AM to seek HTP legal advised on issues raised by MyEG together with Integration PM. In Progress. | PWC # 2/2020 - Updates : - S5 contract ready to be signed after Revised payment schedule is finalised. - CCIS - contract with KKM completed, signed, stamped and received on 6/3/2020. Contract with Netllee has been finalized. Awaiting for signatures from both parties. Already passed the deadline of 30/6/2020. - Contract PSP with MBPP - agreed on 3 July 2020. Contract given to MBPP Legal for signing. - Contract PSP with MBSP - MBSP raised some comments to HTP on 13 July 2020. HTP replied on 23 July 2020. Signing is expected in August 2020. - Contract with MyEG - AM tand Integration PM to seek HTP legal advised on issues raised by MyEG . In Progress. | PWC # 2/2020 - Updates : - S5 contract ready to be signed after Revised payment schedule is finalised. - CCIS - Contract with Netllee has been finalized. Awaiting for signatures from both parties. Already passed the deadline of 30/6/2020. - Contract PSP with MBPP - agreed on 3 July 2020. Contract given to MBPP Legal for signing. - Contract PSP with MBSP - MBSP raised some comments to HTP on 13 July 2020. HTP replied on 23 July 2020. Signing is expected in August 2020. - Contract with MyEG - AM tand Integration PM to seek HTP legal advised on issues raised by MyEG . In Progress. | PWC # 3/2020 - Updates : - Contract PSP with MBPP given to Legal for signing. - Contract with MyEG - HTP return the document to Myeg after putting some amendment. Awaiting feedback from myEG . In Progress.
| All related projects | Contract management - External | COVID-19 Pandemic has caused a 'Force Majeure' Condition for all projects. | Due to prolong restriction on 'Movement Control Order' (MCO) would resulted in the overall delay in implementing all related projects. | Mitigation - 1. Based on Corporate Comm directive, all project are to inform respective Clients of the Pandemic situation. A ' Customer Holding Statement' was issued to all Clients on 18/3/2020. - 2. Certain projects had issued a 'Force Majeure' letter to enforce the norice as per also elaborated in Contract document. | BD, AM, PD, PM | Within 18/3 - 14/4/2020 | Mitigation Completed. - Actions based on mitigation action plan fully executed. | None | No PSC - MCO (18/3-14/4) - MCO still on-going till April 2020. | No PSC - Extended MCO (15/4 - 29/4/2020) - Mitigation action items - Status Quo. | PSC #3/ 2020 - Updates : - All contract requirement to tackle unpreceedented event eg COVID-19 Force Majeure already handled accordingly. CLOSED. | Strategy – to deliver a Stand Alone CCIS solution as COE delay
NOTE :
|  | RISKS | New risks included are in blue texts.

## Closed Issues
CLOSED ISSUES
No. | Customer | Status | Project Name | Issue
1 | JPJ | Closed | JPJ MAINTENANCE: MAINTENANCE AND TECHNICAL SUPPORT SERVICES FOR COMPUTER (HARDWARE AND SOFTWARE) AND RELATED PERIPHERALS | 1. Pending payment to vendor. Finance to look into the matter (Closed)
2 | JPJ | Closed | PRISM PROJECT: TO SUPPLY, DELIVER, INSTALL, CONFIGURE, TEST, COMMISSION AND MAINTAIN THE MAINFRAME SYSTEM HARDWARE AND SOFTWARE | 1. DR Testing – limited component (hardware and software) covered under PRISM. RM3,988,424.00 potentially cannot be invoiced if DR Testing cannot be executed. However, the above to be billed based on IBM quotation. Supplementory contract, CR to be prepared accordingly.(Closed) 2. Payment issue on power cuttoff activity in Apr and May 2016 (out of scope). JPJ decided not to pay the RM70k and HTP Management has decided to absorb the cost. (Closed) 3. mySIKAP Loading at branches. Happen more often after code signing implementation. Issue due to branch network. (Closed) 4. SCAPM deployment, acquisition of services whether from IBM or other vendor, team to provide impact analysis accordingly. - IBM owned with no extra cost. Status: JPJ has decided to drop the product. (Closed) 5. PSC 10/2017 - 26/10/2018 JPJ wants compensation for SCAPM deployment failure. IBM to produce letter to state that no additional cost for SCAPM. Project Team to follow up with VIP Towers for the letter since IBM didn't agree with JPJ request. Project Team still has not received the letter from VIP Towers due to change in VIP Towers person in charge. The previous officer has resigned. Letter submitted to JPJ on 27/3/2018 (Closed) 6. Not able to invoice JPJ RM31M for 2018, 2019 License Renewal due to pending payment to IBM. JPJ agreed to proceed with payment with below condition that HTP will cleanup license list and produce LOU. Finally, invoce was endorsed by JPP Committee at BTM level. (Closed) 7. PSC 2/2018 - 21/2/2018: IBM announced that zOS 2.1 will be end of service (EOS). IBM claimed the support for ZOS 2.1 is void and HTP will require to take up Extended Support (chargeable) to get support. HTP has paid for 5 years services of the current version. HTP/VIP Towers need to review contract and have further discussion on the matter with IBM. PSC 3/2018 - Project Team has discussed with IBM and were given 2 options which involve cost and 1 option with no additional cost but with operational risk. Project Team has decided to maintain as is. (Closed) 8. PSC 6/2018 - IBM claimed that HW maintenance for certain machines is twice (2) times per year, against our commitment to JPJ which is four (4) times per year. Action: Project team to discuss with HMS Team (Wan Zailani & Hyree) to find the solution. PSC 7/2018 (25/7/2018): Discussion on 20/7/2018 - a) HMS Team to negotiate with IBM on the cost quoted by IBM for the “missing” PM by 3/8/2018. b )HMS to explore if HMS can provide the services for the “missing” PM by 3/8/2018. Must be resolved urgently since it impact Q2 billing amounting RM1,044,215. PSC 8/2018 (27/8/2018)- HMS appointed third party vendor INFOWARE SDN BHD to do the "missing" preventive maintenance. (Closed) 9. PSC 11/2018: High CPU utilization in six WAS production servers was observed beginning November 2017 to date. a) As per Dynatrace recommendation, upgrade/config the SSLUTIL b) Engage ISAT to perform deep dive analysis using AppMon based on 1 month data sampling captured between 1-31/10/2018 from all six WAS servers. PSC 12/2018: Project team has implemented SSL UTIL reconfiguration as per IBM's recommendation, on-going monitoring indicates that zVM CPU utilization has significantly dropped. Monitoring in progress. PSC 2/2019:JPJ agreed to apply the SSLUTIL to all WAS servers. Completed on 30-Jan-2019. (Closed) 10. (PSC 8/2019) Insufficient software licensed led to usage of unlicensed software by project team. Project Team need to identify the quantity of unlicensed software and take necessary action to avoid being penalised by software principal if software audit is performed. PM to discuss further with HMS Team. (PSC 10/2019) To make proper acquisition of software license for development team if new contract is awarded. (Closed)
3 | JPJ |  | JPJ REVAMP PROJECT: PROJEK PEMBANGUNAN SEMULA SISTEM PENGKOMPUTERAN JABATAN | 1. Outstanding payment to vendors. To follow up with Finance.(Closed)
4 | PUSPAKOM |  | PUSPAKOM: JPJ INTEGRATION | 1. Puspakom don't want to sign-off closure acceptance since there is a module (Vehicle Plan) which JPJ has not implemented. PM to prepare a LOU stating that Project Team will support the module when JPJ decides to implement the module. LOU was submitted to PUSPAKOM on 5/4/2018 (Closed)
5 | JPJ | Closed | SURUHANJAYA PENGANGKUTAN AWAN DARAT | NA
6 | JPJ | Closed | eAuto eSTM (CR 2) | NA
7 | JIM | Closed | MyIMMs Application Maintenance | 1. SQL DB Locking Issue:Upgrade SQL Version to MSSQL 2012 – implemented at Menara Ikhlas, Kelana Jaya and Kajang Deployment of 1Chip project using a ‘straight thru’ process approach currently in progress. After One month monitoring, Straight Thru process identified had almost eliminated SQL DB Locking problem. Project team currently focus on hang symptom due to other sources. 2. Inaccuracy statistical report in eReporting Module. Resolution by the team in progress. 3. Pending payment of RM1.5mil due to SLA issue. Potential penalty for SLA breached and amount will be deducted from the RM1.5mil. (Closed)
8 | JIM | Closed | MyIMMs Application Maintenance (2016-2017) | 1. Performance Issue: Taskforce lead by KDN has been created to resolve myIMMs performance issue at KLIA and KLIA2. Enhancement on Module of Kawalan has successfully deployed at both side. (Monitoring in progress). 2. CR on Rehiring Program issue. It has been decided that CR to be billed to KDN. BTMR urged to exclude 4 CR (RM133,475) which has been issued during last contract period ended 16/2/2016.(Closed) 3. Contract pending sign-off from JIM (Closed) 4. Delay in development activity under Transformation scope due to lack of resources. SDC and HR to assist on recruitment. (In Progress) 5. No. of SL records has identified not tally between local server and host. The downloading programs has enhanced to webservice methodology using IP instead of ordinary SNA. BTMR requires daily monitoring especially for main Entry Exit points KLIA, KLIA2, BSI, KSAB etc Webservice sometime found halted due to huge connection to local database. Rectification on UIDM program currently in progress.New proposal on mysql to be by solution team has been prepared.Implementation in progress under new contract. (closed) 6. Upload offline transaction records to host issue. Team to analyse and find solution to resolve. (In Progress) *Solution will be implemented in the new contract 7. Inaccuracy statistical report in eReporting Module. New timeline of 12 weeks action plan has submitted to JIM on 7 issues identified for major cause of inaccuracy reports. (Closed) 8. SOW for Perluasan dan Perpindahan has exceeded no. of location per year agreed in the contract. PBD request HTP to proceed with new branch installation activity as instructed by ministry. HTP to come out with a formal letter with the quotation to JIM. (Closed) 9. Potential penalty due to SLA breached. Total penalty as of end of contract period is RM442,893. PM to further negotiate for discount. Based on assessment, any further appeal will result in greater LAD. (Closed) 10. myIMM integration projects (PIB, eGate, ESD Portal and MBIKE) non-compliance issues: a) Tailoring checklist is not produced b) Project documentation is not present c) Contracts not available d) Risk list not updated Project team to close issue by mid October 2017. Project Team has provided the audit response to the issues raised (Closed) F11
|  |  | MyIMMs Application Maintenance (2017-2020) | 1. Conflict of priority between myIMMs Maintenance Team and Transformation Team. Team leaders not willing to let the team members to assist the other team due to tight schedule. Project Director is in planning of organising a teambuilding session. Team building done on 27-29/4/2018 (Closed). 2. (PSC 5/2018 - 23/5/2018) Revised timeline in delivering the Transformation project even after EOT to August 2018 has resulted in JIM imposing LAD to HTP with the amount of RM300K++. Project Team to identify factors that contribute to the delay and strategise for appeal for reduction of LAD. PM to properly monitor project activities to ensure new timeline is met. (PSC 6/2018 - 26/6/2018) Meeting to discuss the LAD has been made. Initial action agreed was to write to JIM and inform on correction calculation of LAD and negotiate for discount. (In progress) 3. (PSC 5/2018 - 23/5/2018) Revised timeline in delivering the Transformation project even after EOT to August 2018 has resulted in JIM imposing LAD to HTP with the amount of RM300K++. Project Team to identify factors that contribute to the delay and strategise for appeal for reduction of LAD. PM to properly monitor project activities to ensure new timeline is met. (PSC 6/2018 - 26/6/2018) Meeting to discuss the LAD has been made. Initial action agreed was to write to JIM and inform on correction calculation of LAD and negotiate for discount. (Refer to Risk Summary-this is registered as risk) (Closed) 4. (PSC 6/2018 - 26/6/2018) Slow in development and resolving technical issues due to: - Inadequate no of .Net expert in team – Too much reworks - Slow device integration development - Inadequate no of developer Project Team requires sufficient and skilled developers to ensure revised timeline can be met. (PSC 10/2018) SDC and HR are assisting in fulfilling the required resources. (Closed) 5. (PSC 9/2018 - 25/10/2018) Roll-out for myIMMS Transformation Phase 1 and 2 is delayed due to insufficient supply of SAGEM FP devices (MS300/M1300). There will be impact on cost and timeline since Project Team need to revisit the branches which PM activities were already done. PSC 10/2018 - 27/11/2018) Schedule rearranged to accomodate work for roll-out of Passport, Permit and PM activities. Roll-out target to complete in March 2018 (Closed) 6. (PSC 12/2018) - Slow progress development for phase 3 in Transformation is due to rework and bug fixing of production issues of Phase 1 & 2. Project Team is advised to convince BTMR to stop any new deployment of completed transaction and focus the team to complete all development. (Closed) (PSC 1/2019) - Project Team has implemented for Phase 3. (Closed) 7. (PSC 12/2018) - Device integration with NERS, Project Team is facing difficulty in resolving issues with S5 since the technical person was not around to resolve issues. Project Team to request from BTMR for S5 technical team to be with the team until problem is resolved. (PSC 4/2019) UAT done. (Closed) 8. (PSC 1/2019) - Project Team is not allowed to access production which slow down problem resolution process and impact SLA. Project Team to work with BTMR on testing at production as part of TOT process. Project Team to get agreement from BTMR for SLA to start/& stop at certain point to avoid being penalised for delay on BTMR part. Once HTP team provides Script/coding for BTMR to execute. SLA clock HTP will stop. (Closed) (PSC 2/2019) - BTMR will take up the task involving testing in production. (Closed) 9. (PSC 5/2019) - Users still using old transaction after implementation of new transactions especially for Sistem Passport and Permit. Project Team to plan for closing of old trasactions after system stabilisation target to be by 30/6/2019. (PSC 6/2019) Closing for Sistem Passport and Permit are still in progress. (PSC 7/2019) Rollout for Passport, Permit and Hasil are completed.(Closed) 10. (PSC 7/2018- 25/7/2018) System slow response which may be due to high bandwidth utilisation. Project team need to measure myIMMs bandwidth requirement and submit to JIM BTMR. (PSC10/2018) BTMR has still not given the required bandwidth to be tested. (PSC 12/2018) Project team has installed a few tools to collect the information that might caused the slow response and come out with the following : - bandwidth optimum size required by myIMMs web - Any process/ SQL that can be enhanced /optimized (PSC 1/2019 ) - Project team need a license monitoring tool to investigate application slow response/ hang issues. SDC proposed to use the trial version temporarily.F13 (Update 31/12/2019) - Bandwidth has been shared with JIM and most main JIM branches have been upgraded except for small branches. Upgrading of bandwidth is under JIM action. (Closed) 11. (PSC 12/2019) - XML Injection must be completed by 30/3/2020 but the project team is facing technical errors during internal testing and need help from HTP technical experts. (In progress) (PSC 1/2020) - SDC technical team managed to identify and resolved the problem.(closed) 12. ( PSC2/2020)- Related to myEG pending contract, final scope of work has been confirmed by Project Team. AM has passed to myEG for review and yet to receive any response (open) (PSC 4/2020) - myEG contract completed (closed) 13. ( PSC2/2020)- Related to MBIKE pending service agreement, final scope of work has been confirmed by Project Team. AM has passed to VKSB-MBIKE for review and yet to receive any response (open) (PSC 4/2020) - MBIKE service agreement scope of work has beeen agreed by both parties (closed)
9 | JIM |  | S5 System Sdn Bhd: Projek Integrasi Biometrik (PIB) | 1. Audit non-compliance issues: a) Tailoring checklist is not produced b) Project documentation is not present c) Contracts not available d) Risk list not updated Project team to close issue and responded to auditor by end of August 2017. (In Progress)
10 | JIM |  | (PERLUASAN) Migrasi Data PATI Depoh For MKN | NA
11 | JIM | Closed | S5 System Sdn Bhd: eGate Integration (JIM) | 1. S5 insist HTP to resolve the integration issue before project closure can be done. Closure notification has been sent to S5. (Closed) 2. Audit non-compliance issues: a) Tailoring checklist is not produced b) Project documentation is not present c) Contracts not available d) Risk list not updated Project team to close issue by mid October 2017. (closed)
12 | JIM | Closed | Education Malaysia Global Services (EMGS) Integration Service between STAR-EMGS and myIMMs System | 1. Difficulties in getting JIAS support as it is previously supported by HeB. Immediate support will take some time as client required immediate resolution. (Closed. SDC take over)
13 | JIM | Closed | MyIMMs Integration with Facial LIVE Capture | NA
14 | BESTINET | Closed | BESTINET: Integration Service Between Foreign Worker Centralized Mgmt System (FWCMS) and myIMMs System | Require dedicated resource to support the project. (Closed. Team to utilize existing myIMM staff for support)
15 | JIM | Closed | NZ Gemilang Sdn Bhd: Integration Service Between PDRM's Central Intelligence Unit (CIU) - PDRM and myIMMs System | NA
16 | JIM | Closed | ESD Talent Corp Malaysia: Integration Services Between Talent Corp's ESD Portal and myIMMs System | 1. Pending development for integration enhancement due to JIM approval. Team has communicated & email to TC regarding conditional closure and suggest enhancement during maintenance. (Closed) 2. Audit non-compliance issues: a) Tailoring checklist is not produced b) Project documentation is not present c) Contracts not available d) Risk list not updated Project team to close issue by mid October 2017. (Closed - Project Team has provided the audit response to the issues raised)
17 | JIM | Closed | Innovezion Tech Sdn Bhd: Development services for Regula Integration and deployment services for selected sites | NA
18 | myEG | Closed | my EG Sevices Bhd: Working Permit Renewal of Foreign Workers | 1. PSC 4/2020) –Claim for myEG for Dec 2019 RM108,788 is yet to be paid (closed)
19 | JIM | Closed | Vista Kencana: MBIKE Enhancement | 1. Audit non-compliance issues: a) Tailoring checklist is not produced b) Project documentation is not present c) Contracts not available d) Risk list not updated Project team to close issue by mid October 2017. (Closed - Project Team has provided the audit response to the issues raised)
20 | JIM | Closed | MARDI | 1. Potential loss of RM50K due to MARDI unreadiness to complete the project. Account Manager will provide official letter to MARDI on the matter. Potential to terminate project as customer unwilling to proceed with payment. (Closed)
21 | JPN | Closed | JPN Maintenance | 1. Pending payment to vendors and partners. Affected vendors refused to do Preventive Maintenance work because of payment issue.(Closed) 2. Insufficient resources. KIV until contract renewed. (Closed) 3. Collectors terminal (7 units) for e-debit and MEPS, still awaiting new vendor to perform preventive maintenance(Closed) 4. Unstable eJPN. JPN feel annoyed with our solution. Been piloted since 12 August 2015. eJPN team request SDC to help in providing solution and troubleshoot current problem/slow response issue. (Closed) 5. Network Upgrade Contract & Green Data Center awarded to other companies. Need to support these vendors or JPN will ask for credit note on cost savings. HMS is working on SOW to support this activity (Closed) 6. TDA demands for either Bank Guarantee or Coporate Guarantee. Customer concern on the delivery end date.Team to issue letter of appeal to TDA for exception. (Closed) 7. Archive Database: Number of records not tally between PDB and ADB potentially due to storage or problem on synchronization. Team will further discuss and investigate .(Closed) 8. Increase in GSCB Storage: Proposal submitted to BTM for the extra 4TB permanent storage for 5 year plan of growing databases. BTM agreed on 2TB for short term planning and suggest to take off ADB or SDB and use ODM at DRC as a backup storage. Team need further discussion. Additional 2 TB storage required licence for migrate to DRC (Closed) 9. Problem Photo in DB2: 2 Suggestion: 1)Check compress process in MyKad 2)Change photo column size in DB2 – HeiTech need to submit requirement study to BTM. On photo and thumbprint not found in DB2 issue, team need to verify with MyKad transaction. Photo size for branches decrease from 300x400 to 150x200. ESDC to amend the program for 3175 resolution compression. (Closed) 10. Data Centre Expansion under TDA. Issue on financial as vendor required payment before delivery. Delay in payment may affect factory test activities. Issue has been resolved by HMS. (Closed) 11. CR budget of RM3.5mil is still untouch and will affect overall project revenue. Team to relook on other possibility to utilize this budget. (Closed) 12. Technical/field support competency issue. IA need to undergo training to enhance skill and knowledge. PM will provide training requirement and tentative date to Mokhtar for further action. (Closed) 13. Insufficient advance for IA. Management approved lesser than the amount applied. IA unable to provide corrective support services when required due to insufficient fund. (Closed) 14. PO issuance to Optima still pending for approval. Optima has completed CR work and payment need to be made to the vendor. Team to obtain approval of PO from EVP immediately.(Closed) 15. Project non-compliance issue. Team to close all gaps by mid October 2017.(Closed) 16. JPN claimed source code handed over by HTP upon contract end is not latest version. PM to do the handover again with proper documentation. (Closed - second has been done )
22 | JPN | Closed | PERKHIDMATAN PENYELENGGARAAN SISTEM BOOMGATE MYKAD & BOOMGATE RFID JPN | NA
23 | MOH | Closed | SPP V2.6 MAINTENANCE (Hospital Tuanku Ja'afar Seremban (HTJ) & Hospital Port Dickson) | NA
24 | MOH | Closed | SPP V2.6 MAINTENANCE-eKL (Hospital Kuala Lumpur (HKL), Hospital Kajang (HKJG), Hospital Tengku Ampuan Rahimah (HTAR)) | 1. Life span of hardware already > than 6 years. PSC #9 reported SLA for hardware have achieved 100% (Sept-2018).Continuous monitoring. Project has already ended. Should be next tender project risk. (Closed) 2. Knowledge and skills of support team on SPP have been improved. Internal training and coaching conducted. Project has already ended. (Closed)
25 | MOH | Closed | SPP V3 Rollout Project - Hospital Bentong Pahang | NA
26 | MOH | Closed | SPP V3 Rollout Project - Hospital Tuanku Jaafar Seremban | NA
27 | MOH | Closed | SPP V3 Rollout Project - Hospital Raja Perempuan Zainab II, Kota Bharu | NA
28 | MOH | Closed | SPP V3.1 Rollout Project - Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu (Extension of Time (EOT)) | 1. “Power trip” at New Building ( ACC Building ). TNB has conducted assessment activities on 8 Apr 2016 due to unstable incoming power to Hospital Power source. On monitoring period until 31st May 2016 - closed 2. System Performance issue, conduct onsite monitoring by technical team from 13th March 2016 to 16th March 2016 with fine tuning on SQL Query, Bugs fixing, Domain synchronization and Pillot JVM domain setting. Create new domain D29 for O&G clinic on 13052016. On monitoring period until 26th May 2016-Closed
29 | MOH | Closed | SPP V3 CR Med. Record - HRPZ | NA
30 | MOH | Closed | SPP PERLUASAN HARDWARE DELIVERY FOR HBEN, HRPZ AND HTJS | NA
31 | MOH | Closed | SPP V2.6 Implementation Project - Hospital Taiping Perak (HTPG) | NA
32 | MOH | Closed | Data Center (DC) Queen Elizabeth Hospital Kota Kinabalu (HQE) | NA
33 | MOH | Closed | DC Hospital Sultanah Nora Ismail (HSNI), Batu Pahat | 1. KCSB temporary suspended works related to the system supports. (Closed)
34 | MOH | Closed | DC Hospital Tengku Ampuan Rahimah Klang (HTAR) | 1. Delayed in first partial payment amounted RM745,270.99. As at 10/05/2016, HTP has submitted a letter to HTAR with a copy to JKNS as reminder letter for full payment. Due to this issue/matter, project team are having hard time to ensure scheduled Preventive Maintenance activities by the vendors for the Precision Air Conditioning System and for the Uninterruptible Power Supply System. (Closed) 20/06/2016 – Unit Pembangunan JKNS (Pn Siti Hajar) has been informed by KKM, they still have not yet get any further solid information regarding the payment. JKNS will send another reminder letter KKM regarding this issue. (Closed)
35 | MOH | Closed | SPP-PHIS Integration Project | NA
36 | MOH | Closed | SPP Maintenance - Hospital Bentong | 1. Hospital Bentong will impose penalty due to failure of providing loaner unit for Barcode Printer. Issue may affect payment schedule. Team had discussed with Pengarah on 22/6/2017. Pending decision from KKM. (Closed) 2. PSC 4/2018 24/4/2018 - License renewal for Firewall will be an issue since the current model used is EOL and therefore no support from principal. Project team to get official confirmation from principal. Project Team need to decide whether to maintain current model and hence no support from pricipal or change to new model. Project Team need to also discuss and get approval from customer. PSC 6/2018 26/6/2018 - No impact to customer since hardware and software come in a package, no separate license. (Closed)
37 | MOH | Closed | Project Upgrade Server for HRPB | NA
38 | DEFENSE | Closed | Enhanced Training Aid System (ETAS) | NA
39 | DEFENSE | Closed | IGLA Weapon System | 1. SST was rejected due to Forex – Team to advise Mindef to establish direct negotiation pricing base on current Forex. (Closed)
40 | DEFENSE | Closed | Arthur Radar Weapon Locating System (WLS) | 1. Vendor (EMSB) refuse to start work due to pending payment. Finance to look into the matter and resolve accordingly. (Closed) 2. Late issuance of LO amounting RM800K due to outstanding payment to vendor. Finance to resolve issue immediately. (Closed) 3. PSC 3/2018 (30/3/2018) - 30 % Value of spares to be paid in advance to Vendor. Late payment will affect delivery of spares. PO has not been issued as to-date. WBS not available in ESS. Project team and Finance are working on resolving issues. Payment made to vendor on 27/4/2018) (Closed)
41 | DEFENSE | Closed | Action Speed Tactical Trainer (ASTT) | 1.Contract pending sign-off from customer side. Contract signoff completed. (Closed) 2.Table Top system update. Required at least 1x programmer to help current system developer. (Closed) 3.Support staff required for PM (July 2016)-(Closed) 4.Work pending due to limitation of LO ( only 3 LO in a year). Project have balance of 2 LOs . Based on new instruction from DSA, work can only be executed once receive LO. Therefore to minimize in using LO, work/job need to be compile before LO can be released, result in pending of work execution. LO no longer limited to 3 LO per year once the contract submited in mac 2017 (Closed) 5. Yearly maintenance suspended – Instruction from Chief Navy to all unit in TLDM except for boat maintenance. Pustakmar will write a letter to DSA, request to proceed with maintenance.Yearly Preventive Maintenance was done on May 2017. (Closed) 6. PSC 3/2018 (30/3/2018)- Cannot claim full contract value. Project is based on LO but project team has no Account Manager to manage the account. Project Manager will manage the situation accordingly (Closed) 7. PSC 6/2018 - Defense A/c Director queried on the support committment by TFSD unit for ASTT project. TFS replied that currently 9 SE's are supporting on-need basis. However, no personnel charges directly to DEF account. Will be discussed at MCM level. PSC 7/2018 - TFSC will assign dedicated SE and charge the services to Defence accordingly. (Closed)
42 | DEFENSE | Closed | JHEV-Projek Penyelenggaraan Aplikasi (Sistem Pengurusan Pencen), Perisian & Perkakasan. | 1. VIBES system developers have resigned. Junior developer does not have system knowledge to support JHEV. PM requested Norainon to be onsite for 2 days supporting account closing activity (VO basis).(Closed) 2. Support staff need to have knowledge in .C#.Net programming , DBA and network in order to support VIBES system. (Closed) 3.Issue on access level via remote access. Require assistance from Hamadi to resolve it. (Closed).
43 | MOH | Closed | SPP V2.6 MAINTENANCE-eKL (Hospital Kuala Lumpur (HKL), Hospital Kajang (HKJG), Hospital Tengku Ampuan Rahimah (HTAR)) | 1. Insufficient cooling system in server room. Hot temperature may damage the quipment/server. (Closed) 2. Delay in payment by Hospitals to HTP. Currently close monitoring among AM, PM, FIN and e-Perolehan Reps from KKM to resolve LO, eP, Invoice or Credit Note mattters. Payment received. (Closed)
44 | MOH | Ongoing | Clinical Documentation | 1. High expenditure on hotel charges for training/workshop session will increase the chances for project cost overrun. Team to source out other alternative venue with lower cost.(Closed - Project Team conduct training/workschop at lower cost venue or at user site) 2. Source code version issue (based on which SPP HRPZ or Ipoh). Team to further evaluate on which version to be used as baseline (Closed) 3. API Integration readiness with 3rd party system may affect overall scope and timeline. Team to further evaluate before deciding to drop or replacing any scope.(Closed - drop TC and proceed with STB, myTB integration) 4. SDD CR2016 delay submission will cause delay in HIS@KKM design and development activities. Due to the delay, project will require additional 2 months for workshop and SDD SPP Enrichment preparation. (Closed) 5. IVV implementation issue, user raised concern on our capabilities and IVV was not properly done resulting in delay in SDD review target. PM to further monitor IVV team involvement in SDD preparation to avoid any lack of understanding issue on SDD content. (Closed) 6. (PSC 3/2018) Expected date to get budget approval for DB installation must be obtained latest by June 2018 so that acquisition process can proceed by Sept/Oct 2018, failing which will affect project implementation timeline. Project Team to closely monitor the date and follow-up with KKM. (closed) 7. PSC 6/2018 - CD requires Performance tools with capability of testing up to 5,000 concurrent users at five seconds response time. Under action by Testing Center. Project Team will use JMeter (PSC 11/2018) Project Team is performing the testing at DRC .(Closed) 8. (PSC 3/2018) Expected date to get budget approval for DB installation must be obtained latest by June 2018 so that acquisition process can proceed by Sept/Oct 2018, failing which will affect project implementation timeline. Project Team to closely monitor the date and follow-up with KKM. New revised SST was obtained from KKM on 10/10/2018. (Closed) 9. (PSC 10/2018) - Printers with wrong techical specification were delivered to customer and was only realised a month after delivery and therefore could not be changed by vendors. Impact is on Y2018 billing, there will be lesser amount i.e. RM521,339. However, Project Team manage to negotiate with KKM for separate billing on the printers and hence do not affect the billing for other deliverables although it is part of the package. Project management to revise SOP on product purchased, Validate, Verification, and Acceptance in order to avoid wrong product specifications being delivered to Client, hence increase the cost of the project. (PSC 12/2018) - Project Team to buy required spare part of printer in Singapore, do POC and if compatible will purchase for other printers. (PSC 1/2019) - Project Team has successfully upgraded the printer memory from 128MB to 256MB using formatter board HP LaserJet M402DN extended version (HPLJ M402DNe). Project Team in process of acquiring 337 unit formatter. Acquisition of Batch 1 with total of 100 unit target to deliver in Feb 2019. Warranty will be covered by HTP for 3 years. Project Team to ensure the proper process of obtaining approval and procurement is in order. (PSC 2/2019) KKM has agreed with the upgrade of formatter board. Vendor require 70% up front payment to proceed. Finance is in progress of processing payment to the vendor. Target delivery and complete Installation in May-2019 (Slide update on 31/5/2019) All formatter board have been installed and delivered to HRPB for system Go-Live target on 16/6/2019. (Closed) 10. (PSC 5/2020) - 1. (PSC 2/2019) Project Team requires second revised timeline since UAT 2 could not start as planned. Issue has been discussed with Pasukan Kerja KKM and agreed to revise with staggard implementation according to discipline. With revised timeline, FAT will be on 25/10/2019 and warranty support duration will be lesser i.e. 218 days. Project Team to ensure chronology and justification on the cause of delay are properly documented. if project timeline remain until 25/10/2020 does not change i.e. 218 days. (Slide update on 31/5/2019) Go-Live date is rescheduled to be on 16/6/2019 and 17/6/2019 for Lite version. (Slide update on 11/6/2019) Go-Live for Lite version was done as scheduled, however has been reverted to SPP due to system problem. New date to Go-Live is not determined yet by KKM. Project Team in process of rectifying issues. (PSC 5/2019) Go-Live for EMR Basic is rescheduled to be on 24/8/2019 and 12/10/2019, 23/11/2019,07/12/2019 and 26/12/2019 for EMR Plus. (PSC 7/2019) PAT Go-Live at HRPB was rescheduled to 05/10/2019. Entry criteria for PAT Go-Live set on 21/9/2019 was not fulfilled during Mesyuarat Penentuan PAT CD on 20/9/2019. PAT Go-Live HIS@KKM EMR Basic done on 23/11/2019. HIS@KKM EMR Plus will be implemented in stages from 1/2/2020 until 29/3/2020. (PSC 3/2020)- - Revised date of PAT Go-Live to 24/8/2019. - PAT Go-Live on 24/8/2019 cannot proceed because of failure to achieve entry criteria for PAT Go-Live. - HTP proposed revised date of 21/09/2019, but rejected by KKM due to entry criteria not yet fulfilled. A new revised date is still in discussion by HTP (in progress). -. EOT has been approved by KKM Tender Board on 02/03/2020. Approved EOT is from 21/03/2020 to 20/09/2021.(closed)
45 | DEFENSE | Closed | Asean Customs Transit System (ACTS) | 1. Helpdesk implementation-may be using CCC due to IP issue on current product, should be decided before pilot. - Team to use CCC services. (Closed) 2. Issue on staff advance and claim related process affect staff moral. Advance or next expenditure required, advise PM to to provide supporting documents such as ATB, Invoices or billing milestone.(Closed)
46 | MOH | Closed | SPP V3.1 Rollout Project - Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu | 1. Issue related to unavailability of onsite staff, HRPZ had decided to deduct RM14K (based on the staff timesheet)from the amount billed. Team had further negotiate with KKM on the amount and awaiting KKM decision on the matter. Penalty was reduced to RM7,488 (Closed) 2. Unplanned leave taken by IA causing HRPZ II complaint on less than sufficient head count on-site. PSC # 9 - head count for IA's on-site HRPZ II already fulfilled as per contract. (Closed)
47 | MOH | Closed | HKL-Bekalan Perkhidmatan Penggantian Server | NA
48 | LPPKN | Ongoing | Sistem Reproductive Health Information System (RHIS) Membekal, Menghantar, Mengkaji, Merekabentuk, Membangun, Menginstalasi, Menguji, Mentauliah Dan Menyelenggara Bagi Naik Taraf Sistem Reproductive Health Information System (RHIS) di LPPKN | 1. (PSC 6/2018 - 26/6/2018) Delay in purchasing 4 units LAB Analyzer already resolved. However, need Dongle (Moxa) in order to work. But, not in original costs. To propose to LPPKN (PSC 7/2018 - 25/7/2018) Project Team has presented to LPPKN result of feasibility study with additional cost on 30/7/2018. (Closed)
49 | MOH | Closed | SPP Application Maintenance-Hospital Taiping, Perak | NA
50 | JPJ | Closed | mySIKAP Maintenance (Software License Renewal 2015) | NA
51 | JPJ |  | mySIKAP Maintenance (Software License Renewal-Jan-Oct 2016) | NA
52 | JPJ | Closed | mySIKAP Maintenance | 1. Insufficient resources. Ongoing discussion/follow-up with SDC & HR (Closed) 2. No laptops/desktop for the IA and some developers. Laptop requirement has been circulated to Finance. (Closed) 3. Outstanding Payment to Vendors. Finance to look into the matters.PM to provide list (Closed - payment made to vendors) 4. TSM for Icewarp was not included in total pricing. HMS has consolidated all the TSM license and has included TSM license for Icewarp.(Closed). 5. Unable to invoice On Request Services monthly due to clause in contract. AM will revised payment schedule accordingly. (Closed) 6. Insufficient advance for IA. Management approved lesser than the amount applied. IA unable to provide corrective support services when required due to insufficient fund. (Closed) 7. Contract pending sign-off, affecting project billing. Sign-off target to be done by early September 2017.(Closed) 8.IA is working in Firewall Project at the same time need to execute Corrective and Preventive activities for mySIKAP. This will affect SLA and invoicing. PM will sit down with affected parties to resolve issue. (Closed) 9. IA is working in Firewall Project at the same time need to execute Corrective and Preventive activities for mySIKAP. This will affect SLA and invoicing. PM will sit down with affected parties to resolve issue. (Closed) 10. JPJ decided not to pay VEP CR from application CR budget - instead asking TCSEN to pay. No official communication has been established, team to follow up with JPJ immediately. JPJ decided in CCB Meeting dated 3/11/2017 for HTP to bill TCSen. Project Team is in process of communicating with TCSen. (PSC 3/2018) Project Team is advised to invoice JPJ since CR is raised by JPJ. (PSC 4/2018) JPJ has agreed the CR to be under maintenance scope. Project Team will get endorsement in April JTP meeting in order to get the sign-off and payment. (PSC 5/2018) There is still disagreement in JPJ to pay for the CR. MOM with MOT stated that CR should be paid by TCSEN. Acct Manager to send official email to MOT. (PSC 7/2018) Project Team to bring the matter in JPP Meeting and send official letter to JPJ by 10/8/2018. (PSC 8/2018) - Project Team has highlighted the matter in the JPP meeting. (PSC 10/2018) - JPJ confirmed that CR is separate from project scope of work and TCSEN agreed to pay for the CR. (Closed) 11. JPJ has instructed to reduce number of project team members at current project office in JPJIT Block B. Project Team to find new office for remaining project members; to install additional power point and pull cable from outside room to get additional power capacity. Project Team is in process of preparing proposal for management approval to rent venue outside JPJIT since JPJ wants to charge rental. (PSC 3/2018) To reconsider if there is contract extension. (PSC 4/2018)Will proceed with plan for renting out of JPJ if awarded with JPJ Maintenance contract. (Closed) 1. (PSC 2/2018) For a CR that SPANCO pay directly to HeiTech, JPJ decided in CCB dated 23-1-18 that JPJ will pick up the cost and HTP need to return the payment made by SPANCO since there is no legal act that allow this transaction. Project Team will only reimburse the payment when JPJ has sent official notification and pay to HTP. (PSC 3/2018) JPP Meeting decision to proceed with payment for April and hold reimbursement to Spanco until further instruction from JPJ. (PSC 8/2018) JPJ has paid CR for SPANCO to HTP. HTP to reimburse payment received earlier from SPANCO. (PSC 1/2019) HTP has reimbursed the payment to SPANCO on 28/12/2019. (Closed)
53 | FOMEMA | Ongoing | FOMEMA MYIMM Biometric Integration | 1. Fomema failed to have a session with Dato Sri KPI to address concerns from Pengarah Pekerja Asing and Pengarah BTMR related to new biometric policy at Fomema panel clinics. FOMEMA to write formally to Dato Sri KPI. (Closed) 2. Fomema vendor insist to develop all functions related to biometric even though the contract awarded to HTP. The matter was personally highlighted to the top management of Fomema where the vendor was instructed to work with HTP for biometric development. (Closed) 3. Arguments on biometric interface between S5 and Beans. Solution for the interface has agreed in project meeting chaired by Fomema on 24/2/2017. The solution will affect deliverable of SDK by S5 (Closed) 4. Vendor competency issue. PM to look into overall schedule impact as the vendor is claimed to be incompetent. Schedule has been revised and monitoring in progress.Contract preparation also in progress. PM to follow-up with Legal on contract requirment. (Closed) 5. FOMEMA failed to provide the actual number of panel clinics as well as its address for the purpose of deployment. As of 25/8/2017 FOMEMA agreed to deploy to 4050 panel clinics. (Closed) 6. Vendor request for for 50% up-front payment. Finance will look into the payment issue.(Closed) 7. Device not working with current driver version (compatibility issue). Team to require new driver version (dermalog) from S5 before rollout. (Closed) 8. Intermittent network access between JIAS and Fomema-S5 Gateway at NERS. S5 to rectify the root cause and resolve by end Sept 2017. New server provided. (Closed) 9. Insufficient AFIS ID records in myIMMS database. Team to resolve issue with myIMMS team and obtain verification from BTMR. S5 to complete data recovery by 8/10/2017. JIM to resolve the issues (Closed) 10. Windows Version incompatibility issues at Panel Clinic PC. BEANS technical team to resolve issue. (Closed) 11. (PSC 5/2018 - 23/5/2018) PM requested for backup developer for Jualiza since project team has only one developer. SDC Head to identify a person for Jualiza to conduct TOT. (Closed) 12. FOMEMA is still in the discussion with Government to request an Extension of Time (EOT) to allow for deployment to the rest of the Clinics. (Closed) 13. (PSC 11/2018) SDK 1.12.4 will be put on Cloud (Exabyte) for the rest of Clinics to download the latest patches. (PSC 12/2018) Domain registration done and webhosting at Exabyte (M) is ready for use. (Closed) 14. (Transferred from Risk Log):To date, only S5 has performance issue on the device. PSC #9, informed that new SDK 1.12.4 was installed to resolve low quality fingerprints issue and threshold value. The SDK was placed in Cloud-Exayte for immediate download to any Clinics ( Closed) 15. (PSC 1/2019) - DBix vendor of FOMEMA claimed that they have done integration work for HTP and want to claim payment for effort done. Project Team has advised DBix to follow the proper process through FOMEMA. Project Team will only pay upon FOMEMA instruction with proper CR process. (PSC 3/2019) Quotation received from DBix on 20/2/2019. Project Team requires assistance from SDC to assess the quotation and work done. (PSC 4/2019) PM to further discuss with DBix the issues since HTP has no obligation to pay. (PSC 5/2019) Management Committee HTP has agreed to pay for the DBix's CR - Change Request for 70-man-days work (equivalent RM105,000). (PSC 6/2019) Finance HTP agreed to pay DBIX (CR), amounting RM105,000.00 by 30/9/2019. (Closed) 16. (PSC 1/2020) - Time out in getting biodata from JIM. Dynatrace managed to trace the problem is at S5 side. Presnted findings and resolution to Fomema (closed) 17. System Internal Init Error on Windows 7 PC while accessing Dermalog. The issue prior to Microsoft announcement Windows 7 End of Life in June 2020. Steps of procedure has to be triggered to ENABLE TLS 1.0 on each Windows 7 PC at clinic. Prepare Solution Guide and uploaded to Project Exabytes Repository Server. Fomema has broadcasted information and guidance onto its MERTS Portal Task Force with CCC formed starting 5/7/2020 to minimize backlogs (closed) 18. (PSC 7 2018 - 23/7/2018) Subcontract between HTP and S5 is still pending for signing due to payment term which is not agreeable and uncertainty of project. Finance advised to hold the signing. New CEO to sign the Agreement 1st week of Oct with partial payment to S5. (PSC 12/2018) Contract signing still pending. Payment term still not confirmed and awaiting for top management decision. Letter of Demand received from S5 for payment. PM awaiting for management decision. (PSC 3/2019) Contract is still not signed due to indecisive amount of payment term from HTP Management. PM to send email to Group Finance VP to get confirmation status. (PSC 6/2019) PM plan to discuss with CFO on 27/7/2019. (PSC 7/2019) Management has agreed with payment terms and Finance will pay to S5 as agreed by both party. Subcontract document in progress for signing. (closed) 19 (PSC2/2020) Currently HTP has no dedicated Account Manager to talk on business perspective with Fomema as well as top management from HTP to build rapport with Fomema top management PSC2/2020 16/10/2020. Starting July 2020, Fomema Project was tranferred to Internal Security under En aNasrul Hatta supervision as Business Director (closed) (open)
54 | DEFENSE | Closed | SUKHOI-30MKM - TOFT, CBT & Infra Maintenance | 1. Late approval and payment to appointed vendor for critical purchased spares. Management/finance to prioritize urgent approval for critical spares.(In Progress). 2. Roof Leakage (on top of the Simulator Dome). Team to obtain quotation from contractor to conduct thorough investigation on roof of simulator building and resolve issue accordingly.(In Progress-quotation received, awaiting PO issuance. Per forma payment received, has instructed vendor to start work (Closed) 3. RITTEL SK Condenser ( air-conditioning for the Visual System 1 – FMS 2) found leaks and cannot be repaired (Item part number 3397577). SK Condenser need to be replaced. PR to be raised accordingly. Awaiting for payment. Project Team to check the status of SSF as no PR has been raised. Payment done. (Closed) 4. Payment issues with the following items for PM and Finance to follow-up: - Dome painting job completed; invoice for 50% payment is target to pay by end Feb 2018. Payment made. (Closed) - Repair work for roof leakage inside simulator completed; payment done. - 4 out of 7 of CO2 cylinders in the UPS room were triggered during fire drill exercises due to circuitry malfunction. Required full circuitry checks and refill of the CO2 cylinders. PO received. Awaiting 50% proforma payment. Standby manual CO2 fire fighting system is available. Payment received on 16/5/2018 (Closed) 5. PSC 6/2018 - Procurement to purchase projectors. Proposed to purchase direct from BARCO USA instead of local provider IAN Padu, because of cheaper price. Awaiting justification Memo from PM. PSC 7/2018: Request to purchase direct with BARCO has been approved. There will be significant cost saving involved. Project Team will proceed with procurement of projectors. (Closed)
55 | JPJ | Closed | Next Generation Firewall | 1. Hardware delivery issue. PM to revise and finalise deployment plan and ensure timeline is within the agreed project duration.(Closed) 2. License supplied by Data Alliance required additional 25 days in order to comply with project requirement. PM to discuss with Data Alliance. Received updated license on 26/12/2017. Activated via remote on 27/12/2017. (Closed)
56 | MOH | Ongoing blm buat | SPP CAS PHIS Integration-Hospital Raja Permaisuri Bainun Ipoh | 1. Slow performance issue during rollout. Team in progress to resolve issue. All performance issue has been resolved. (Closed). 2. CMG technical team to investigate the TLS and PC setting issue and coming up with result or resolution before 15/2/2019. IT Team still doing the testing. Update: No additional setting done to TLC n PC since letsencrypt option is used to generate ssl cert instead of previously used option selfsign. (Closed)
57 | MOH | Ongoing blm buat | Proof od Concept (POC) HIS@KKM EMR Basic At Hospital Port Dickson | 1. (PSC 2/2020)- Re-authorization for the entire migration of data (billing, medical record, discharge summary) HISKKM considering that only one system will be used and no dependency on the SPP upon completion of the POC. (PSC3/2020) -Data that have been identified to be migrated are Patient Demografi,encounters,discharge summary and appoinment TCA April 4, 2020 onwards. while data of lab, radiology, diet, medicine, and medical record cannot be migrated due to large data structure changes and SPPv2.6 table is no longer used in HISKKM system (closed) 2. PSC 2/2020)- Based on site assessment, the number of computers on wheel (CoW) cannot meet HPD ward1. requirement. IT HPD requested to increase the number of CoW to a ratio (12 beds: 1 CoW) to facilitate the work process (PSC 3/2020) - Increased the CoW number from 4 units to 8 units (open) (PSC4/2020) - CoW delivery in progress(open) (PSC5/2020) - (open) (PSC6/2020) - (closed) 3. (PSC 2/2020)-4G Secondary line is required to assure continuous connectivity ( PSC 3/2020) - WAN Router and 4G LTE Modem has been installed. Pending discussion with core switch and firewall vendor (in progress) (PSC 4/2020)- WAN Router and 4G LTE Modem has been installed. Pending discussion with core switch and firewall vendor (open) (PSC 5/2020- (open) (PSC6/2020) - (closed)
58 | MOH | Ongoing blm buat | RIS PACS HIS@KKM Fasa I | 1. Delay to project timeline since KKM has instructed for UTP cabling installation to stop due to mismatch of understanding on specification of Cat 6A basebox. Project Team Meeting on 25/10/2017 decided that basebox met criteris and approved for cabling work to proceed. (Closed) 2. Delay to project timeline due to change of faceplate SSO Essential works are temporarily stopped while awaiting for change of DB from normal to essential complete. (Closed) 3. Change Request on RIS PACS Business Architecture (change in process flow). Meeting on 2/11/2017 decided to maintain existing RIS PACS but clinician orderable function will use separate VM from radiology processing. (Closed) 4. Infra and Wall mount installation at Operation Theater, ACC Building involved barium and radiation testing. Need to discuss further at KKM level. HTP will bear cost for barrium testing and radiation testing will be done by HRPZ (Closed) 5. HW vendor VIP Tower demanded 100% upfront payment to release equipment to HTP. Pending payment from HTP will cause delay to project. Finance to expedite on payment. All hardware has been delivered (Closed) 6. Change Mmgt Plan (CMP) yet to be finalised and signoff. Impacting unclear scope of deliverables. CMP has been presented to KKM and in principal is agreed by KKM (Closed) 7. (PSC 11/2018) Initial planned to UAT on 19/12/2018 has been deferred to 30/12/2018 which was approved during PSC/KKM 27/11/2018 (Closed) 8. Go Live PACS was done earlier. Warranty and SLA started earlier for Vendor's equipment. Currently, 2 logs on PACS modalities are being escalated to Manufacturer. Problems are resolved by vendor accordingly. (Closed) 9. (PSC 9/2018) Project Team has requested for EOT 4 months with the justification: - Basic Forensic Management Module has become bigger requirement, which initially was only based on good will.; additional scope on RIS stand alone - Delay in getting sign-off for SRS and SDD has impacted timeline for design and development - additional coding time required due to complexity of requirement (PSC 10/2018) EOT has been approved by KKM. (Closed) 10. (PSC 1/2019) UAT was unsucessful due to the following reason: i) System was not thoroughly tested due to time constraint ii) Test script was prepared based on SDD, however for UAT 2 team didn't have enough time to prepare and verify with updated system iii) Overall test case considered fail although certain steps in the test script showed it was successful. iv) Data preparation and mapping was not properly calibrated due to last minutes changes. iv) New requirement came in later and impacted readiness of system. PM to improve internal process, compile all bugs and identify other factors that influenced failure of UAT.(closed) 11. (PSC2/2019) Based on internal discussion, new timeline is to be presented to KKM. Based on UAT Cycle 2 result, Project Team to present again in PSC#3/2019-KKM on 4/3/2019. HTP requested for Anjakan Masa of 5 months, but still within Contract period. (PSC 3/2019) New timeline was presented to Pemandu #1/2019 KKM on 20/3/2019. HTP request on new project timeline was rejected, it will be subjected to UAT Cycle 3. (PSC 9/2019) KKM has approved request for extension of time with LAD imposed to HTP. (Closed) 12. (PSC 9/2018) Fazgate may not be able to support project on infra problem resolution during warranty period which impact problem time resolution. Since there is no subcontract between both parties, HTP have difficulty to hold Fazgate responsible to resolve problems. Project Team to use remaining payment as retention if Fazgate fail to deliver service during warranty period. PM to write officially to Fazgate informing the matter. (PSC 10/2018) Project Team to get Legal advice on the matter. To have proper subcontract with Fazgate. PM in process of finalising subcontract with Fazgate and target to complete by 30/11/2018. (PSC 11/2018) Subcontract being reviewed by Fazgate. Target to finalise by 4/1/2018. (PSC 1/2019) Subcontract in process of signing. Will pass to Fazgate for signing and stamping. (PSC 3/2019) Fazgate still in process of stamping due to stamping cost. (In progress). PSC 7/2019) Fazgate is no longer in business. Hence, the contract is no longer valid. (Closed). 13. (PSC 5/2019) Target delivery of NCT (Non-critical Txns) shifted from 31/7/2019 to 14/8/2019 due to focusing on stabilization of Systems since PAT on 18/7/19) (PSC 6/2019) PAT transaction is yet to achieve 100% pass as per requested by Jawatankuasa Pemandu Bil 2/2019. PM to request for time extension to complete the transaction. FAT and warranty period to be extended due to time extension for PAT. (PSC 7/2019) Related to Non-critical function for Test Case/Script, as at 24/9/2019, 44 test script have passed UAT, 21 test script have passed PAT and only test script involving Laporan Bulanan SMRP could not proceed and agreed to be done during warranty period. Project Team has obtained approval for time extension with penalty. (Closed) 14. (PSC 7/2019) Issue of slowness to the SPP system arised with implementation of RISPACS. Project team is required to take interim action to the issue and resolve during the FAT period. Failure to resolve the issue will cause no acceptance for FAT. Currently, project team is diagnosing and taking necessary action. Solution to be presented to HRPZII on 7/10/2019. (PSC 8/2019) Solution presented to KKM to use load balancer since source code of SPP couldn't be touch. (PSC 3/2020 Suradi update )- KKM agreed on the solution and it had been implemented during FAT period. It resolve the slowness issues of SPP (closed) 15. (PSC 2/2020) - Extension of 1 UTP cable to Royal Ward (PSC 3/2020) - contracted out to KB's vendor to do the work (closed) 16.. (PSC 2/2020) - HRPZII IT do not allow remote access for support services fo rsecurity reason. . (PSC 3/2020 Suradi update )-: HRPZII IT allow for remote access provided HTP provides all necessary information and they will granted the permission on case by case basis only (closed)
59 | JIM | Ongoing | MyIMMs Application Maintenance (2017-2020) | 1. Conflict of priority between myIMMs Maintenance Team and Transformation Team. Team leaders not willing to let the team members to assist the other team due to tight schedule. Project Director is in planning of organising a teambuilding session. Team building done on 27-29/4/2018 (Closed). 2. (PSC 5/2018 - 23/5/2018) Revised timeline in delivering the Transformation project even after EOT to August 2018 has resulted in JIM imposing LAD to HTP with the amount of RM300K++. Project Team to identify factors that contribute to the delay and strategise for appeal for reduction of LAD. PM to properly monitor project activities to ensure new timeline is met. (PSC 6/2018 - 26/6/2018) Meeting to discuss the LAD has been made. Initial action agreed was to write to JIM and inform on correction calculation of LAD and negotiate for discount. (closed) 3. (PSC 6/2018 - 26/6/2018) Slow in development and resolving technical issues due to: - Inadequate no of .Net expert in team – Too much reworks - Slow device integration development - Inadequate no of developer Project Team requires sufficient and skilled developers to ensure revised timeline can be met. (PSC 10/2018) SDC and HR are assisting in fulfilling the required resources. (Closed) 4. (PSC 9/2018 - 25/10/2018) Roll-out for myIMMS Transformation Phase 1 and 2 is delayed due to insufficient supply of SAGEM FP devices (MS300/M1300). There will be impact on cost and timeline since Project Team need to revisit the branches which PM activities were already done. PSC 10/2018 - 27/11/2018) Schedule rearranged to accomodate work for roll-out of Passport, Permit and PM activities. Roll-out target to complete in March 2018 (Closed) 5. (PSC 12/2018) - Slow progress development for phase 3 in Transformation is due to rework and bug fixing of production issues of Phase 1 & 2. Project Team is advised to convince BTMR to stop any new deployment of completed transaction and focus the team to complete all development. (Closed) (PSC 1/2019) - Project Team has implemented for Phase 3. (Closed) 6. (PSC 12/2018) - Device integration with NERS, Project Team is facing difficulty in resolving issues with S5 since the technical person was not around to resolve issues. Project Team to request from BTMR for S5 technical team to be with the team until problem is resolved. (PSC 4/2019) UAT done. (Closed) 7. (PSC 1/2019) - Project Team is not allowed to access production which slow down problem resolution process and impact SLA. Project Team to work with BTMR on testing at production as part of TOT process. Project Team to get agreement from BTMR for SLA to start/& stop at certain point to avoid being penalised for delay on BTMR part. Once HTP team provides Script/coding for BTMR to execute. SLA clock HTP will stop. (Closed) (PSC 2/2019) - BTMR will take up the task involving testing in production. (Closed) 8. (PSC 5/2019) - Users still using old transaction after implementation of new transactions especially for Sistem Passport and Permit. Project Team to plan for closing of old trasactions after system stabilisation target to be by 30/6/2019. (PSC 6/2019) Closing for Sistem Passport and Permit are still in progress. (PSC 7/2019) Rollout for Passport, Permit and Hasil are completed.(Closed) 9. (PSC 7/2018- 25/7/2018) System slow response which may be due to high bandwidth utilisation. Project team need to measure myIMMs bandwidth requirement and submit to JIM BTMR. (PSC10/2018) BTMR has still not given the required bandwidth to be tested. (PSC 12/2018) Project team has installed a few tools to collect the information that might caused the slow response and come out with the following : - bandwidth optimum size required by myIMMs web - Any process/ SQL that can be enhanced /optimized (PSC 1/2019 ) - Project team need a license monitoring tool to investigate application slow response/ hang issues. SDC proposed to use the trial version temporarily. (Update 31/12/2019) - Bandwidth has been shared with JIM and most main JIM branches have been upgraded except for small branches. Upgrading of bandwidth is under JIM action. (Closed) 10. (PSC 12/2019) - XML Injection must be completed by 30/3/2020 but the project team is facing technical errors during internal testing and need help from HTP technical experts. (In progress) (PSC 1/2020) - SDC technical team managed to identify and resolved the problem.(closed) 11 (PSC 4/2020) – PM3 for China, Hong Kong, Taiwan , USA, Taiwan, Cambodia and India to be reschedule due to MCO. Letter to KDN was submitted on 7/4/2020 and awaiting further instruction. (open) (PSC 5/2020) - HTP had received the letter regarding the activity delay in those countries. (closed) 12. ( PSC2/2020)- HeiTech Padu is requested to provide 24 hours support for KLIA, KLIA2, BSI and KSAB via letters, IM.101/B/KLIA-P/1122/73(31) and IM. 101/HQ-D/978/30(24) dated 13 February 2020 and 20 January 2020 respectively. Currently, HeiTech Padu provides supports during office hours for the above four sites. We have replied the above letters on 17 February with the assistance from HeiTech lawyer but was rejected today by JIM lawyer. à Additional eleven (11) implementation analysts are required in 3 shifts for each site as to provide 24 hours support (open) (PSC 5/2020) - HTP had agreed to deploy people to these sites but PBD instructed through whatsapp HTP to hold. HTP had been waiting an official email. The email might be backfired to BTMR, thus En Hatta, En. Khairi and En Azlan will discuss with PBD this issue (PWC 2/2020)- This requirement will be budgeted for in the new contract (closed) 13. (PSC 11/2018) - KPI raised concern that Transformation not completing as target in August 2018. HTP had send justification letter for the delays on 13/11/2018. But, pending reply from KDN. (PSC 1/2019) - Project Team has revised the timeline and target to complete the project by 31/5/2019. PM was given the budget to pay for extra effort done by Project team as motivation to expedite activities and successfully done for preparation of program specification. It will be extended to application development. PM to monitor the quality of work done. (PSC 6/2019) Roll-out of all systems except Sistem Kawalan have been done successfully. Kawalan is target to complete in August 2019. (PSC 10/2019) Roll-out for Sistem Kawalan A (17 transactions) has already completed and pilot at KLIA2 since 8/8/2019. Roll-out will be done when 27 transactions in Kawalan B complete. Kawalan B was delayed since user won’t accept. Project team in process of fulfilling the requirement. Target completion pilot 2 on15/11/2019. (PSC 12/2019)- Target pilot 2 at KLIA2 is rescheduled to 10/1/2020 and rollout will be from 13/1/2020 until 31/1/2020. (PWC2/2020) - Transformation modules have completed and acceepted by JIM on 13/8/2020. (closed) 14. (PSC 1/2020) - Concerns on the amount of the penalties imposed due to breached SLAs. For 2019 (Jan to September) penalties imposed to HTP is RM167,185..83 (PWC 2/2020) - Penalties due to breach SLAs hve been brought down around RM 3000 to RM4000 amonth regular monitoring, daily discusion between IAs and SAs (closed)
60 | JPJ | Closed core3 | JPJ Mobile Handheld Enforcement | 1. MobileFirst Server: Failure to deploy application due to incorrect server deployment. To work with IBM. (In progress) 2. Development Vendor - scope deviation and actual on-site effort burst over 3 weeks, therefore require additional cost RM 25,000 to outsource development for Offline version. To engage Innovatz Solution (In progress) 3.PSC 2/2018 (21/2/2018): Lack of expertise for developing function using features in Mobile First. Not able to deliver MobileFirst feature (dependency to get support from IBM). PM to engage third party company which have MobileFirst expertise to perform the task. As at 24/4/2018: Quoation obtained from iSentric amount RM34.8k. PSC 6/2018 (22/6/2018): will not proceed with Push Notification and therefore no need to engage third party. (Closed) 4. PSC 3/2018 (22/3/2018): JPJ considering between MobileFirst vs Knox Manage. Project Team to perform POC for Knox Manage (VO) via JPJ VPN to deliver feature Push Notification & Application Publishing & Application Automatic Updating (Tender Compliance & Technical Proposal) PSC 6/2018 (22/6/2018): JPOC Knox Manage done. 9 units of production devices already released. (Closed) 5. (PSC 10/2018) Push notification function for could not be done with Mobile First which is proposed in tender proposal. JPJ agreed to omit the feature and swap with with PCID application. Project Team to get formal approval from JPJ. (PSC 1/2019) Approval to swapped was obtained and development in progress. (Closed)
61 | JTKSM | Closed | JTKSM WNP | NA
62 | JTKWP | Closed | JTKN Hardware Supply | NA
63 | DATASONIC | Closed | DATASONIC SMART SOLUTIONS: DTSB Onechip Integration with myIMMs | NA
64 | BORDERPASS TRAVEL | Closed | BORDERPASS TRAVEL: Integration between myIMMs and eGate ASEAN Borderpass | NA
65 | ITSB | Closed | INTIPADU TECHNOLOGY: Integration with myIMMs PLKS & Enforcement modules | NA
66 | MDEC | Closed | MALAYSIA DIGITAL ECONOMY CORPORATION (MDEC): Development of webservices for integration between eXpat system and myIMMs | NA
67 | JPJ | Closed | PUSPAKOM: IBM Websphere Subscription + Renewal
68 | TALENTCORP | Closed | TALENTCORP: RP-T System Integration with myIMMs | NA
69 | MDEC | Closed | MALAYSIA DIGITAL ECONOMY CORPORATION (MDEC): Development of webservices for integration between MTEP system and myIMMs closed | NA
70 | MAHB | Ongoing | MALAYSIA AIRPORT HOLDINGS BERHAD (MAHB): SKI Automated QMS Integration with myIMMs | NA
71 | MOH | Ongoing | CRITICAL CARE INFORMATION SYSTEM (CCIS) | 1. (PSC 3/2019) Project Team requires expert on SPP to give briefing on SPP. Due to project commitment and busy schedule, briefing still could not be done. PM to discuss with respective team to find suitable date to do the briefing session. PSC 5/2019 All required briefing and discussion on SPP have been conducted. (Closed) 2. (PSC 3/2019) SA or AD Leader with knowledge on SPP is still vacant. User Requirement process need the involvement from SA or ADL. SDC to find the suitable candidate urgently.(closed) 3. (PSC 5/2019) PM to revise timeline for integration to be done in October 2019 since CD and RISPACS have been implemented and experts from the projects can be released and join CCIS project team. (In progress) (PSC 6/2019) PM has revised timeline for integration to be done in October 2019.(Closed). 4. (PSC 5/2019) Based on site assessment finding, Project Team has identified devices which integration requires 3rd party integration hardware/software. KKM inform that HTP must bear the incurred cost as stated in Jadual 3 of tender document. (PSC 6/2019) Based on meeting with KKM on 18 July 2019, the working committee agreed that the obsolete hardware/software will be replaced by hospital. HTP and Netlee would only bear the cost of integration card.(Closed) 5. (PSC 7/2019) KCSB is not performing their work as required/planned. PM to send letter to CEO of KCSB to highlight about the issues and request to assign new PM for the infrastructure work. Chairman has also instructed for Zulkifli Kassim to be assigned to CCIS Project for two months, to monitor KCSB work. (PSC 8/2019) PM has already sent a letter of complaint and there is some improvement seen. As for assigning Zulkifli Kassim to monitor KCSB work, he will be involved as and when required. (Closed) . 6. (PSC 6/2019) Hospital Melaka has not enough electrical capacity to run CCIS Project. Project team to obtain approval from MOH on reduction of scope cost. (PSC 7/2018) Hospital Melaka will implement CCIS at one of two wards to match with electrical capacity. Cost was approved in MOH PSC on 14/10/2019. (Closed) 7.(PSC 6/2019) Project Team need to identify listed equipment that are able to be integrated but these devices are not able to service all allocated bed as per tender specification.i.e HTAR has 32 ICU beds but medical devices that are able to integrate only 5 monitor. (PSC 9/2019) Equipment has already been identified and will be confirmed during implementation. (Closed) 8. (PSC 7/2019) KCSB has installed a 63AMP electrical DB at the sites without the official agreement with HeiTech and KKM, whereas in the contract with KKM it has already agreed in the tender/contract for 250AMP. Since work was already done, HeiTech need to get the agreement from KKM. PM to propose to KKM on how to counter the reduction in the contract. (PSC 8/2019) KCSB has already explained the reason which indicated that Project has provided more than the tender requirement. PM will present the explanation to KKM accordingly. (PSC 9/2019) PM has presented the explanation to KKM. (Closed) 9. Change of UPS Servers (10Kval) (PSC DEC 2019 - to obtain latest design. Approved by MOH PSC on 14/10/2019 (closed) 10. Change for UPS for Switch and for servers have been approved in MOH PSC on 14/10/2019. (Closed) 11..(PSC 6/2019) Project Team need to identify listed equipment that are able to be integrated but these devices are not able to service all allocated bed as per tender specification.i.e HTAR has 32 ICU beds but medical devices that are able to integrate only 5 monitor. (PSC 9/2019) Equipment has already been identified and will be confirmed during implementation. (Closed) 12. (PSC 7/2019) KCSB has installed a 63AMP electrical DB at the sites without the official agreement with HeiTech and KKM, whereas in the contract with KKM it has already agreed in the tender/contract for 250AMP. Since work was already done, HeiTech need to get the agreement from KKM. PM to propose to KKM on how to counter the reduction in the contract. (PSC 8/2019) KCSB has already explained the reason which indicated that Project has provided more than the tender requirement. PM will present the explanation to KKM accordingly. (PSC 9/2019) PM has presented the explanation to KKM. (Closed) 13. Change of UPS for Switch brand from Liebert to Vertiv due to discountinue sales Updated Mach 2020 ( closed) 14. 2.(PSC 6/2019) Project Team need to identify non related CCIS medical devices/equipment in the tender list that will cause non 100% integration medical device status. MOH has reviewed but decision still pending at MOH. Updated Mach 2020 (closed) 15. 1. (PSC 6/2019) Delay in approval of hardware brand change have caused delay to hardware delivery and sign-off. The following hardware:- i . Change of Printer brand from HP to Canon (open) (PSC 5/2020)- HTP letter agreed on MoH suggested printer model HP m507dn. Requested MoH confirmation for HTP to raise order due to: Delivery orders will be extended due to COVID-19 virus outbreak that cause stop HP production in China (PSC 6/2020) - HTP agreed with MoH suggested printer model which is HP m507dn. MoH requested HTP to confirm order : • Delivery orders will be extended due to COVID-19 virus outbreak that cause stop HP production in China. • Delay in delivery of printer will cause the delay in Parallel Testing. (HTAA & HQEI) • Delay for hospital to raise budget for toner. HTP is no longer providing toner to HTAR and HTAA for the Parallel Testing. (closed) 16. 3. (PSC 1/2020) - Discharge summary printing for CCIS stand alone hospital (open) (PSC 5/2020)- (open) - MOH to advice on the policies to standardize the process. - HTAR will print only Discharge Summary for the usage of other primary care doctors (PSC 6/ 2020) - MOH policies to standardize the process based on best practice where Discharge Summary will be main documentation for next treatment process( closed) 17. 4. (PSC 1/2020) - Additional ICU infection control protocol requirements identified upon delivery of hardware. (open) (PSC 5/2020)- HTP proposed MOH to advice all hospital that these new requirements is not within the project scope Requested hospitals are HTAR, HUS, HAS, HMelaka, HQEI, HPP (PSC 6/2020) - HTP propose MOH to advice all hospital that these new requirements is not within the project scope (closed) 18. ( PSC 2/2020) - Requirement of IP Address and Network segmentation is needed from all hospitals (PSC 5/2020)- HTP needs to review the existing network in HUS before configure CCIS network for not to interrupt with future Hospital Network configuration. Currently there is no Core Switches available in HUS. (PSC 6/2020) - Obtain IP Address from GITN for CCIS configuration KKM request to review the existing network and Core Switch requirement ( closed) 19. ( PSC 2/2020) -Additional electrical work for UPS installation in HQE and HUS ( open) PSC 5/2020)-(open) Delay in decision due to ICU converted to COVID 19 center HQEI – 27/2/20 completed reconfigure and reinstall HTP additional ELCB in the current DB HUS – Target in end Mac 2020 after complete hardware work in HPP an HRPB (PSC 6/2020) - HQEI – 27/2/20 completed reconfigure and reinstall HTP additional ELCB in the current DB (closed) HUS - Target Sept 2020 after complete hardware work in HPP an HRPB (open) 20. ( PSC 2/2020) -Readiness in Hospital antivirus and intrusion policy (PSC 5/2020)- HTP recommended that all hospital has to comply to MOH standard antivirus protection policy to safeguards the IT network (PSC 6/2020) - KKM Project Working Committee (PWC) agreed that all hospital to comply to MOH standard antivirus protection policy to safeguards the IT network ( closed) 21. ( PSC 2/2020) -Mobility and ease of trolley movement due to limited working area in ICU ( open) (PSC 5/2020)- HTP propose to use project cost saving of RM896K KKM agreed to present it in the next Technical Meeting (PSC 6/2020) - KKM Project Working Committee decide that this is nice to have requirement (closed) 22. (PSC 4/2020)- Resource - Infra & Tech Support – Team Leader (Shahril) resigned resigned in Aug 2019 18 Mac 2020 - Resource available and getting Cloud Hosting to start off development work 19 Mac 2020 – WFH and concentration on project documentation (open) (PSC 5 /2020) – ( open) 1) Shahbuddin has to oversee Infra (KCSB) work 2) Waiting for Integration team and resources will be released after CD go live in Aug 2019, proceed with workshop for Stand Alone hospital in May 2019 and integration workshop in Dec 2019 3) Shahbuddin has to oversee the Tech Support team and called for discussion with HMS and Healthcare team, agreed that HMS Rizaki team will lead 4) Jipri team need to review Netvault SOP, installation guide and test script as this will also be used during IT Central Training (PSC 6/2020)-– monthly ccordination discussion on Healthcare project matter (Closed) Jipri team to review Netvault SOP, installation guide and test script as this will also be used during IT Central Training while Rizaki will lead HMS team (closed) 23. PSC 4/2020)- Solution Architect and SME feedback Delay in getting internal Health Solution Architect / SME feedback on SRS and SDD, this will delay in providing the final documentation to KKM for review and feedback. Getting assistance with ADL from RIS/PACs and CD to review the documentation (open) (PSC 5/2020) - Getting assistance with ADL from RIS/PACs and CD to review the documentation. This will also provide an overview to other project that CCIS project will be integrated to the respective system (open) (PSC 6/ 2020) - Getting assistance from RIS/PACs and CD ADLs to review the documentation. This will also provide an overview to other project that CCIS project will be integrated to the respective system Monthly discussion on Healthcare project matter- (closed) 24. PSC 4/2020)- Development Integration module Resources only available- SA Oct 2019 and Jan 2020 SD - Dec 2019 (junior developer) and Feb 2020 (senior developer) Strategy – to deliver a Stand Alone CCIS solution (open) (PSC 5/2020) - Take advantage on MCO period has caused in overall project delay Escalate the development work – 2 available resources available + 2 assistance from current CD resources • Saufi • Zaidi Note: Strategy – to deliver a Stand Alone CCIS solution if COE delay (PSC 6/2020) - – Monthly coordination discussion on Healthcare project matter En Aizam will coordinate the progress through weekly discussion( closed) 25. (PSC 1/2020) - Medical record roles and access of CCIS data. HTAR not able to go live without confirmation of process and policies. (open) (PSC 5/2020)- (open) - Delay in decision due to ICU converted to COVID 19 center MOH to advise on the policies - HTAR requested for MR Dept to do the printing - MR Dept needs to access to CCIS, however issues are: - No allocation of PC to MR Dept - Additional network wiring and network configuration is need to provide access to MR Dept - Who responsible for CCIS ID creation (PSC 6/2020) - Agreed in KKM Project Working Committee PWC and Technical Meeting Committee endorsed for relocate PC to Medical Record unit at respective hospital To bring to Steering Meeting Committee for endorsement PWC 2/2020 - Agreed in KKM Project Working Committee PWC that additional PC will be used for hospital that requested for additional CCIS License except for Hospital that requires PC. Will raised in Project Technical Committee (PTC) and Project Steering Committee (PSC) for endorsed and approval. (closed) 26. ( PSC 2/2020) -Hospital people readiness and coordination in accepting CCIS systemClosed - on HMLK Code Orange Issue WIP - HTP will discussed and present with KKM Project team on the new revised timeline due to delay of MCO and site readiness (closed) 27. ( PSC 2/2020) - equipment for HPP. HPP is lacking of additional 10 trolley thus will affect the delivery and installation of PC at bedside ( PSC 6/2020)- KKM Project Working Committee (PWC) meeting has agreed. Project Technical Committee (PTC) meeting endorsed and to bring to Project Steering Committee (PSC) Meeting for approval and to obtain Tender Board to use the Project Cost Saving for additional Trolley PWC 2/2020 WIP - KKM Project Working Committee (PWC) meeting agreed. Project Technical Committee (PTC) meeting endorsed and to bring to Project Steering Committee (PSC) Meeting for approval and to obtain Tender Board to use the Project Cost Saving for additional Trolley PSC 2/202015/10/2020 Approval obtained on 30/9/2020 (closed) 28. .( PSC 2/2020) - HRPZ Electrical Infrastructure ( open) (PSC 5/2020) - Delay in decision due to ICU converted to COVID 19 center HTP propose to use the unallocated DB (available 2 units from HMelaka and HTJS) Discussion with HRPZ on 11 Feb 2020 Submit proposal on 25 Feb 2020 (PSC 6/2020) - KKM Project Working Committee (PWC) meeting agreed. Project Technical Committee (PTC) meeting endorsed and to bring to Project Steering Committee (PSC) Meeting Committee for approval to use the unallocated DB (available 2 units from HMLK and HTJS) pwc 2/2020 WIP - KKM Project Working Committee (PWC) meeting agreed. Project Technical Committee (PTC) meeting endorsed and to bring to Project Steering Committee (PSC) Meeting Committee for approval to use the unallocated DB (available 2 units from HMLK and HTJS) Discussion with HRPZ on 11 Feb 2020 and agreed with proposal on 25 May 2020 (closed) 29. ( PSC 2/2020) -Readiness of Hospital infrastructure site (open) (PSC 5/2020) - HTP will deliver all required hardware but instalationl of respective hardware will be delayed until the completion of Ward ICU3. HTP is proposing payment based on delivering of hardware (PSC 6/2020) - HTP will discussed and present with KKM Project Working Committee (PWC) team on the new revised timeline due to delay of MCO and site readiness PWC 2/2020 - HTP will discussed and present with KKM Project Working Committee (PWC) team on the new revised timeline due to delay of MCO and site readiness PSC 2/2020 15/10/2020 Presented and approved by PWC on 21/9/2020 (closed) 30 PSC 2/2020 15/10/2020 ( PSC 3/2020) -COVID19 and Movement Control Order MCO till 14 Apr 2020 most likely will impacted payment and Implementation (open) ( PSC 5/2020) – MCO is further extended until 12 May 2020. Payment requested for 2.5M may be delayed as KKM has yet to provide LO to proceed with payment Implementation to put on hold: • All 11 site hospital are converted into COVID19 center • All hardware are to put aside to cater for COVID10 operation (open) (PSC 6/2020 ) - Raised in KKM Project Technical Committee (PTC) Meeting – acknowledge Suggest & advice from KKM: • To request for EOT by 3 months before end of contract • To present the revised timeline in KKM Project Working Committee PWC Meeting for detail discussion • To include stand alone to all 11 site • To include integration timeline after stand alone 3 hospital PSC 2/2020 15/10/2020 Payment received 30/5/2020 (closed) 31 PSC 4/2020)- Partner Netlee Limited resources Incomplete and delay in project documentation Delay in the plan and strategy on BI & Medical Device status (open) (PSC 5/2020) – HTP (BD ,PD and PMC) will meet with Netlee to discuss the issue on 3/6/2020 (PSC 6/2020)- Netlee has deployed 3 team to do expedite the deployment process PWC 2/2020 - - Netlee has deploy 3 team to do escalate deployment process Initiation Phase – Installation of Picis server & Medical Device nstallation of Picis 15/10/2020PSC 2/202–PSC 2/2020 15/10/2020 Local configuration Activation Phase – verification and train Supper User / Change Agent (open)
|  |  | CCIS | 30. PSC 2/2020 15/10/2020 Net Lee has hired new staffs to look into the project management matters while the existing stffs will focus on the technical matters. (closed)
72 | HRPB MAINT | Ongoing |  | Contract renewal still not ready. (CLOSED)
73 | EMGS - STAR | Closed | EDUCATION MALAYSIA GLOBAL SERVICES (EMGS): Annual lMaintenance Support IntegrationBetween EMGS and MYIMMS closed | NA
74 | JPJ | Ongoing | Next Generation FireWall - NGFW (2018 - 2020) core3 | 1. (PSC 1/2019) PO has been issued to Infomina to purchase software license for Firewall. However, Infomina has only issued half of payment to Data Alliance and hence partial delivery by Data Alliance which has impacted the overall timeline and delay some activities to be done. Finance informed that Infomina will pay by 1/2/2019 and delivery is target to be in mid February 2019. (PSC 2/2019) Payment made and delivery done. (Closed)
75 | JPJ | Closed | mySIKAP Maintenance Extension (Jan - June 2019) core3 | 1. PSC 2/2019 - JPJ (application team) claimed that they only started log issues to CCC on 15-Jan-2019 therefore JPJ (application team) claimed that corrective maintenance has not been done for 1-Jan-2019 till 15-Jan-2019, there fore HTP cannot bill 100% for Jan 2019 (RM682,287.50) PM to send official letter to describe the issues and to ask for their reconsideration Alternatively, to nego for some coaching mandays on mySIKAP if not accepted. PSC 3/2019 - PTD agreed to close if HTP can prove that JPJ had logged issues that were reported during 1-15/1/2019 regardless actual date reported was after 15/1/2019. PSC 5/2019 - Based on PPU JPJ feedback, HTP is entitled to claim for the issues that were reported during 1-15/1/2019. (Closed) 2.P SC 5/2019 - Out of 62 software licences only 52 licences will be renewed. Remaining licences won’t be renewed since functions have been replaced by other software. Amount of RM772k++ could not be claimed from project amount. Project Team to get confirmation on software not to be renewed and prepare supplementary/addendum contract on changes incurred. (PSC 6/2019) Project Team has presented in the JPP Meeting and accepted. (Closed)
76 | MBPP, MBSP | Ongoing | Penang Smart Parking (PSP) updated for sept | 1. PSC 5/2019 - Difficulties in forming the project team fast (experienced SA/BA & Developer) since the short timeline for Phase 1 delivery. SDC and HR to expedite process of getting the complete team on board. (closed) 2. PSC 5/2019 - Late conduct of Procurement Committee Meeting give impact to negotiation with vendors resulting in late issuance of PO and hence delivery of services/product by vendors. PSC 6/2019 - Procurement done and PO issued to relevant service provider. (Closed) 3. (PSC 6/2019) - Late sensor delivery due to late SIRIM certification. Sensor installation could not be started. Resolution Project team to start with baymarking, coring and numbering . Then sensor installation can be started. (PSC 8/2019) Sensor for Phase 1 has been delivered. (Closed) 4. (PSC 8/2019) - Lack of resources. Pending vacancy: AD Manager (1), SA (1), SE (1), Infra Lead (1), Developer (3). (PSC 11/2019) Vacancy filled from new recruitment (closed) 5. (PSC 8/2019) - Dependency on Gerbang Bestari for bugs fixing and resolution. Recruitment of three developers is in progress. Minimal support from mySIKAP due to project commitment. (PSC 8/2019) - Interview is in progress. Target to get the developer in early November 2019. (PSC 4/2020)- Source code has been obtained from GB on 10/2/2020. Currently supported by 5 developers from mySIKAP (open) (PSC 6/2020) – Currently supported by 5 developers from mySIKAP. Source code has been obtained from GB on 10/2/2020. (closed) 6. (PSC 8/2019) - Poor quality of application developed by vendor/project team. To get advise from internal expertise and review overall architecture and design including the source code. Ongoing process (PSP 6/2020) – to obtain from internal expertise (En Ahmad Soupian ) ( closed) 7. (PSC 1/2020) Team concurrently provide support/resolution action for incident log (phase1) and development (phase 2) . Action to prioritize task and getting help from internl staff. (PSC 4/2020)- Obtain assistance from mySIKAP team and interns until 30/6/2020 PSC 6/2020 – Obtain assistance from mySIKAP team and interns till 31/7/2020 (closed) 8. ( PSC 3/2020) - Delivery of Batch 1 sensor (15,000 unit) due to COVID19 outbreaks which affects the supply chain for sensor's communication module and PCB. To revise timeline and obtain approval from Councils. ( in progress) (PSC 4/2020)- Batch 1 target delivery in June 2020.Revised timeline for Batch 2 and 3 (extension of 12 months) was presented in the TSC meeting on 21/4/2020. Awaiting council response (open) (PSC 6/2020) – Batch 1 has arrived on 27/6/2020. Revised timeline for batch 2 and 3 (7 months extension) has been presented in TSC meeting on 20/5/2020 and approved in MMK on 10/6/2020 (closed) 9. ( PSC 3/2020) - No decision/acceptance on type of sensor (surface mounted) from Majliswill affect overall implementation strategy and timeline. Procurement for Batch 2 & 3 need to be made soonest to avoid delay. To obtain support from MIROS in order to speed up buy in from Majlis. (PSC 4/2020)- Meeting with MIROS was held on 11/3/2020. MIROS responded on 30/3/2020 indicating that they have no issue on surface mounted sensor implementation To discuss with JKR after MCO lifted. (PSC 6/2020) – Meeting with MIROS was held on 11/3/2020. MIROS responded on 30/3/2020 they have on the issue of on the surface mounted sensor implementation. Discussion with JKR cannot pursue due to MCO. TSC meeting on 25/2/2020 has approved this sensor(closed) 10. (PSC 4/2020) – Installation of time control board, bay marking, promotional related activities and change management training has to put on hold due to MCO and this has affected the overall timeline. (PSC 6/2020) – Revised plan and status has been presented in the TSC meeting on 20/5/2020. Time Control Board bay marking promotional and change management activities will continue after MCO (closed) 11. (PWC1/2020) Sigfox Network signal is not strong enough to enable the smooth transmission of signal between the sensor and the base station. This will give impact to PSP dashboard and publics mobile application for not showing the right information of parking activities. This activity target to start on 12 August 2020 at FIZ and Bandar Sunway sites. 13 sites at MBPP and 10 sites at MBSP has been identified. Target to complete all sites by end of October 2020 (open) PSC 1/2020 16/10/2020 The signal and coverage is getting better and strong (closed)

## Billing Plan Y2020 (hidden)
BIILING PLAN Y2020
checking
No. | Main Project | Status | Project Name | Project Value (RM) | Total Billed as at 31/12/2019 | Balance to Bill (RM) | 2020 BILLING PLAN/PROJECTION | [11 empty] | TOTAL PLAN Y2020 | TOTAL PLAN Y2021 | TOTAL PLAN Y2022 | Remaining | Remarks | variance
[7 empty] | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC
TRANSPORT
1 | JPJ | Ongoing | New Generation FireWall - NGFW 01 Oct 2018 - 31 Dec 2020 (2 Years 3 Mths) | 2979157.4222 | 1647031.88 | 1332125.5422 | 0 | 0 | 0 | 1241650.24 | 0 | 0 | 30158.43 | 0 | 0 | 30158.43 | 0 | 30158.44 | 1332125.54 | 0.0022 | 0 | 0 |  | 0.0022
2 | JPJ | Ongoing | mySIKAP Maintenance Extension Jul 2019 - Oct 2019 (4 mths) - 2nd extension - Carry forward for On Request | 7016592.27 | 4833869.24 | 2182723.03 | 1273705.39 | 0 | 0 | 0 | 0 | 909017.64 | 0 | 0 | 0 | 0 | 0 | 0 | 2182723.03 | 0 | 0 | 0 |  | 0
3 | JPJ | Ongoing | mySIKAP Maintenance Extension Nov 2019 - Dec 2019 (2 mths) - 3rd extension | 3508296.13 | 1764232.2 | 1744063.93 | 1744063.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1744063.93 | 0 | 0 | 0 |  | 0
4 | JPJ | Ongoing | mySIKAP Maintenance Extension Jan 2020 - June 2020 (6 mths) - 4th extension | 10524888.4 | 0 | 10524888.4 | 2020 BILLING PLAN/PROJECTION FEB: 1391222.44; 2020 BILLING PLAN/PROJECTION MAR: 1391222.44; 2020 BILLING PLAN/PROJECTION APR: 4959998.64; 2020 BILLING PLAN/PROJECTION MAY: 1391222.44; 2020 BILLING PLAN/PROJECTION JUN: 1391222.44 | 10524888.4 | 0 | 0 | 0 |  | 0
5 | PSP | Ongoing | Penang Smart Parking (PSP) - Majlis Bandaraya Pulau Pinang (MBPP) - Majlis Perbandaran Seberang Prai (MPSP) 01 May 2019 - 30 April 2026 (7 years) | 259686000 | 357814.21 | 259328185.79 | [12 empty] | 0 |  |  |  |  | 259328185.79
|  |  |  | 283714934.2222 | 8602947.53 | 275111986.6922 | 3017769.32 | 1391222.44 | 1391222.44 | 6201648.88 | 1391222.44 | 2300240.08 | 30158.43 | 0 | 0 | 30158.43 | 0 | 30158.44 | 15783800.9 | 0.0022 | 0 | 0
INTERNAL SECURITY
1 | JIM | Ongoing | myIMMS Maintenance 18 Aug 2017 - 17 Aug 2020 (3 Years) | 42430740 | 29230993.19 | 13199746.81 | 963554.65 | 1008810.48 | 1008810.48 | 1008810.48 | 1008810.48 | 2598810.48 | 1008810.48 | 1008810.48 | 1805561.6 |  |  |  | 11420789.61 |  | 0 | 0 |  | 1778957.2
2 | JIM - BESTINET | Ongoing | JIM-BESTINET/FWCMS 1 Nov 2018 - 31 Oct 2021 (3 Years) | 2289600 | 890400 | 1399200 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 63600 | 763200 | 636000 | 0 | 0 |  | 636000
3 | JIM - MYEG | Ongoing | JIM-myEG (Transaction Basis) Transaction base since 2013 | 2400000 | 2766555.23 | -366555.23 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 600000 | 0 | 0 | 0 |  | -966555.23
4 | JIM - MAHB | Ongoing | JIM - MAHB QMS Integration 29 Dec 2017 - 23 Mar 2018 | 625292 | 657223.5 | -31931.5 | [12 empty] | 0 | 0 | 0 | 0
5 | JIM - VKSB | Ongoing | JIM - VISTA KENCANA 01 Oct 2014 - 30 Sept 2017 (3 Years) | 180000 | 166368.31 | 13631.69 | 2020 BILLING PLAN/PROJECTION JAN: 2122.12; 2020 BILLING PLAN/PROJECTION FEB: 2000; 2020 BILLING PLAN/PROJECTION MAR: 2000; 2020 BILLING PLAN/PROJECTION APR: 2000; 2020 BILLING PLAN/PROJECTION MAY: 2000; 2020 BILLING PLAN/PROJECTION JUN: 2000; 2020 BILLING PLAN/PROJECTION JUL: 1509.57 | 13631.69
|  |  |  | 47925632 | 33711540.23 | 14214091.77 | 1079276.77 | 1124410.48 | 1124410.48 | 1124410.48 | 1124410.48 | 2714410.48 | 1123920.05 | 1122410.48 | 1919161.6 | 113600 | 113600 | 113600 | 12797621.3 | 636000 | 0 | 0
FOMEMA
1 | FOMEMA | Ongoing | FOMEMA MYIMM Biometric Integration 01 Jan 2017 - 31 Dec 2026 (10 Years) | 48230000 | 19817957.9 | 28412042.1 | 0 | 0 | 1439946.43 | 0 | 0 | 1439946.43 | 0 | 0 | 1439946.43 | 0 | 0 | 1439946.43 | 5759785.72 | 5759785.72 | 5759785.72 | 11132684.94 |  | 22652256.38
|  |  |  | 48230000 | 19817957.9 | 28412042.1 | 0 | 0 | 1439946.43 | 0 | 0 | 1439946.43 | 0 | 0 | 1439946.43 | 0 | 0 | 1439946.43 | 5759785.72 | 5759785.72 | 5759785.72 | 11132684.94
HEALTH/MOH
1 | CCIS | Ongoing | Critical Care Information System (CCIS) 1 Feb 2019 - 31 Jan 2022 (3 Years) | 33179367.26 | 0 | 33179367.26 | 0 | 0 | 2556500 | 15388505.53 | 0 | 0 | 0 | 8747789.34 | 0 | 0 | 0 | 5298350.13 | 31991145 | 634133.01 | 554089.25 | 0 |  | 1188222.26
2 | CD | Ongoing | Clinical Documentation 21 Mar 2016 - 20 Mar 2020 (4 Years) | 30101218.92 | 26191691.74 | 3909527.18 | 0 | 0 | 0 | 0 | 3190968.37 | 251512.56 | 0 | 0 | 0 | 0 | 0 | 0 | 3442480.93 | 0 | 0 | 0 |  | 467046.25
3 | RISPACS | Ongoing | RIS PACS HIS@KKM Fasa I 17 Jul 2017 - 16 Jan 2020 (30 Months) | 10090979.26 | 7455217.95 | 2635761.31 | 0 | 0 | 0 | 2227057.827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2227057.827 | 0 | 0 | 0 |  | 408703.483
4 | HRPZII | Ongoing | Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu - Perkhidmatan Penyelenggaraan 01 Oct 2019 - 31 Dec 2019 (3 mths) | 226639 | 187492.8 | 39146.2 | 17025.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17025.77 |  |  |  |  | 22120.43
5 | HRPZII | Ongoing | Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu - Perolehan Peralatan Tambahan 01 Nov 2019 - 28 Feb 2020 (4 mths) | 496000 | 0 | 496000 | 2020 BILLING PLAN/PROJECTION APR: 496000 | 496000 |  |  |  |  | 0
6 | HRPZII | Ongoing | Hospital Raja Perempuan Zainab II (HRPZ II), Kota Bharu - Perkhidmatan Penyelenggaraan 01 Jan 2020 - 31 Dec 2022 (3 years) | 2399802 | 0 | 2399802 | 2020 BILLING PLAN/PROJECTION APR: 199983.5; 2020 BILLING PLAN/PROJECTION JUL: 199983.5; 2020 BILLING PLAN/PROJECTION OCT: 199983.5 | 599950.5 | 799934 | 999917.5 | 0 |  | 1799851.5
7 | RHIS-LPPKN | Ongoing | Reproductive Health Information System (RHIS) - LPPKN 1 Nov 2016 - 6 Feb 2020 (3 Years++) | 1901901.21 | 1901901.21 | 0 | [12 empty] | 0 | 0 | 0 | 0 |  | 0
8 | SPP-IPOH | Ongoing | Sistem Pengurusan Pesakit (SPP) Permaisuri Bainun, Ipoh 1 June 2019 - 31 May 2020 (1 Year) | 493499.17 | 283848.22 | 209650.95 | 2020 BILLING PLAN/PROJECTION FEB: 41124.93; 2020 BILLING PLAN/PROJECTION MAR: 41124.93; 2020 BILLING PLAN/PROJECTION APR: 41124.93; 2020 BILLING PLAN/PROJECTION MAY: 41124.93; 2020 BILLING PLAN/PROJECTION JUN: 41124.93 | 205624.65 | 0 | 0 | 0 |  | 4026.3
9 | SPP-TAIPING | Ongoing | SPP V2.6 Implementation Project - Hospital Taiping Perak - HWSW Maint Renewal 14 Sept 2018 - 13 Sept 2020 (2 Years) | 123275.4 | 61637.7 | 61637.7 | 0 | 0 | 30818.85 | 0 | 0 | 0 | 0 | 0 | 30818.85 | 0 | 0 | 0 | 61637.7 | 0 | 0 | 0 |  | 0
10 | SPP-TAIPING | Ongoing | SPP Application Maintenance-Hospital Taiping, Perak - Application Maint Renewal 18 Sept 2018 - 17 Sept 2020 (2 Years) | 180200.424 | 90100.22 | 90100.204 | 0 | 0 | 45050.11 | 0 | 0 | 0 | 0 | 0 | 45050.11 | 0 | 0 | 0 | 90100.22 | 0 | 0 | 0 |  | -0.016
11 | SPP-CAS PHIS | Ongoing | Dataware - SPP CAS PHIS Integration 01 June 2017 - 31 Aug 2020 (3 Years++) | 396556.6 | 396556.6 | 0 | [12 empty] | 0 | 0 | 0 | 0
|  |  |  | 79589439.244 | 36568446.44 | 43020992.804 | 17025.77 | 41124.93 | 2673493.89 | 18352671.787 | 3232093.3 | 292637.49 | 199983.5 | 8747789.34 | 75868.96 | 199983.5 | 0 | 5298350.13 | 39131022.597 | 1434067.01 | 1554006.75 | 0
OTHERS
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | GRAND TOTAL (RM) | 459460005.4662 | 98700892.1 | 360759113.3662 | 4114071.86 | 2556757.85 | 6629073.24 | 25678731.147 | 5747726.22 | 6747234.48 | 1354061.98 | 9870199.82 | 3434976.99 | 343741.93 | 113600 | 6882055 | 73472230.517 | 7829852.7322 | 7313792.47 | 11132684.94 | 0
Note on G9: Aida Rashid: RM909,017.64 -opportunity loss to project
Note on T33: Aida Rashid: Balance to bill vs Total Plan Y2020 - Variance due to GST/SST
Note on E34: Aida Rashid: Original Contract value RM10,123,738.81
Note on T34: Aida Rashid: Balance to bill vs Total Plan Y2020 - Variance due to Possibility for CN in Y2020
Note on T35: Aida Rashid: Balance to bill vs Total Plan Y2020 - Variance due to CN in Y2019 & Y2020
Note on T39: Aida Rashid: Balance to bill vs Total Plan Y2020 - Variance due to CN in Y2019 - RM4,026.30